## Summary
AIA Summary
Build-Up to Columns |  | A | B | C | D = B - C | E | E - D | A - B
|  |  | Debits - Gross Amount (1) |  |  | Credits (2)
|  | Scheduled | Gross |  | Net | Net | Cash | Remaining
# | Category | Value | Total Spend | Retainage | Total Spend | Total Received | Balance | Gross Budget
1 | General Conditions | 650000 | 629748.7583 | 0 | 629748.7583 | 629748.7583 | 0 | 20251.2417
2 | Sitework | 886000 | 886000.0043 | -13347.7456 | 872652.2588 | 872652.2588 | 0 | -0.0043056
3 | Concrete | 1074000 | 1037347.01 | -47363 | 989984.01 | 989984.01 | 0 | 36652.99
4 | Masonry | 9000 | 8964.51 | -800 | 8164.51 | 8164.51 | 0 | 35.49
5 | Metals | 155000 | 100636.91 | -5167.5 | 95469.41 | 95469.41 | 0 | 54363.09
6 | Wood, Plastics And Composites | 1301000 | 1301000 | -37147.813 | 1263852.187 | 1263852.187 | 0 | -1.8626e-09
7 | Thermal And Moisture Protection | 1006000 | 994430.3956 | -81440.4922 | 912989.9033 | 912989.9033 | 0 | 11569.6044
8 | Openings | 805000 | 685050 | -1887.5 | 683162.5 | 683162.5 | 0 | 119950
9 | Finishes | 1040000 | 966900.57 | -66615 | 900285.57 | 900285.57 | 0 | 73099.43
10 | Specialties And Equipment | 430000 | 405599.77 | 0 | 405599.77 | 405599.77 | 0 | 24400.23
11 | Furnishings | 290000 | 224165.55 | 0 | 224165.55 | 224165.55 | 0 | 65834.45
12 | Swimming Pool | 215000 | 206863.6989 | -14294.5989 | 192569.1 | 192569.1 | 0 | 8136.3011
13 | Conveying Equipment | 270000 | 270000 | -25820 | 244180 | 244180 | 0 | 0
14 | Fire Suppression | 197000 | 197000 | -19700 | 177300 | 177300 | 0 | 0
15 | Plumbing/HVAC | 1891000 | 1888406.2856 | -157843.0252 | 1730563.2603 | 1730563.2603 | 0 | 2593.7144
16 | Electrical | 1189000 | 1169838.4233 | -39920 | 1129918.4233 | 1129918.4233 | 0 | 19161.5767
17 | General Liability | 92000 | 92000 | 0 | 92000 | 92000 | 0 | 0
18 | Contractor'S Fee | 300000 | 283333.3333 | -28333.3333 | 255000 | 255000 | 0 | 16666.6667
| Total | 11800000 | 11347285.2192 | -539680.0082 | 10807605.211 | 10807605.211 | 0 | 452714.7808
(1) Total spend on the project.
(2) Balance received from the bank draws.

## Bid
Bid Summary
DESCRIPTION | Budget | Total Spend | Remaining | Percentage | # | Coding
GENERAL CONDITIONS
Mobilization (erosion control, storm water reports) | 22000 | 22000 | 0 | 100% | 1 | Mobilization
Testing and Inspection Services | 11000 | 13295.55 | -2295.55 | 120.9% | 1 | Testing and Inspection Services
Layout/Engineering | 10000 | 0 | 10000 | 0% | 1 | Layout/Engineering
Final Cleanup | 29000 | 0 | 29000 | 0% | 1 | Final Cleanup
Temporary Fencing | 10000 | 6591.5342 | 3408.4658 | 65.92% | 1 | Temporary Fencing
Wash Exterior Windows | 10000 | 0 | 10000 | 0% | 1 | Wash Exterior Windows
Waste Removal Services | 53000 | 60958.33 | -7958.33 | 115% | 1 | Waste Removal Services
Safety | 25000 | 24129.55 | 870.45 | 96.52% | 1 | Safety
Jobsite Material Expenses | 39000 | 46055.084 | -7055.084 | 118.1% | 1 | Jobsite Material Expenses
Rough Hardware | 0 | 0 | 0 | 0% | 1
Jobsite Office Rental | 30000 | 36622.95 | -6622.95 | 122.1% | 1 | Jobsite Office Rental
Temporary Toilets | 0 | 0 | 0 | 0% | 1
Temporary Electric | 0 | 0 | 0 | 0% | 1
Temporary Telephone/Internet | 0 | 0 | 0 | 0% | 1
Temporary Water | 0 | 0 | 0 | 0% | 1
Superintendent | 159000 | 182500 | -23500 | 114.8% | 1 | Superintendent
Per diem | 0 | 0 | 0 | 0% | 1
General Superintendent/PM | 70000 | 66111.1111 | 3888.8889 | 94.44% | 1 | General Superintendent/PM
Jobsite Labor | 50000 | 42379.35 | 7620.65 | 84.76% | 1 | Jobsite Labor
Carpenter | 0 | 0 | 0 | 0% | 1
Gas/Oil/Travel | 25000 | 15740.93 | 9259.07 | 62.96% | 1 | Gas/Oil/Travel
Container Storage Rental | 29000 | 41647.4 | -12647.4 | 143.6% | 1 | Container Storage Rental
Plan Reproduction/Postage | 13000 | 10328.08 | 2671.92 | 79.45% | 1 | Plan Reproduction/Postage
Job Accounting /Administration | 65000 | 61388.8889 | 3611.1111 | 94.44% | 1 | Job Accounting/Administration
SUB TOTAL | 650000 | 629748.7582 | 20251.2417 | 96.88%
SITEWORK
Landscaping and Irrigation (Allowance) | 100000 | 108905.0556 | -8905.0556 | 108.9% | 2 | Landscaping and Irrigation
Earthwork (Allowance) | 300000 | 276834.7807 | 23165.2193 | 92.28% | 2 | Earthwork
Equipment Rental | 160000 | 162660.36 | -2660.36 | 101.7% | 2 | Equipment Rental
SWPPP/Erosion control | 0 | 0 | 0 | 0% | 2
Site Utilities/Storm Drainage | 315000 | 337599.808 | -22599.808 | 107.2% | 2 | Utilities
Patio Storm Drainage | 0 | 0 | 0 | 0% | 2
Spoil Removal | 0 | 0 | 0 | 0% | 2
Striping | 11000 | 0 | 11000 | 0% | 2 | Striping
SUB TOTAL | 886000 | 886000.0043 | -0.0043056 | 100%
CONCRETE
Site and Building Concrete | 975000 | 962934.51 | 12065.49 | 98.76% | 3 | Concrete
Pool Deck Concrete (broom finish, Pool Deck Drains, Included) | 0 | 0 | 0 | 0% | 3
Patio Stamp Concrete | 0 | 0 | 0 | 0% | 3
Termite Control | 13000 | 5412.5 | 7587.5 | 41.63% | 3 | Termite Control
Gypcrete | 86000 | 69000 | 17000 | 80.23% | 3 | Gypcrete
SUB TOTAL | 1074000 | 1037347.01 | 36652.99 | 96.59%
MASONRY
CMU (Dumpster) | 9000 | 8964.51 | 35.49 | 99.61% | 4 | CMU
SUB TOTAL | 9000 | 8964.51 | 35.49 | 99.61%
METALS
Structural Steel Material (Allowance) | 100000 | 96888.91 | 3111.09 | 96.89% | 5 | Structural Steel Material
Sales tax | 0 | 0 | 0 | 0% | 5
Steel Erection | 0 | 0 | 0 | 0% | 5
Stair Handrail Install | 0 | 0 | 0 | 0% | 5
Misc. Steel | 45000 | 3748 | 41252 | 8.329% | 5 | Misc. Steel
Fencing | 0 | 0 | 0 | 0% | 5
Access Structures | 10000 | 0 | 10000 | 0% | 5 | Access Structures
SUB TOTAL | 155000 | 100636.91 | 54363.09 | 64.93%
WOOD, PLASTICS AND COMPOSITES
Framing Material (Allowance) | 514000 | 524045.6 | -10045.6 | 102% | 6 | Framing Material
Framing Labor - (Allowance) | 360000 | 442798.23 | -82798.23 | 123% | 6 | Framing Labor
Simpson Hardware | 24000 | 0 | 24000 | 0% | 6 | Simpson Hardware
Trusses (Allowance) | 253000 | 235796.6 | 17203.4 | 93.2% | 6 | Trusses
Public Area Millwork Material | 150000 | 98359.57 | 51640.43 | 65.57% | 6 | Public Area Millwork Material
BOH Shelving - Included in Millwork. ($5,500.00) | 0 | 0 | 0 | 0% | 6
SUB TOTAL | 1301000 | 1301000 | 1.7462e-10 | 100%
THERMAL AND MOISTURE PROTECTION
Waterproofing/Joint Sealants | 0 | 0 | 0 | 0% | 7
Steel Fireproofing / Fire Caulking | 22000 | 0 | 22000 | 0% | 7 | Steel Fireproofing/Fire Caulking
Roofing | 234000 | 297100 | -63100 | 127% | 7 | Roofing
EFIS/Stone (Allowance) | 580000 | 584233.3956 | -4233.3956 | 100.7% | 7 | EFIS/Stone
Building Insulation | 170000 | 113097 | 56903 | 66.53% | 7 | Building Insulation
SUB TOTAL | 1006000 | 994430.3956 | 11569.6044 | 98.85%
OPENINGS
Doors and Hardware | 300000 | 235079.59 | 64920.41 | 78.36% | 8 | Doors and Hardware
Hollow Metal Doors/Frames/Wood Doors/ Hardware - | 75000 | 0 | 75000 | 0% | 8 | Hollow Doors Hardware
Sales Tax - | 0 | 0 | 0 | 0% | 8
Electronic Locksets - Onity | 82000 | 58967.68 | 23032.32 | 71.91% | 8 | Electronic Locksets
Automatic Sliding Doors | 149000 | 0 | 149000 | 0% | 8 | Automatic Sliding Doors
Aluminum Storefront and Entrances | 0 | 0 | 0 | 0% | 8
Guest room windows (with flashing) | 174000 | 285266.61 | -111266.61 | 163.9% | 8 | Guest Room Windows
Sales tax - Integrity to pay: | 0 | 0 | 0 | 0% | 8
Metal Flashing | 25000 | 105736.12 | -80736.12 | 422.9% | 8 | Metal Flashing
SUB TOTAL | 805000 | 685050 | 119950 | 85.1%
FINISHES
Lay-in Ceiling's Materials | 80000 | 70154.5 | 9845.5 | 87.69% | 9 | Lay-in Ceiling's Materials
Lay-in ceiling Install | 0 | 0 | 0 | 0% | 9
Drywall, RC channel/Soundboard, etc., Materials (Allowance) | 293000 | 262581.86 | 30418.14 | 89.62% | 9 | Drywall Material
Drywall hanging and finishing Labor (Allowance) | 204000 | 124200 | 79800 | 60.88% | 9 | Drywall Labor
Furr downs - | 0 | 0 | 0 | 0% | 9
Painting | 159000 | 146740.58 | 12259.42 | 92.29% | 9 | Painting
VWC Install | 70000 | 75000 | -5000 | 107.1% | 9 | VMC Install
Floor Skim | 0 | 0 | 0 | 0% | 9
Flooring Materials- Carpet/Pad/LVT/Base/Glue (Allowance) | 128000 | 48962.63 | 79037.37 | 38.25% | 9 | Flooring Material
Flooring install | 106000 | 226111 | -120111 | 213.3% | 9 | Flooring Install
Transition/Stair Trim | 0 | 0 | 0 | 0% | 9
Model Room (Change Order) | 0 | 13150 | -13150 | 0% | 9 | Model Room | <--- CHANGE ORDER; ADDED AFTER THE FACT
SUB TOTAL | 1040000 | 966900.57 | 73099.43 | 92.97%
SPECIALTIES AND EQUIPMENT
Fire Extinguishers & Cabinets Materials | 11000 | 5859.97 | 5140.03 | 53.27% | 10 | Fire Extinguisher Material
Toilet Accessories/Toilet Compartments Materials (Allowance) | 60000 | 67658.5199 | -7658.5199 | 112.8% | 10 | Toilet Material
Corner Guard Materials | 0 | 0 | 0 | 0% | 10
Guestroom appliances - owner provided | 0 | 0 | 0 | 0% | 10
Kitchen Equipment (Allowance) | 150000 | 150000 | 0 | 100% | 10 | Kitchen Equipment
Glass Shower Panel Materials | 0 | 0 | 0 | 0% | 10
Glass shower/Surround Install (surrounds and glass doors) | 64000 | 77233.8101 | -13233.8101 | 120.7% | 10 | Glass Shower/Surround Install
Sport Court Equipment - Allowance | 10000 | 0 | 10000 | 0% | 10 | Sport Court Equipment
BBQ Grill (Allowance) | 25000 | 4847.47 | 20152.53 | 19.39% | 10 | BBQ Grill
Fireplace - (Allowance) | 10000 | 0 | 10000 | 0% | 10 | Fireplace
Fire Pit/Install | 0 | 0 | 0 | 0% | 10
Fitness Equipment (Allowance) | 0 | 0 | 0 | 0% | 10
Laundry Equipment (Allowance) | 100000 | 100000 | 0 | 100% | 10 | Laundry Equipment
SUB TOTAL | 430000 | 405599.77 | 24400.23 | 94.33%
FURNISHINGS
Vanity Bases & Tops - quoted as install only | 0 | 0 | 0 | 0% | 11
Cultured Marble Tub/Shower Surrounds and Shower Pan Material - | 123000 | 42388.3 | 80611.7 | 34.46% | 11 | Tub/Shower Surrounds and Pan
Quartz materials and install public areas/GR window sills - | 64000 | 90864.15 | -26864.15 | 142% | 11 | Quartz Materials & Public Install
Quartz materials for guestrooms. - quoted as install only | 0 | 0 | 0 | 0% | 11
Vanity install | 0 | 0 | 0 | 0% | 11
FFE Installation | 80000 | 90913.1 | -10913.1 | 113.6% | 11 | FF&E Installation
Hotel Rooms for installers | 0 | 0 | 0 | 0% | 11
Public Area Installation (Allowance) | 7000 | 0 | 7000 | 0% | 11 | Public Area Installation
Fitness Room Mirrors with Installation | 16000 | 0 | 16000 | 0% | 11 | Fitness Room Mirrors w/ Install
SUB TOTAL | 290000 | 224165.55 | 65834.45 | 77.3%
SWIMMING POOL
Swimming Pool (Allowance) | 215000 | 206863.6989 | 8136.3011 | 96.22% | 12 | Swimming Pool
SUB TOTAL | 215000 | 206863.6989 | 8136.3011 | 96.22%
CONVEYING EQUIPMENT
Elevators (Allowance) | 249000 | 258200 | -9200 | 103.7% | 13 | Elevators
Elevator Temporary Usage | 0 | 0 | 0 | 0% | 13
Elevator Safety | 0 | 0 | 0 | 0% | 13
Linen Chute | 21000 | 11800 | 9200 | 56.19% | 13 | Linen Chute
SUB TOTAL | 270000 | 270000 | 2.9104e-11 | 100%
FIRE SUPPRESSION
FIRE SUPPRESSION | 197000 | 197000 | 0 | 100% | 14 | Fire Suppression
SUB TOTAL | 197000 | 197000 | 0 | 100%
PLUMBING/HVAC
Mechanical | 749000 | 756742.6656 | -7742.6656 | 101% | 15 | Mechanical
Plumbing | 900000 | 908988.1 | -8988.1 | 101% | 15 | Plumbing
VTAC's (Allowance) | 242000 | 222675.52 | 19324.48 | 92.01% | 15 | VTACs
Sub Total | 1891000 | 1888406.2856 | 2593.7144 | 99.86%
ELECTRICAL
Base Bid (Allowance) | 895000 | 967588.4233 | -72588.4233 | 108.1% | 16 | Electrical
Structural Cabling | 106000 | 56250 | 49750 | 53.07% | 16 | Structural Cabling
Fire alarm | 108000 | 146000 | -38000 | 135.2% | 16 | Fire Alarm
Audio/Visual | 0 | 0 | 0 | 0% | 16
Light Poles | 38000 | 0 | 38000 | 0% | 16 | Light Poles
Security Monitoring System | 21000 | 0 | 21000 | 0% | 16 | Security Monitoring System
Phone System | 21000 | 0 | 21000 | 0% | 16 | Phone System
Utilities Company Fees | 0 | 0 | 0 | 0% | 16
Subtotal | 1189000 | 1169838.4233 | 19161.5767 | 98.39%
Subtotal | 11408000 | 10971951.8859 | 436048.1141 | 96.18%
Contractor Contingency | 0 | 0 | 0 | 0%
General Libility & Builder's Risk (Allowance) | 92000 | 92000 | 0 | 100% | 17 | General Liability
Contractor's Fee | 300000 | 283333.3333 | 16666.6667 | 94.44% | 18 | Contractor's Fee
Utility Service or Tap Fees, Permit Fee (By Owner) | 0 | 0 | 0 | 0%
Bond Premium | 0 | 0 | 0 | 0%
Subtotal | 392000 | 375333.3333 | 16666.6667 | 95.75%
Total Construction Costs | 11800000 | 11347285.2192 | 452714.7808 | 96.16%

## Detail
12556
Detailed Spend
[5 empty] | Debits |  |  | Credits |  |  | Other Information
Date | G703 # | Draw | Description | Commentary or Counterparty | Gross Amount | Retainage | Net Amount | Gross Amount | Retainage | Net Amount | Bid Line Item | Counterparty | Paid By | Backup | Received K1 | Type | Unique ID | Unique ID
1. General Conditions
| 1 | 1 | Draw 1 Funds |  |  |  |  | 36429.0243 | 0 | 36429.0243
| 1 | 2 | Draw 2 Funds |  |  |  |  | 51562.51 | 0 | 51562.51
| 1 | 3 | Draw 3 Funds |  |  |  |  | 43878.26 | 0 | 43878.26
| 1 | 4 | Draw 4 Funds |  |  |  |  | 43213.34 | 0 | 43213.34
| 1 | 5 | Draw 5 Funds |  |  |  |  | 17500 | 0 | 17500
| 1 | 6 | Draw 6 Funds - Reimbursements |  |  |  |  | 25932.36 | 0 | 25932.36
| 1 | 6 | Draw 6 Funds - To Be Paid |  |  |  |  | 19000 | 0 | 19000
| 1 | 7 | Draw 7 Funds - Reimbursements |  |  |  |  | 13132.18 | 0 | 13132.18
| 1 | 7 | Draw 7 Funds - To Be Paid |  |  |  |  | 17500 | 0 | 17500
| 1 | 8 | Draw 8 Funds - Reimbursements |  |  |  |  | 12703.55 | 0 | 12703.55
| 1 | 8 | Draw 8 Funds - To Be Paid |  |  |  |  | 17500 | 0 | 17500
| 1 | 9 | Draw 9 Funds - Reimbursements |  |  |  |  | 11787.31 | 0 | 11787.31
| 1 | 9 | Draw 9 Funds - To Be Paid |  |  |  |  | 17500 | 0 | 17500
| 1 | 10 | Draw 10 Funds - Reimbursements |  |  |  |  | 13581.8 | 0 | 13581.8
| 1 | 11 | Draw 11 Funds - Reimbursements |  |  |  |  | 26352.54 | 0 | 26352.54
| 1 | 11 | Draw 11 Funds - To Be Paid |  |  |  |  | 17500 | 0 | 17500
| 1 | 12 | Draw 12 Funds - Reimbursements |  |  |  |  | 10377.124 | 0 | 10377.124
| 1 | 12 | Draw 12 Funds - To Be Paid |  |  |  |  | 17500 | 0 | 17500
| 1 | 13 | Draw 13 Funds - Reimbursements |  |  |  |  | 18363.28 | 0 | 18363.28
| 1 | 13 | Draw 13 Funds - To Be Paid |  |  |  |  | 17500 | 0 | 17500
| 1 | 14 | Draw 14 Funds - Reimbursements |  |  |  |  | 31114.26 | 0 | 31114.26
| 1 | 14 | Draw 14 Funds - To Be Paid |  |  |  |  | 17500 | 0 | 17500
| 1 | 15 | Draw 15 Funds - Reimbursements |  |  |  |  | 29893.12 | 0 | 29893.12
| 1 | 15 | Draw 15 Funds - To Be Paid |  |  |  |  | 35000 | 0 | 35000
| 1 | 16 | Draw 16 Funds - Reimbursements |  |  |  |  | 31226.14 | 0 | 31226.14
| 1 | 16 | Draw 16 Funds - To Be Paid |  |  |  |  | 10000 | 0 | 10000
| 1 | 17 | Draw 17 Funds - Reimbursements |  |  |  |  | 16201.96 | 0 | 16201.96
| 1 | 17 | Draw 17 Funds - To Be Paid |  |  |  |  | 10000 | 0 | 10000
2024-07-29 | 1 | 1 | Blueprint Printing | Stewart Engineering | 278.74 | 0 | 278.74 |  |  |  | Plan Reproduction/Postage | Stewart Engineering | Rush | 10001 | NA | Credit Card | RIW-CFR-01-001
2024-08-02 | 1 | 1 | Blueprint Printing | Stewart Engineering | 321.5 | 0 | 321.5 |  |  |  | Plan Reproduction/Postage | Stewart Engineering | Rush | 10002 | NA | Credit Card | RIW-CFR-01-002
2024-08-02 | 1 | 1 | Temporary Toilets | A-1 Little John | 211.63 | 0 | 211.63 |  |  |  | Container Storage Rental | A-1 Little John | Rush | 10003 | NA | Credit Card | RIW-CFR-01-003
2024-08-07 | 1 | 1 | Temporary Fencing (Chain Link) | Viking Fence Co | 5179.6542 | 0 | 5179.6542 |  |  |  | Temporary Fencing | Viking Fence | Jai | 10004 | NA | Credit Card | RIW-CFR-01-004
| 1 | 1 | Mobilization | Boulder Construction | 22000 | 0 | 22000 |  |  |  | Mobilization | Boulder Construction | RI Waxahachie | NA | NA | Fee | RIW-CFR-01-005
| 1 | 1 | Project Manager | Boulder Construction - For August 2024 | 4375 | 0 | 4375 |  |  |  | General Superintendent/PM | Boulder Construction | RI Waxahachie | NA | NA | Fee | RIW-CFR-01-006
| 1 | 1 | Job Accounting / Administration | Boulder Construction - For August 2024 | 4062.5 | 0 | 4062.5 |  |  |  | Job Accounting/Administration | Boulder Construction | RI Waxahachie | NA | NA | Fee | RIW-CFR-01-007
| 1 | 2 | Job Supervisor | For Two Weeks Through 9/9/24 | 5000 | 0 | 5000 |  |  |  | Superintendent | Boulder Construction | RI Waxahachie | NA | NA | Fee | RIW-CFR-01-008
| 1 | 2 | Job Supervisor | For Remaining of September 2024 | 7500 | 0 | 7500 |  |  |  | Superintendent | Boulder Construction | RI Waxahachie | NA | NA | Fee | RIW-CFR-01-009
| 1 | 2 | Project Manager | Boulder Construction - For September 2024 | 4375 | 0 | 4375 |  |  |  | General Superintendent/PM | Boulder Construction | RI Waxahachie | NA | NA | Fee | RIW-CFR-01-010
| 1 | 2 | Job Accounting / Administration | Boulder Construction - For September 2024 | 4062.5 | 0 | 4062.5 |  |  |  | Job Accounting/Administration | Boulder Construction | RI Waxahachie | NA | NA | Fee | RIW-CFR-01-011
2024-10-04 | 1 | 2 | Temporary Fencing (Chain Link) | Viking Fence Co - Additional Payment | 110.41 | 0 | 110.41 |  |  |  | Temporary Fencing | Viking Fence | Jai | 10005 | NA | Credit Card | RIW-CFR-01-012
2024-09-30 | 1 | 2 | Blueprint Printing | Stewart Engineering | 617.28 | 0 | 617.28 |  |  |  | Plan Reproduction/Postage | Stewart Engineering | Rush | 10016 | NA | Credit Card | RIW-CFR-01-013
2024-08-30 | 1 | 2 | Temporary Toilets - Recurring Payment | A-1 Little John | 130.44 | 0 | 130.44 |  |  |  | Container Storage Rental | A-1 Little John | Rush | 10006 | NA | Credit Card | RIW-CFR-01-014
2024-09-27 | 1 | 2 | Temporary Toilets - Recurring Payment | A-1 Little John | 130.44 | 0 | 130.44 |  |  |  | Container Storage Rental | A-1 Little John | Rush | 10007 | NA | Credit Card | RIW-CFR-01-015
2024-08-21 | 1 | 2 | OpenSpace - Camera | Testing and Inspection Services - Monitoring | 969.9 | 0 | 969.9 |  |  |  | Testing and Inspection Services | OpenSpace | Jai | 10008 | NA | Credit Card | RIW-CFR-01-016
2024-08-21 | 1 | 2 | OpenSpace - Camera Accessories | Testing and Inspection Services - Monitoring | 106.21 | 0 | 106.21 |  |  |  | Testing and Inspection Services | OpenSpace | Jai | 10009 | NA | Credit Card | RIW-CFR-01-017
2024-10-04 | 1 | 2 | OpenSpace - Subscription | Testing and Inspection Services - Monitoring | 5863 | 0 | 5863 |  |  |  | Testing and Inspection Services | OpenSpace | Jai | 10010 | NA | Credit Card | RIW-CFR-01-018
2024-08-06 | 1 | 2 | Construction Signage & Safety Equipment |  | 340.05 | 0 | 340.05 |  |  |  | Jobsite Material Expenses | Alibaba | Uma | 10011 | NA | Credit Card | RIW-CFR-01-019
2024-08-06 | 1 | 2 | Construction Signage & Safety Equipment |  | 26.96 | 0 | 26.96 |  |  |  | Jobsite Material Expenses | Amazon | Uma | 10012 | NA | Credit Card | RIW-CFR-01-020
2024-08-06 | 1 | 2 | Construction Signage & Safety Equipment |  | 64.32 | 0 | 64.32 |  |  |  | Jobsite Material Expenses | Amazon | Uma | 10013 | NA | Credit Card | RIW-CFR-01-021
2024-08-02 | 1 | 2 | Construction Signage & Safety Equipment |  | 82.91 | 0 | 82.91 |  |  |  | Jobsite Material Expenses | Amazon | Uma | 10014 | NA | Credit Card | RIW-CFR-01-022
2024-08-04 | 1 | 2 | Construction Signage & Safety Equipment |  | 140.62 | 0 | 140.62 |  |  |  | Jobsite Material Expenses | Etsy | Uma | 10015 | NA | Credit Card | RIW-CFR-01-023
2024-08-25 | 1 | 2 | Water Station Tent | Required by Safety Consultant | 215.42 | 0 | 215.42 |  |  |  | Jobsite Material Expenses | Home Depot | Jai |  | NA | Credit Card | RIW-CFR-01-024
2024-07-09 | 1 | 2 | Notary Fees | For Draw | 10 | 0 | 10 |  |  |  | Plan Reproduction/Postage | The UPS Store | Rush |  | NA | Credit Card | RIW-CFR-01-025
2024-08-22 | 1 | 2 | Notary Fees | For Draw | 10 | 0 | 10 |  |  |  | Plan Reproduction/Postage | The UPS Store | Rush |  | NA | Credit Card | RIW-CFR-01-026
2024-08-23 | 1 | 2 | Misc. Jobsite Materials | From Office Depot | 143.94 | 0 | 143.94 |  |  |  | Jobsite Material Expenses | Office Depot | Rush |  | NA | Credit Card | RIW-CFR-01-027
2024-09-04 | 1 | 2 | Misc. Jobsite Materials | From Home Depot | 194.69 | 0 | 194.69 |  |  |  | Jobsite Material Expenses | Home Depot | Rush |  | NA | Credit Card | RIW-CFR-01-028
2024-08-10 | 1 | 2 | Misc. Jobsite Materials | From Home Depot | 18.38 | 0 | 18.38 |  |  |  | Jobsite Material Expenses | Home Depot | Rush |  | NA | Credit Card | RIW-CFR-01-029
2024-09-20 | 1 | 2 | Misc. Jobsite Materials | From Home Depot | 17.54 | 0 | 17.54 |  |  |  | Jobsite Material Expenses | Home Depot | Rush |  | NA | Credit Card | RIW-CFR-01-030
| 1 | 2 | Project Manager | Boulder Construction - For October 2024 | 4375 | 0 | 4375 |  |  |  | General Superintendent/PM | Boulder Construction | RI Waxahachie | NA | NA | Fee | RIW-CFR-01-031
| 1 | 2 | Job Accounting / Administration | Boulder Construction - For October 2024 | 4062.5 | 0 | 4062.5 |  |  |  | Job Accounting/Administration | Boulder Construction | RI Waxahachie | NA | NA | Fee | RIW-CFR-01-032
| 1 | 2 | Job Supervisor | For October 2024 | 10000 | 0 | 10000 |  |  |  | Superintendent | Boulder Construction | RI Waxahachie | NA | NA | Fee | RIW-CFR-01-033
2024-11-12 | 1 | 2/3 | Cornerstone Safety | Per Ownership Requirements | 3039.85 | 0 | 3039.85 |  |  |  | Safety | Cornerstone Safety | Rush | 10017 | NA | Credit Card | RIW-CFR-01-034
2024-11-12 | 1 | 3 | Cornerstone Safety | Per Ownership Requirements | 1544.85 | 0 | 1544.85 |  |  |  | Safety | Cornerstone Safety | Jai | 10018 | NA | Credit Card | RIW-CFR-01-035
2024-11-12 | 1 | 3 | Cornerstone Safety | Per Ownership Requirements | 1544.85 | 0 | 1544.85 |  |  |  | Safety | Cornerstone Safety | Jai | 10019 | NA | Credit Card | RIW-CFR-01-036
2024-11-22 | 1 | 3 | Jobsite Storage Container | From Willscot | 150.74 | 0 | 150.74 |  |  |  | Container Storage Rental | Willscot | Rush | 10116 | NA | Credit Card | RIW-CFR-01-037
2024-10-11 | 1 | 3 | Jobsite Storage Container | From Willscot | 781.84 | 0 | 781.84 |  |  |  | Container Storage Rental | Willscot | Rush | 10117 | NA | Credit Card | RIW-CFR-01-038
2024-10-25 | 1 | 3 | Jobsite Storage Container | From Willscot | 150.74 | 0 | 150.74 |  |  |  | Container Storage Rental | Willscot | Rush | 10114 | NA | Credit Card | RIW-CFR-01-039
2024-11-22 | 1 | 3 | Jobsite Storage Container | From Willscot | 150.74 | 0 | 150.74 |  |  |  | Container Storage Rental | Willscot | Rush | 10115 | NA | Credit Card | RIW-CFR-01-040
2024-10-11 | 1 | 3 | Jobsite Storage Container | From Willscot | 781.84 | 0 | 781.84 |  |  |  | Container Storage Rental | Willscot | Rush | 10118 | NA | Credit Card | RIW-CFR-01-041
2024-10-25 | 1 | 3 | Jobsite Storage Container | From Willscot | 150.74 | 0 | 150.74 |  |  |  | Container Storage Rental | Willscot | Rush | 10113 | NA | Credit Card | RIW-CFR-01-042
2024-11-19 | 1 | 3 | Jobsite Office | From Willscot | 817.83 | 0 | 817.83 |  |  |  | Jobsite Office Rental | Willscot | Rush | 10119 | NA | Credit Card | RIW-CFR-01-043
2024-10-23 | 1 | 3 | Jobsite Office | From Willscot | 1997.75 | 0 | 1997.75 |  |  |  | Jobsite Office Rental | Willscot | Rush | 10120 | NA | Credit Card | RIW-CFR-01-044
2024-11-22 | 1 | 3 | Temporary Toilets - Recurring Payment | A-1 Little John | 260.88 | 0 | 260.88 |  |  |  | Container Storage Rental | A-1 Little John | Rush | 10096 | NA | Credit Card | RIW-CFR-01-045
2024-10-25 | 1 | 3 | Temporary Toilets - Recurring Payment | A-1 Little John | 342.07 | 0 | 342.07 |  |  |  | Container Storage Rental | A-1 Little John | Rush | 10081 | NA | Credit Card | RIW-CFR-01-046
2024-10-09 | 1 | 3 | Temporary Fencing (Chain Link) | Viking Fence Co | 457.36 | 0 | 457.36 |  |  |  | Temporary Fencing | Viking Fence | Jai | 10063 | NA | Credit Card | RIW-CFR-01-047
2024-10-27 | 1 | 3 | Temporary Fencing (Chain Link) | Viking Fence Co | 98.54 | 0 | 98.54 |  |  |  | Temporary Fencing | Viking Fence | Jai | 10080 | NA | Credit Card | RIW-CFR-01-048
2024-11-21 | 1 | 3 | Misc. Jobsite Materials | From Home Depot | 430.19 | 0 | 430.19 |  |  |  | Jobsite Material Expenses | Home Depot | Boulder AMEX | 10094 | NA | Credit Card | RIW-CFR-01-049
2024-12-02 | 1 | 3 | Misc. Jobsite Materials | From Home Depot | 104.67 | 0 | 104.67 |  |  |  | Jobsite Material Expenses | Home Depot | Boulder AMEX | 10093 | NA | Credit Card | RIW-CFR-01-050
2024-12-06 | 1 | 3 | Misc. Jobsite Materials | From Home Depot | 200.47 | 0 | 200.47 |  |  |  | Jobsite Material Expenses | Home Depot | Boulder AMEX | 10095 | NA | Credit Card | RIW-CFR-01-051
2024-11-25 | 1 | 3 | Misc. Jobsite Materials | From Home Depot | 23.6 | 0 | 23.6 |  |  |  | Jobsite Material Expenses | Home Depot | Boulder AMEX | 10129 | NA | Credit Card | RIW-CFR-01-052
2024-10-25 | 1 | 3 | Misc. Jobsite Materials | From Home Depot | 238.58 | 0 | 238.58 |  |  |  | Jobsite Material Expenses | Home Depot | Rush | 10130 | NA | Credit Card | RIW-CFR-01-053
2024-10-16 | 1 | 3 | Misc. Jobsite Materials | From Home Depot | 112.11 | 0 | 112.11 |  |  |  | Jobsite Material Expenses | Home Depot | Rush | 10127 | NA | Credit Card | RIW-CFR-01-054
2024-10-15 | 1 | 3 | Misc. Jobsite Materials | From Home Depot | 56.13 | 0 | 56.13 |  |  |  | Jobsite Material Expenses | Home Depot | Rush |  | NA | Credit Card | RIW-CFR-01-055
2024-11-01 | 1 | 3 | Misc. Jobsite Materials | From Home Depot | 45.4 | 0 | 45.4 |  |  |  | Jobsite Material Expenses | Home Depot | Rush | 10121 | NA | Credit Card | RIW-CFR-01-056
2024-10-11 | 1 | 3 | Misc. Jobsite Materials | From Home Depot | 83.67 | 0 | 83.67 |  |  |  | Jobsite Material Expenses | Home Depot | Rush | 10082 | NA | Credit Card | RIW-CFR-01-057
2024-11-18 | 1 | 3 | Misc. Jobsite Materials | From Home Depot | 207.27 | 0 | 207.27 |  |  |  | Jobsite Material Expenses | Home Depot | Rush |  | NA | Credit Card | RIW-CFR-01-058
2024-10-30 | 1 | 3 | Misc. Jobsite Materials | From Home Depot | 202.58 | 0 | 202.58 |  |  |  | Jobsite Material Expenses | Home Depot | Jai | 10151 | NA | Credit Card | RIW-CFR-01-059
2024-10-15 | 1 | 3 | Misc. Jobsite Materials | From Home Depot | 48.84 | 0 | 48.84 |  |  |  | Jobsite Material Expenses | Home Depot | Rush |  | NA | Credit Card | RIW-CFR-01-060
2024-11-23 | 1 | 3 | Misc. Jobsite Materials | From Lowe's | 331.7 | 0 | 331.7 |  |  |  | Jobsite Material Expenses | Lowe's | Boulder AMEX | 10162 | NA | Credit Card | RIW-CFR-01-061
2024-11-13 | 1 | 3 | Sidewalk Closed Signs - Per City Requirements | From Lite & Barricade | 151.55 | 0 | 151.55 |  |  |  | Jobsite Material Expenses | Lite & Barricade | Rush | 10145 | NA | Credit Card | RIW-CFR-01-062
2024-11-01 | 1 | 3 | Diesel for Equipment | Job Supervisor | 1000 | 0 | 1000 |  |  |  | Gas/Oil/Travel | Maddox Sullivan | Boulder | 10155 | NA | Check | RIW-CFR-01-063
2024-11-21 | 1 | 3 | Jobsite Dumpster | From Advantage Waste Disposal | 724.74 | 0 | 724.74 |  |  |  | Waste Removal Services | Advantage Waste | Rush | 10089 | NA | Credit Card | RIW-CFR-01-064
2024-10-31 | 1 | 3 | Jobsite Dumpster | From Advantage Waste Disposal | 206 | 0 | 206 |  |  |  | Waste Removal Services | Advantage Waste | Rush | 10083 | NA | Credit Card | RIW-CFR-01-065
2024-10-14 | 1 | 3 | Jobsite Dumpster | From Advantage Waste Disposal | 724.74 | 0 | 724.74 |  |  |  | Waste Removal Services | Advantage Waste | Rush |  | NA | Credit Card | RIW-CFR-01-066
2024-11-01 | 1 | 3 | Jobsite Dumpster | From Advantage Waste Disposal | 1540.74 | 0 | 1540.74 |  |  |  | Waste Removal Services | Advantage Waste | Rush | 10084 | NA | Credit Card | RIW-CFR-01-067
2024-11-29 | 1 | 3 | Jobsite Dumpster | From Advantage Waste Disposal | 703.63 | 0 | 703.63 |  |  |  | Waste Removal Services | Advantage Waste | RI Waxahachie | 10090 | NA | ACH | RIW-CFR-01-068
2024-12-05 | 1 | 3 | Jobsite Dumpster | From Advantage Waste Disposal | 703.63 | 0 | 703.63 |  |  |  | Waste Removal Services | Advantage Waste | RI Waxahachie | 10091 | NA | ACH | RIW-CFR-01-069
2024-12-02 | 1 | 3 | Security Cameras | Birdseye Surveillance | 1665.5 | 0 | 1665.5 |  |  |  | Jobsite Material Expenses | Birdseye Surveillance | RI Waxahachie | 10079 | NA | ACH | RIW-CFR-01-070
2024-10-10 | 1 | 3 | Notary Fees | For Draw | 10 | 0 | 10 |  |  |  | Plan Reproduction/Postage | The UPS Store | Rush | 10153 | NA | Credit Card | RIW-CFR-01-071
| 1 | 3 | Job Supervisor | For November 2024 | 10000 | 0 | 10000 |  |  |  | Superintendent | Boulder Construction | RI Waxahachie | NA | NA | Fee | RIW-CFR-01-072
| 1 | 3 | Job Supervisor | For December 2024 | 10000 | 0 | 10000 |  |  |  | Superintendent | Boulder Construction | RI Waxahachie | NA | NA | Fee | RIW-CFR-01-073
| 1 | 3 | Project Manager | Boulder Construction - For November 2024 (True Up Prior - 18 Mo) | 2430.5556 | 0 | 2430.5556 |  |  |  | General Superintendent/PM | Boulder Construction | RI Waxahachie | NA | NA | Fee | RIW-CFR-01-074
| 1 | 3 | Job Accounting / Administration | Boulder Construction - For November 2024 (True Up Prior - 18 Mo) | 2256.9444 | 0 | 2256.9444 |  |  |  | Job Accounting/Administration | Boulder Construction | RI Waxahachie | NA | NA | Fee | RIW-CFR-01-075
2024-10-24 | 1 | 3 | Blueprint Printing | Stewart Engineering | 399.4 | 0 | 399.4 |  |  |  | Plan Reproduction/Postage | Stewart Engineering | Jai | 10154 | NA | Credit Card | RIW-CFR-01-076
| 1 | 4 | Job Supervisor | For January 2025 | 10000 | 0 | 10000 |  |  |  | Superintendent | Boulder Construction | RI Waxahachie | NA | NA | Fee | RIW-CFR-01-077
| 1 | 4 | Project Manager | Boulder Construction - For December 2024 | 3888.8889 | 0 | 3888.8889 |  |  |  | General Superintendent/PM | Boulder Construction | RI Waxahachie | NA | NA | Fee | RIW-CFR-01-078
| 1 | 4 | Job Accounting / Administration | Boulder Construction - For December 2024 | 3611.1111 | 0 | 3611.1111 |  |  |  | Job Accounting/Administration | Boulder Construction | RI Waxahachie | NA | NA | Fee | RIW-CFR-01-079
| 1 | 4 | Project Manager | Boulder Construction - For January 2025 | 3888.8889 | 0 | 3888.8889 |  |  |  | General Superintendent/PM | Boulder Construction | RI Waxahachie | NA | NA | Fee | RIW-CFR-01-080
| 1 | 4 | Job Accounting / Administration | Boulder Construction - For January 2025 | 3611.1111 | 0 | 3611.1111 |  |  |  | Job Accounting/Administration | Boulder Construction | RI Waxahachie | NA | NA | Fee | RIW-CFR-01-081
2024-12-29 | 1 | 4 | Cornerstone Safety | Per Ownership Requirements | 1500 | 0 | 1500 |  |  |  | Safety | Cornerstone Safety | Jai | 10164 | NA | Credit Card | RIW-CFR-01-082
2025-01-10 | 1 | 4 | Cornerstone Safety | Per Ownership Requirements | 1500 | 0 | 1500 |  |  |  | Safety | Cornerstone Safety | Jai | 10208 | NA | Credit Card | RIW-CFR-01-083
2024-12-18 | 1 | 4 | Blueprint Printing | Office Depot | 5.54 | 0 | 5.54 |  |  |  | Plan Reproduction/Postage | Office Depot | Boulder AMEX | 10185 | NA | Credit Card | RIW-CFR-01-084
2024-12-18 | 1 | 4 | Blueprint Printing | Office Depot | 20.5 | 0 | 20.5 |  |  |  | Plan Reproduction/Postage | Office Depot | Boulder AMEX | 10186 | NA | Credit Card | RIW-CFR-01-085
2024-12-09 | 1 | 4 | Jobsite Labor | Clean Up | 380 | 0 | 380 |  |  |  | Jobsite Labor | Rodolfo Rios | RI Waxahachie | 10187 | NA | Check | RIW-CFR-01-086
2024-12-13 | 1 | 4 | Jobsite Labor | Clean Up | 950 | 0 | 950 |  |  |  | Jobsite Labor | Rodolfo Rios | RI Waxahachie | 10188 | NA | Check | RIW-CFR-01-087
2024-12-20 | 1 | 4 | Jobsite Labor | Clean Up | 370 | 0 | 370 |  |  |  | Jobsite Labor | Rodolfo Rios | RI Waxahachie | 10189 | NA | Check | RIW-CFR-01-088
2024-12-27 | 1 | 4 | Jobsite Labor | Clean Up | 475 | 0 | 475 |  |  |  | Jobsite Labor | Rodolfo Rios | RI Waxahachie | 10190 | NA | Check | RIW-CFR-01-089
2025-01-03 | 1 | 4 | Jobsite Labor | Clean Up | 807.5 | 0 | 807.5 |  |  |  | Jobsite Labor | Rodolfo Rios | RI Waxahachie | 10191 | NA | Check | RIW-CFR-01-090
2024-12-17 | 1 | 4 | Jobsite Dumpster | From Advantage Waste Disposal | 807.19 | 0 | 807.19 |  |  |  | Waste Removal Services | Advantage Waste | Boulder AMEX | 10192 | NA | Credit Card | RIW-CFR-01-091
2024-12-31 | 1 | 4 | Jobsite Dumpster | From Advantage Waste Disposal | 990.11 | 0 | 990.11 |  |  |  | Waste Removal Services | Advantage Waste | Boulder AMEX | 10193 | NA | Credit Card | RIW-CFR-01-092
2025-01-07 | 1 | 4 | Jobsite Dumpster | From Advantage Waste Disposal | 811.93 | 0 | 811.93 |  |  |  | Waste Removal Services | Advantage Waste | Boulder AMEX | 10194 | NA | Credit Card | RIW-CFR-01-093
2024-12-29 | 1 | 4 | Security Cameras | Birdseye Surveillance | 1515.5 | 0 | 1515.5 |  |  |  | Jobsite Material Expenses | Birdseye Surveillance | Boulder AMEX | 10195 | NA | Credit Card | RIW-CFR-01-094
2024-12-20 | 1 | 4 | Jobsite Storage Container | From Willscot | 150.74 | 0 | 150.74 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10196 | NA | Credit Card | RIW-CFR-01-095
2024-12-20 | 1 | 4 | Jobsite Storage Container | From Willscot | 150.74 | 0 | 150.74 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10197 | NA | Credit Card | RIW-CFR-01-096
2024-12-17 | 1 | 4 | Jobsite Office | From Willscot | 817.83 | 0 | 817.83 |  |  |  | Jobsite Office Rental | Willscot | Rush | 10198 | NA | Credit Card | RIW-CFR-01-097
2024-12-26 | 1 | 4 | Temporary Toilets - Recurring Payment | A-1 Little John | 260.88 | 0 | 260.88 |  |  |  | Container Storage Rental | A-1 Little John | Rush | 10207 | NA | Credit Card | RIW-CFR-01-098
2024-12-12 | 1 | 4 | Misc. Jobsite Materials | From Home Depot | 71.87 | 0 | 71.87 |  |  |  | Jobsite Material Expenses | Home Depot | Boulder AMEX | 10200 | NA | Credit Card | RIW-CFR-01-099
2024-12-18 | 1 | 4 | Misc. Jobsite Materials | From Home Depot | 115.41 | 0 | 115.41 |  |  |  | Jobsite Material Expenses | Home Depot | Boulder AMEX | 10201 | NA | Credit Card | RIW-CFR-01-100
2024-12-02 | 1 | 4 | Procore Subscription | For Jobsite Reporting | 6502.6 | 0 | 6502.6 |  |  |  | Jobsite Material Expenses | Procore | Boulder AMEX | 10217 | NA | Credit Card | RIW-CFR-01-101
2024-12-11 | 1 | 4 | Notary Fees | For Draw | 10 | 0 | 10 |  |  |  | Plan Reproduction/Postage | The UPS Store | Boulder AMEX |  | NA | Credit Card | RIW-CFR-01-102
| 1 | 5 | Job Supervisor | For February 2025 | 10000 | 0 | 10000 |  |  |  | Superintendent | Boulder Construction | RI Waxahachie | NA | NA | Fee | RIW-CFR-01-103
| 1 | 5 | Project Manager | Boulder Construction - For February 2025 | 3888.8889 | 0 | 3888.8889 |  |  |  | General Superintendent/PM | Boulder Construction | RI Waxahachie | NA | NA | Fee | RIW-CFR-01-104
| 1 | 5 | Job Accounting / Administration | Boulder Construction - For February 2025 | 3611.1111 | 0 | 3611.1111 |  |  |  | Job Accounting/Administration | Boulder Construction | RI Waxahachie | NA | NA | Fee | RIW-CFR-01-105
2025-01-14 | 1 | 6 | Notary Fees | For Draw | 10 | 0 | 10 |  |  |  | Plan Reproduction/Postage | The UPS Store | Boulder AMEX |  | NA | Credit Card | RIW-CFR-01-106
2025-01-15 | 1 | 6 | Jobsite Dumpster | From Waste Connections | 1216.12 | 0 | 1216.12 |  |  |  | Waste Removal Services | Waste Connections | Boulder AMEX | 10223 | NA | Credit Card | RIW-CFR-01-107
2025-01-22 | 1 | 6 | Jobsite Dumpster | From Waste Connections | 1 | 0 | 1 |  |  |  | Waste Removal Services | Waste Connections | Boulder AMEX | 10224 | NA | Credit Card | RIW-CFR-01-108
2025-01-22 | 1 | 6 | Jobsite Dumpster | From Waste Connections | 1009.79 | 0 | 1009.79 |  |  |  | Waste Removal Services | Waste Connections | Boulder AMEX | 10225 | NA | Credit Card | RIW-CFR-01-109
2025-01-22 | 1 | 6 | Jobsite Dumpster | From Waste Connections | 1149.9 | 0 | 1149.9 |  |  |  | Waste Removal Services | Waste Connections | Boulder AMEX | 10226 | NA | Credit Card | RIW-CFR-01-110
2025-02-13 | 1 | 6 | Jobsite Dumpster | From Waste Connections | 943.58 | 0 | 943.58 |  |  |  | Waste Removal Services | Waste Connections | Boulder AMEX | 10227 | NA | Credit Card | RIW-CFR-01-111
2025-02-13 | 1 | 6 | Jobsite Dumpster | From Waste Connections | 1009.79 | 0 | 1009.79 |  |  |  | Waste Removal Services | Waste Connections | Boulder AMEX | 10228 | NA | Credit Card | RIW-CFR-01-112
2025-01-14 | 1 | 6 | Jobsite Office - Recurring Rental | From Willscot | 817.83 | 0 | 817.83 |  |  |  | Jobsite Office Rental | Willscot | Boulder AMEX | 10242 | NA | Credit Card | RIW-CFR-01-113
2025-01-16 | 1 | 6 | Jobsite Storage Container - Rental + Drop Off | From Willscot | 1031.62 | 0 | 1031.62 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10243 | NA | Credit Card | RIW-CFR-01-114
2025-01-17 | 1 | 6 | Jobsite Storage Container - Recurring Rental | From Willscot | 150.74 | 0 | 150.74 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10244 | NA | Credit Card | RIW-CFR-01-115
2025-01-17 | 1 | 6 | Jobsite Storage Container - Recurring Rental | From Willscot | 150.74 | 0 | 150.74 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10245 | NA | Credit Card | RIW-CFR-01-116
2025-01-17 | 1 | 6 | Jobsite Storage Container - Rental + Drop Off | From Willscot | 1031.62 | 0 | 1031.62 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10246 | NA | Credit Card | RIW-CFR-01-117
2025-02-11 | 1 | 6 | Jobsite Office - Recurring Rental | From Willscot | 817.83 | 0 | 817.83 |  |  |  | Jobsite Office Rental | Willscot | Boulder AMEX | 10247 | NA | Credit Card | RIW-CFR-01-118
2025-02-13 | 1 | 6 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10248 | NA | Credit Card | RIW-CFR-01-119
2025-02-14 | 1 | 6 | Jobsite Storage Container - Recurring Rental | From Willscot | 150.74 | 0 | 150.74 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10249 | NA | Credit Card | RIW-CFR-01-120
2025-02-14 | 1 | 6 | Jobsite Storage Container - Recurring Rental | From Willscot | 150.74 | 0 | 150.74 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10250 | NA | Credit Card | RIW-CFR-01-121
2025-02-14 | 1 | 6 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10251 | NA | Credit Card | RIW-CFR-01-122
2025-02-27 | 1 | 6 | Jobsite Storage Container - Rental + Drop Off | From Willscot | 1031.62 | 0 | 1031.62 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10252 | NA | Credit Card | RIW-CFR-01-123
2025-01-15 | 1 | 6 | Misc. Jobsite Materials | From Home Depot - Bags, Fuel and Oil, Spray Paint | 181.8 | 0 | 181.8 |  |  |  | Jobsite Material Expenses | Home Depot | Boulder AMEX | 10253 | NA | Credit Card | RIW-CFR-01-124
2025-01-15 | 1 | 6 | Misc. Jobsite Materials | From Home Depot - Spray Paint & Other for Marriott Walk | 216.51 | 0 | 216.51 |  |  |  | Jobsite Material Expenses | Home Depot | Boulder AMEX | 10254 | NA | Credit Card | RIW-CFR-01-125
2025-01-16 | 1 | 6 | Misc. Jobsite Materials | From Home Depot - Spray Paint for Marriott Walk | 43.21 | 0 | 43.21 |  |  |  | Jobsite Material Expenses | Home Depot | Boulder AMEX | 10255 | NA | Credit Card | RIW-CFR-01-126
2025-01-17 | 1 | 6 | Temporary Toilets - Recurring Payment | A-1 Little John | 260.88 | 0 | 260.88 |  |  |  | Container Storage Rental | A-1 Little John | Boulder AMEX | 10256 | NA | Credit Card | RIW-CFR-01-127
2025-01-24 | 1 | 6 | Misc. Jobsite Materials | From Home Depot - Fuel and Oil | 22.64 | 0 | 22.64 |  |  |  | Gas/Oil/Travel | Home Depot | Boulder AMEX | 10258 | NA | Credit Card | RIW-CFR-01-128
2025-02-04 | 1 | 6 | Misc. Jobsite Materials | From Home Depot - Cable Ties | 31.37 | 0 | 31.37 |  |  |  | Jobsite Material Expenses | Home Depot | Boulder AMEX | 10265 | NA | Credit Card | RIW-CFR-01-129
2025-02-13 | 1 | 6 | Misc. Jobsite Materials | From Home Depot - Ice Melt Bag | 86.44 | 0 | 86.44 |  |  |  | Jobsite Material Expenses | Home Depot | Boulder AMEX | 10266 | NA | Credit Card | RIW-CFR-01-130
2025-02-17 | 1 | 6 | Misc. Jobsite Materials | From Home Depot - Gas Can | 48.65 | 0 | 48.65 |  |  |  | Gas/Oil/Travel | Home Depot | Boulder AMEX | 10267 | NA | Credit Card | RIW-CFR-01-131
2025-02-19 | 1 | 6 | Temporary Toilets - Recurring Payment | A-1 Little John | 260.88 | 0 | 260.88 |  |  |  | Container Storage Rental | A-1 Little John | Boulder AMEX | 10268 | NA | Credit Card | RIW-CFR-01-132
2025-02-21 | 1 | 6 | Misc. Jobsite Materials | From Home Depot - Combination Lock | 32.65 | 0 | 32.65 |  |  |  | Jobsite Material Expenses | Home Depot | Boulder AMEX | 10269 | NA | Credit Card | RIW-CFR-01-133
2025-01-15 | 1 | 6 | Jobsite Dumpster | From Advantage Waste Disposal | 57.81 | 0 | 57.81 |  |  |  | Waste Removal Services | Advantage Waste | Boulder AMEX | 10272 | NA | Credit Card | RIW-CFR-01-134
2025-01-20 | 1 | 6 | Jobsite Dumpster | From Advantage Waste Disposal | 724.74 | 0 | 724.74 |  |  |  | Waste Removal Services | Advantage Waste | Boulder AMEX | 10273 | NA | Credit Card | RIW-CFR-01-135
2025-03-04 | 1 | 6 | Notary Fees | For Draw | 10 | 0 | 10 |  |  |  | Plan Reproduction/Postage | The UPS Store | Boulder AMEX |  | NA | Credit Card | RIW-CFR-01-136
2025-03-07 | 1 | 6 | Jobsite Dumpster | From Waste Connections | 943.58 | 0 | 943.58 |  |  |  | Waste Removal Services | Waste Connections | Boulder AMEX | 10275 | NA | Credit Card | RIW-CFR-01-137
2025-02-12 | 1 | 6 | Security Cameras | Birdseye Surveillance | 1515.5 | 0 | 1515.5 |  |  |  | Jobsite Material Expenses | Birdseye Surveillance | Owner (JP) AMEX | 10284 | NA | Credit Card | RIW-CFR-01-138
2025-02-26 | 1 | 6 | Security Cameras | Birdseye Surveillance | 1515.5 | 0 | 1515.5 |  |  |  | Jobsite Material Expenses | Birdseye Surveillance | Owner (JP) AMEX | 10289 | NA | Credit Card | RIW-CFR-01-139
2025-01-11 | 1 | 6 | Jobsite Labor | Clean Up & Other Misc. Tasks | 760 | 0 | 760 |  |  |  | Jobsite Labor | Rodolfo Rios | RI Waxahachie | 10331 | NA | Check | RIW-CFR-01-140
2025-01-17 | 1 | 6 | Jobsite Labor | Clean Up & Other Misc. Tasks | 1185.75 | 0 | 1185.75 |  |  |  | Jobsite Labor | Rodolfo Rios | Boulder | 10334 | NA | Check | RIW-CFR-01-141
2025-01-25 | 1 | 6 | Jobsite Labor | Clean Up & Other Misc. Tasks | 1282.5 | 0 | 1282.5 |  |  |  | Jobsite Labor | Rodolfo Rios | RI Waxahachie | 10312 | NA | Check | RIW-CFR-01-142
2025-01-31 | 1 | 6 | Jobsite Labor | Clean Up & Other Misc. Tasks | 665 | 0 | 665 |  |  |  | Jobsite Labor | Rodolfo Rios | RI Waxahachie | 10313 | NA | Check | RIW-CFR-01-143
2025-02-07 | 1 | 6 | Jobsite Labor | Clean Up & Other Misc. Tasks | 546.25 | 0 | 546.25 |  |  |  | Jobsite Labor | Rodolfo Rios | RI Waxahachie | 10314 | NA | Check | RIW-CFR-01-144
2025-02-14 | 1 | 6 | Jobsite Labor | Clean Up & Other Misc. Tasks | 617.5 | 0 | 617.5 |  |  |  | Jobsite Labor | Rodolfo Rios | RI Waxahachie | 10315 | NA | ACH | RIW-CFR-01-145
2025-02-21 | 1 | 6 | Jobsite Labor | Clean Up & Other Misc. Tasks | 356.25 | 0 | 356.25 |  |  |  | Jobsite Labor | Rodolfo Rios | RI Waxahachie | 10332 | NA | Check | RIW-CFR-01-146
2025-02-28 | 1 | 6 | Jobsite Labor | Clean Up & Other Misc. Tasks | 1068.75 | 0 | 1068.75 |  |  |  | Jobsite Labor | Rodolfo Rios | RI Waxahachie | 10316 | NA | ACH | RIW-CFR-01-147
2025-03-07 | 1 | 6 | Jobsite Labor | Clean Up & Other Misc. Tasks | 950 | 0 | 950 |  |  |  | Jobsite Labor | Rodolfo Rios |  | 10317 | NA | ACH | RIW-CFR-01-148
2025-02-13 | 1 | 6 | Cornerstone Safety | Per Ownership Requirements | 1500 | 0 | 1500 |  |  |  | Safety | Cornerstone Safety | Jai | 10330 | NA | Credit Card | RIW-CFR-01-149
2025-03-21 | 1 | 6 | Job Supervisor | For March 2025 | 10000 | 0 | 10000 |  |  |  | Superintendent | Boulder Construction | RI Waxahachie | NA | NA | Fee | RIW-CFR-01-150
2025-03-21 | 1 | 6 | Project Manager | Boulder Construction - For March 2025 | 3888.8889 | 0 | 3888.8889 |  |  |  | General Superintendent/PM | Boulder Construction | RI Waxahachie | NA | NA | Fee | RIW-CFR-01-151
2025-03-21 | 1 | 6 | Job Accounting / Administration | Boulder Construction - For March 2025 | 3611.1111 | 0 | 3611.1111 |  |  |  | Job Accounting/Administration | Boulder Construction | RI Waxahachie | NA | NA | Fee | RIW-CFR-01-152
2025-04-04 | 1 | 6 | Cornerstone Safety | Per Ownership Requirements | 1500 | 0 | 1500 |  |  |  | Safety | Cornerstone Safety | Jai | 10336 | NA | Credit Card | RIW-CFR-01-153
2025-03-11 | 1 | 7 | Jobsite Office - Recurring Rental | From Willscot | 817.83 | 0 | 817.83 |  |  |  | Jobsite Office Rental | Willscot | Boulder AMEX | 10349 | NA | Credit Card | RIW-CFR-01-154
2025-03-13 | 1 | 7 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10350 | NA | Credit Card | RIW-CFR-01-155
2025-03-14 | 1 | 7 | Jobsite Storage Container - Recurring Rental | From Willscot | 150.74 | 0 | 150.74 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10352 | NA | Credit Card | RIW-CFR-01-156
2025-03-14 | 1 | 7 | Jobsite Storage Container - Recurring Rental | From Willscot | 150.74 | 0 | 150.74 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10353 | NA | Credit Card | RIW-CFR-01-157
2025-03-14 | 1 | 7 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10351 | NA | Credit Card | RIW-CFR-01-158
2025-03-27 | 1 | 7 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10354 | NA | Credit Card | RIW-CFR-01-159
2025-04-04 | 1 | 7 | Jobsite Storage Container - Rental + Drop Off | From Willscot | 1031.62 | 0 | 1031.62 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10355 | NA | Credit Card | RIW-CFR-01-160
2025-04-04 | 1 | 7 | Jobsite Storage Container - Rental + Drop Off | From Willscot | 1031.62 | 0 | 1031.62 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10356 | NA | Credit Card | RIW-CFR-01-161
2025-03-16 | 1 | 7 | Temporary Toilets - Recurring Payment | A-1 Little John | 260.88 | 0 | 260.88 |  |  |  | Container Storage Rental | A-1 Little John | Boulder AMEX | 10357 | NA | Credit Card | RIW-CFR-01-162
2025-03-17 | 1 | 7 | Notary Fees | For Draw | 10 | 0 | 10 |  |  |  | Plan Reproduction/Postage | The UPS Store | Boulder AMEX |  | NA | Credit Card | RIW-CFR-01-163
2025-03-18 | 1 | 7 | Meal for Jobsite Crew | From Dominos | 121.16 | 0 | 121.16 |  |  |  | Jobsite Material Expenses | Dominos | Boulder AMEX |  | NA | Credit Card | RIW-CFR-01-164
2025-03-25 | 1 | 7 | Jobsite Dumpster | From Waste Connections | 1009.79 | 0 | 1009.79 |  |  |  | Waste Removal Services | Waste Connections | Boulder AMEX | 10358 | NA | Credit Card | RIW-CFR-01-165
2025-04-01 | 1 | 7 | Generators for Jobsite Office + Building | From Harbor Freight Tools | 3355.71 | 0 | 3355.71 |  |  |  | Gas/Oil/Travel | Harbor Freight | Boulder AMEX | 10359 | NA | Credit Card | RIW-CFR-01-166
2025-03-19 | 1 | 7 | Misc. Jobsite Materials | From Home Depot - Hand Truck (Dolley) | 75.26 | 0 | 75.26 |  |  |  | Jobsite Material Expenses | Home Depot | Boulder AMEX | 10363 | NA | Credit Card | RIW-CFR-01-167
2025-03-21 | 1 | 7 | Misc. Jobsite Materials | From Home Depot - Coil Chain, Deck Screws, and Padlock | 50.55 | 0 | 50.55 |  |  |  | Jobsite Material Expenses | Home Depot | Boulder AMEX | 10367 | NA | Credit Card | RIW-CFR-01-168
2025-03-31 | 1 | 7 | Misc. Jobsite Materials | From Home Depot - Deck Screws and Padlock/Combination Locks | 80.17 | 0 | 80.17 |  |  |  | Jobsite Material Expenses | Home Depot | Boulder AMEX | 10369 | NA | Credit Card | RIW-CFR-01-169
2025-03-25 | 1 | 7 | Permit and New Construction Display Board | From Minuteman Press | 909.3 | 0 | 909.3 |  |  |  | Jobsite Material Expenses | Minuteman Press | Owner (JP) AMEX | 10388 | NA | Credit Card | RIW-CFR-01-170
2025-03-14 | 1 | 7 | Jobsite Labor | Clean Up & Other Misc. Tasks | 502.5 | 0 | 502.5 |  |  |  | Jobsite Labor | Rodolfo Rios |  | 10395 | NA | ACH | RIW-CFR-01-171
2025-03-21 | 1 | 7 | Jobsite Labor | Clean Up & Other Misc. Tasks | 1045 | 0 | 1045 |  |  |  | Jobsite Labor | Rodolfo Rios | RI Waxahachie | 10396 | NA | ACH | RIW-CFR-01-172
2025-03-28 | 1 | 7 | Jobsite Labor | Clean Up & Other Misc. Tasks | 500 | 0 | 500 |  |  |  | Jobsite Labor | Rodolfo Rios | Jai | 10397 | NA | Zelle | RIW-CFR-01-173
2025-04-04 | 1 | 7 | Jobsite Labor | Clean Up & Other Misc. Tasks | 1467.5 | 0 | 1467.5 |  |  |  | Jobsite Labor | Rodolfo Rios | RI Waxahachie | 10398 | NA | ACH | RIW-CFR-01-174
2025-04-29 | 1 | 7 | Job Supervisor | For April 2025 | 10000 | 0 | 10000 |  |  |  | Superintendent | Boulder Construction | RI Waxahachie | NA | NA | Fee | RIW-CFR-01-175
2025-04-29 | 1 | 7 | Project Manager | Boulder Construction - For April 2025 | 3888.8889 | 0 | 3888.8889 |  |  |  | General Superintendent/PM | Boulder Construction | RI Waxahachie | NA | NA | Fee | RIW-CFR-01-176
2025-04-29 | 1 | 7 | Job Accounting / Administration | Boulder Construction - For April 2025 | 3611.1111 | 0 | 3611.1111 |  |  |  | Job Accounting/Administration | Boulder Construction | RI Waxahachie | NA | NA | Fee | RIW-CFR-01-177
2025-04-08 | 1 | 8 | Jobsite Office - Recurring Rental | From Willscot | 817.83 | 0 | 817.83 |  |  |  | Jobsite Office Rental | Willscot | Boulder AMEX | 10416 | NA | Credit Card | RIW-CFR-01-178
2025-04-10 | 1 | 8 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10419 | NA | Credit Card | RIW-CFR-01-179
2025-04-11 | 1 | 8 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10422 | NA | Credit Card | RIW-CFR-01-180
2025-04-11 | 1 | 8 | Jobsite Storage Container - Recurring Rental | From Willscot | 150.74 | 0 | 150.74 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10423 | NA | Credit Card | RIW-CFR-01-181
2025-04-11 | 1 | 8 | Jobsite Storage Container - Recurring Rental | From Willscot | 150.74 | 0 | 150.74 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10424 | NA | Credit Card | RIW-CFR-01-182
2025-04-25 | 1 | 8 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10430 | NA | Credit Card | RIW-CFR-01-183
2025-04-09 | 1 | 8 | Jobsite Dumpster | From Waste Connections | 538 | 0 | 538 |  |  |  | Waste Removal Services | Waste Connections | Boulder AMEX | 10418 | NA | Credit Card | RIW-CFR-01-184
2025-04-11 | 1 | 8 | Temporary Toilets - Recurring Payment | A-1 Little John | 260.88 | 0 | 260.88 |  |  |  | Container Storage Rental | A-1 Little John | Boulder AMEX | 10411 | NA | Credit Card | RIW-CFR-01-185
2025-04-11 | 1 | 8 | Jobsite Labor | Clean Up & Other Misc. Tasks | 1438.75 | 0 | 1438.75 |  |  |  | Jobsite Labor | Rodolfo Rios | RI Waxahachie | 10435 | NA | Check | RIW-CFR-01-186
2025-04-21 | 1 | 8 | Jobsite Labor | Clean Up & Other Misc. Tasks | 1575 | 0 | 1575 |  |  |  | Jobsite Labor | Rodolfo Rios | RI Waxahachie | 10436 | NA | Check | RIW-CFR-01-187
2025-04-24 | 1 | 8 | Jobsite Labor | Clean Up & Other Misc. Tasks | 950 | 0 | 950 |  |  |  | Jobsite Labor | Rodolfo Rios | RI Waxahachie | 10437 | NA | Check | RIW-CFR-01-188
2025-05-02 | 1 | 8 | Jobsite Labor | Clean Up & Other Misc. Tasks | 973.75 | 0 | 973.75 |  |  |  | Jobsite Labor | Rodolfo Rios | RI Waxahachie | 10455 | NA | Check | RIW-CFR-01-189
2025-05-02 | 1 | 8 | Jobsite Labor | Clean Up & Other Misc. Tasks | 240 | 0 | 240 |  |  |  | Jobsite Labor | David Salinas | RI Waxahachie | 10456 | NA | Check | RIW-CFR-01-190
2025-04-08 | 1 | 8 | Misc. Jobsite Materials | From Home Depot - Gloves, Glass Cleaner, Shop Vac, Cloth, Broom | 165.05 | 0 | 165.05 |  |  |  | Jobsite Material Expenses | Home Depot | Boulder AMEX | 10425 | NA | Credit Card | RIW-CFR-01-191
2025-04-21 | 1 | 8 | Misc. Jobsite Materials | From Home Depot - Gas String Trimmer and Fuel | 254.72 | 0 | 254.72 |  |  |  | Jobsite Material Expenses | Home Depot | Boulder AMEX | 10438 | NA | Credit Card | RIW-CFR-01-192
2025-04-21 | 1 | 8 | Misc. Jobsite Materials | From Home Depot - Return | -90.06 | 0 | -90.06 |  |  |  | Jobsite Material Expenses | Home Depot | Boulder AMEX |  | NA | Credit Card | RIW-CFR-01-193
2025-04-11 | 1 | 8 | Misc. Jobsite Materials - Model Room | From Home Depot - Wire Shelving and Closet Shelf | 39.42 | 0 | 39.42 |  |  |  | Jobsite Material Expenses | Home Depot | Boulder AMEX | 10421 | NA | Credit Card | RIW-CFR-01-194
2025-04-09 | 1 | 8 | Petty Cash | Reimbursement for Expenses/Petty Cash to Job Supervisor | 1500 | 0 | 1500 |  |  |  | Jobsite Material Expenses | Jason Clayburn | RI Waxahachie | 10445 | NA | Check | RIW-CFR-01-195
2025-04-01 | 1 | 8 | Diesel for Equipment |  | 33.96 | 0 | 33.96 |  |  |  | Gas/Oil/Travel | Racetrac | Boulder AMEX |  | NA | Credit Card | RIW-CFR-01-196
2025-03-11 | 1 | 8 | Diesel for Equipment |  | 27.57 | 0 | 27.57 |  |  |  | Gas/Oil/Travel | Shell | Boulder AMEX |  | NA | Credit Card | RIW-CFR-01-197
2025-03-11 | 1 | 8 | Diesel for Equipment |  | 28 | 0 | 28 |  |  |  | Gas/Oil/Travel | Shell | Boulder AMEX |  | NA | Credit Card | RIW-CFR-01-198
2025-04-25 | 1 | 8 | Diesel for Equipment |  | 31.16 | 0 | 31.16 |  |  |  | Gas/Oil/Travel | Shell | Boulder AMEX |  | NA | Credit Card | RIW-CFR-01-199
2025-04-25 | 1 | 8 | Diesel for Equipment |  | 13.4 | 0 | 13.4 |  |  |  | Gas/Oil/Travel | Shell | Boulder AMEX |  | NA | Credit Card | RIW-CFR-01-200
2025-04-25 | 1 | 8 | Diesel for Equipment |  | 11.83 | 0 | 11.83 |  |  |  | Gas/Oil/Travel | Shell | Boulder AMEX |  | NA | Credit Card | RIW-CFR-01-201
2025-05-02 | 1 | 8 | Security Cameras | Birdseye Surveillance | 1515.5 | 0 | 1515.5 |  |  |  | Jobsite Material Expenses | Birdseye Surveillance | Owner (JP) AMEX | 10451 | NA | Credit Card | RIW-CFR-01-202
2025-05-02 | 1 | 8 | Security Cameras | Birdseye Surveillance | 1515.5 | 0 | 1515.5 |  |  |  | Jobsite Material Expenses | Birdseye Surveillance | Owner (JP) AMEX | 10452 | NA | Credit Card | RIW-CFR-01-203
[To Be Paid] | 1 | 8 | Job Supervisor | For May 2025 | 10000 | 0 | 10000 |  |  |  | Superintendent | Boulder Construction | [To Be Paid] |  | NA |  | RIW-CFR-01-204
[To Be Paid] | 1 | 8 | Project Manager | Boulder Construction - For May 2025 | 3888.8889 | 0 | 3888.8889 |  |  |  | General Superintendent/PM | Boulder Construction | [To Be Paid] |  | NA |  | RIW-CFR-01-205
[To Be Paid] | 1 | 8 | Job Accounting / Administration | Boulder Construction - For May 2025 | 3611.1111 | 0 | 3611.1111 |  |  |  | Job Accounting/Administration | Boulder Construction | [To Be Paid] |  | NA |  | RIW-CFR-01-206
2025-05-05 | 1 | 9 | Notary Fees | For Draw | 10 | 0 | 10 |  |  |  | Plan Reproduction/Postage | The UPS Store | Boulder AMEX |  | NA | Credit Card | RIW-CFR-01-207
2025-05-06 | 1 | 9 | Jobsite Office - Recurring Rental | From Willscot | 817.83 | 0 | 817.83 |  |  |  | Jobsite Office Rental | Willscot | Boulder AMEX | 10467 | NA | Credit Card | RIW-CFR-01-208
2025-05-02 | 1 | 9 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10466 | NA | Credit Card | RIW-CFR-01-209
2025-05-02 | 1 | 9 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10465 | NA | Credit Card | RIW-CFR-01-210
2025-05-09 | 1 | 9 | Jobsite Storage Container - Rental + Drop Off | From Willscot | 1038.12 | 0 | 1038.12 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10464 | NA | Credit Card | RIW-CFR-01-211
2025-05-09 | 1 | 9 | Jobsite Storage Container - Rental + Drop Off | From Willscot | 1038.12 | 0 | 1038.12 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10463 | NA | Credit Card | RIW-CFR-01-212
2025-05-09 | 1 | 9 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10462 | NA | Credit Card | RIW-CFR-01-213
2025-05-09 | 1 | 9 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10461 | NA | Credit Card | RIW-CFR-01-214
2025-05-09 | 1 | 9 | Jobsite Storage Container - Recurring Rental | From Willscot | 150.74 | 0 | 150.74 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10460 | NA | Credit Card | RIW-CFR-01-215
2025-05-09 | 1 | 9 | Jobsite Storage Container - Recurring Rental | From Willscot | 150.74 | 0 | 150.74 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10459 | NA | Credit Card | RIW-CFR-01-216
2025-05-09 | 1 | 9 | Jobsite Storage Container - Recurring Rental | From Willscot | 81.19 | 0 | 81.19 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10458 | NA | Credit Card | RIW-CFR-01-217
2025-05-02 | 1 | 9 | Jobsite Labor | Clean Up & Other Misc. Tasks | 225 | 0 | 225 |  |  |  | Jobsite Labor | David Salinas | RI Waxahachie | 10473 | NA | Credit Card | RIW-CFR-01-218
2025-05-02 | 1 | 9 | Jobsite Labor | Clean Up & Other Misc. Tasks | 950 | 0 | 950 |  |  |  | Jobsite Labor | Rodolfo Rios | RI Waxahachie | 10474 | NA | Credit Card | RIW-CFR-01-219
2025-05-02 | 1 | 9 | Cornerstone Safety | Per Ownership Requirements | 1500 | 0 | 1500 |  |  |  | Safety | Cornerstone Safety | Jai | 10493 | NA | Credit Card | RIW-CFR-01-220
2025-05-07 | 1 | 9 | Jobsite Dumpster | From Waste Connections | 1720.9 | 0 | 1720.9 |  |  |  | Waste Removal Services | Waste Connections | Boulder AMEX | 10469 | NA | Credit Card | RIW-CFR-01-221
2025-05-07 | 1 | 9 | Misc. Jobsite Materials | From Home Depot - Bags, Paper Towels, Cleaner, Bucket | 77.27 | 0 | 77.27 |  |  |  | Jobsite Material Expenses | Home Depot | Boulder AMEX | 10470 | NA | Credit Card | RIW-CFR-01-222
2025-05-13 | 1 | 9 | Temporary Toilets - Recurring Payment | A-1 Little John | 260.88 | 0 | 260.88 |  |  |  | Container Storage Rental | A-1 Little John | Boulder AMEX | 10479 | NA | Credit Card | RIW-CFR-01-223
2025-05-15 | 1 | 9 | Misc. Jobsite Materials | From Home Depot - Adjustable Table | 56.01 | 0 | 56.01 |  |  |  | Jobsite Material Expenses | Home Depot | Boulder AMEX | 10480 | NA | Credit Card | RIW-CFR-01-224
2025-05-16 | 1 | 9 | Jobsite Labor | Clean Up & Other Misc. Tasks | 135 | 0 | 135 |  |  |  | Jobsite Labor | David Salinas | RI Waxahachie | 10476 | NA | Credit Card | RIW-CFR-01-225
2025-05-16 | 1 | 9 | Jobsite Labor | Clean Up & Other Misc. Tasks | 902.5 | 0 | 902.5 |  |  |  | Jobsite Labor | Rodolfo Rios | RI Waxahachie | 10477 | NA | Credit Card | RIW-CFR-01-226
2025-05-21 | 1 | 9 | Jobsite Dumpster | From Waste Connections | 538 | 0 | 538 |  |  |  | Waste Removal Services | Waste Connections | Boulder AMEX | 10503 | NA | Credit Card | RIW-CFR-01-227
2025-05-22 | 1 | 9 | Jobsite Dumpster | From Waste Connections | 1198.66 | 0 | 1198.66 |  |  |  | Waste Removal Services | Waste Connections | Boulder AMEX | 10509 | NA | Credit Card | RIW-CFR-01-228
2025-05-22 | 1 | 9 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10510 | NA | Credit Card | RIW-CFR-01-229
[To Be Paid] | 1 | 9 | Job Supervisor | For June 2025 | 10000 | 0 | 10000 |  |  |  | Superintendent | Boulder Construction | [To Be Paid] |  | NA |  | RIW-CFR-01-230
[To Be Paid] | 1 | 9 | Project Manager | Boulder Construction - For June 2025 | 3888.8889 | 0 | 3888.8889 |  |  |  | General Superintendent/PM | Boulder Construction | [To Be Paid] |  | NA |  | RIW-CFR-01-231
[To Be Paid] | 1 | 9 | Job Accounting / Administration | Boulder Construction - For June 2025 | 3611.1111 | 0 | 3611.1111 |  |  |  | Job Accounting/Administration | Boulder Construction | [To Be Paid] |  | NA |  | RIW-CFR-01-232
2025-05-29 | 1 | 10 | Diesel for Equipment |  | 13.61 | 0 | 13.61 |  |  |  | Gas/Oil/Travel | Shell | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-233
2025-05-30 | 1 | 10 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10583 | NA | Credit Card | RIW-CFR-01-234
2025-05-30 | 1 | 10 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10584 | NA | Credit Card | RIW-CFR-01-235
2025-05-31 | 1 | 10 | Misc. Jobsite Materials | From Home Depot - Paint/Canyew Panel/Dark Walnut | 131.6 | 0 | 131.6 |  |  |  | Jobsite Material Expenses | Home Depot | Boulder AMEX | 10585 | NA | Credit Card | RIW-CFR-01-236
2025-06-03 | 1 | 10 | Jobsite Office - Recurring Rental | From Willscot | 817.83 | 0 | 817.83 |  |  |  | Jobsite Office Rental | Willscot | Boulder AMEX | 10560 | NA | Credit Card | RIW-CFR-01-237
2025-06-05 | 1 | 10 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10565 | NA | Credit Card | RIW-CFR-01-238
2025-06-06 | 1 | 10 | Jobsite Storage Container - Recurring Rental | From Willscot | 190.52 | 0 | 190.52 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10563 | NA | Credit Card | RIW-CFR-01-239
2025-06-06 | 1 | 10 | Jobsite Storage Container - Recurring Rental | From Willscot | 190.52 | 0 | 190.52 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10564 | NA | Credit Card | RIW-CFR-01-240
2025-06-06 | 1 | 10 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10566 | NA | Credit Card | RIW-CFR-01-241
2025-06-06 | 1 | 10 | Jobsite Storage Container - Recurring Rental | From Willscot | 150.74 | 0 | 150.74 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10561 | NA | Credit Card | RIW-CFR-01-242
2025-06-06 | 1 | 10 | Jobsite Storage Container - Recurring Rental | From Willscot | 150.74 | 0 | 150.74 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10562 | NA | Credit Card | RIW-CFR-01-243
2025-06-06 | 1 | 10 | Temporary Toilets - Recurring Payment | From A-1 Little John | 684.14 | 0 | 684.14 |  |  |  | Container Storage Rental | A-1 Little John | Boulder AMEX | 10568 | NA | Credit Card | RIW-CFR-01-244
2025-06-12 | 1 | 10 | Jobsite Dumpster | From Waste Connections | 1521.58 | 0 | 1521.58 |  |  |  | Waste Removal Services | Waste Connections | Boulder AMEX | 10545 | NA | Credit Card | RIW-CFR-01-245
2025-06-18 | 1 | 10 | Misc. Jobsite Materials | From Home Depot - Padlock | 62.09 | 0 | 62.09 |  |  |  | Jobsite Material Expenses | Home Depot | Boulder AMEX | 10604 | NA | Credit Card | RIW-CFR-01-246
2025-06-20 | 1 | 10 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10605 | NA | Credit Card | RIW-CFR-01-247
2025-06-03 | 1 | 10 | Notary Fees | For Draw | 10 | 0 | 10 |  |  |  | Plan Reproduction/Postage | The UPS Store | Jaimin AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-248
2025-05-30 | 1 | 10 | Jobsite Labor | Clean Up & Other Misc. Tasks | 926.25 | 0 | 926.25 |  |  |  | Jobsite Labor | Rodolfo Rios | RI Waxahachie | 10548 | NA | ACH | RIW-CFR-01-249
2025-05-30 | 1 | 10 | Jobsite Labor | Clean Up & Other Misc. Tasks | 210 | 0 | 210 |  |  |  | Jobsite Labor | David Salinas | RI Waxahachie | 10549 | NA | ACH | RIW-CFR-01-250
2025-06-06 | 1 | 10 | Jobsite Labor | Clean Up & Other Misc. Tasks | 360 | 0 | 360 |  |  |  | Jobsite Labor | David Salinas | RI Waxahachie | 10550 | NA | ACH | RIW-CFR-01-251
2025-06-06 | 1 | 10 | Jobsite Labor | Clean Up & Other Misc. Tasks | 973.75 | 0 | 973.75 |  |  |  | Jobsite Labor | Rodolfo Rios | RI Waxahachie | 10551 | NA | ACH | RIW-CFR-01-252
2025-06-13 | 1 | 10 | Jobsite Labor | Clean Up & Other Misc. Tasks | 240 | 0 | 240 |  |  |  | Jobsite Labor | David Salinas | RI Waxahachie | 10552 | NA | ACH | RIW-CFR-01-253
2025-06-13 | 1 | 10 | Jobsite Labor | Clean Up & Other Misc. Tasks | 760 | 0 | 760 |  |  |  | Jobsite Labor | Rodolfo Rios | RI Waxahachie | 10553 | NA | ACH | RIW-CFR-01-254
2025-06-20 | 1 | 10 | Jobsite Labor | Clean Up & Other Misc. Tasks | 1211.25 | 0 | 1211.25 |  |  |  | Jobsite Labor | Rodolfo Rios | RI Waxahachie | 10579 | NA | ACH | RIW-CFR-01-255
2025-06-20 | 1 | 10 | Jobsite Labor | Clean Up & Other Misc. Tasks | 555 | 0 | 555 |  |  |  | Jobsite Labor | David Salinas | RI Waxahachie | 10580 | NA | ACH | RIW-CFR-01-256
2025-06-23 | 1 | 10 | Jobsite Labor | Clean Up & Other Misc. Tasks | 500 | 0 | 500 |  |  |  | Jobsite Labor | Rodolfo Rios | RI Waxahachie | 10597 | NA | Check | RIW-CFR-01-257
2025-06-27 | 1 | 10 | Jobsite Labor | Clean Up & Other Misc. Tasks | 641.25 | 0 | 641.25 |  |  |  | Jobsite Labor | Rodolfo Rios | RI Waxahachie | 10613 | NA | ACH | RIW-CFR-01-258
2025-06-27 | 1 | 10 | Jobsite Labor | Clean Up & Other Misc. Tasks | 285 | 0 | 285 |  |  |  | Jobsite Labor | David Salinas | RI Waxahachie | 10612 | NA | ACH | RIW-CFR-01-259
2025-06-27 | 1 | 10 | Jobsite Dumpster | From Waste Connections | 2059.58 | 0 | 2059.58 |  |  |  | Waste Removal Services | Waste Connections | Boulder AMEX | 10610 | NA | Credit Card | RIW-CFR-01-260
2025-07-03 | 1 | 11 | Jobsite Labor | Clean Up & Other Misc. Tasks | 240 | 0 | 240 |  |  |  | Jobsite Labor | David Salinas | RI Waxahachie | 10659 | NA | ACH | RIW-CFR-01-261
2025-07-03 | 1 | 11 | Jobsite Labor | Clean Up & Other Misc. Tasks | 380 | 0 | 380 |  |  |  | Jobsite Labor | Rodolfo Rios | RI Waxahachie | 10660 | NA | ACH | RIW-CFR-01-262
2025-07-11 | 1 | 11 | Jobsite Labor | Clean Up & Other Misc. Tasks | 300 | 0 | 300 |  |  |  | Jobsite Labor | David Salinas | RI Waxahachie | 10661 | NA | ACH | RIW-CFR-01-263
2025-07-11 | 1 | 11 | Jobsite Labor | Clean Up & Other Misc. Tasks | 760 | 0 | 760 |  |  |  | Jobsite Labor | Rodolfo Rios | RI Waxahachie | 10662 | NA | ACH | RIW-CFR-01-264
2025-07-14 | 1 | 11 | Fence Gate Relocation & Addition | From Viking Fence Co | 745.57 | 0 | 745.57 |  |  |  | Temporary Fencing | Viking Fence | Jaimin AMEX | 10671 | NA | Credit Card | RIW-CFR-01-265
2025-06-27 | 1 | 11 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10630 | NA | Credit Card | RIW-CFR-01-266
2025-06-27 | 1 | 11 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10631 | NA | Credit Card | RIW-CFR-01-267
2025-07-01 | 1 | 11 | Notary Fees | For Draw | 13.39 | 0 | 13.39 |  |  |  | Plan Reproduction/Postage | The UPS Store | Boulder AMEX | 10651 | NA | Credit Card | RIW-CFR-01-268
2025-07-02 | 1 | 11 | Notary Fees | For Draw | 13.39 | 0 | 13.39 |  |  |  | Plan Reproduction/Postage | The UPS Store | Boulder AMEX | 10652 | NA | Credit Card | RIW-CFR-01-269
2025-07-01 | 1 | 11 | Misc. Jobsite Materials | From Home Depot - Pliers | 41.97 | 0 | 41.97 |  |  |  | Jobsite Material Expenses | Home Depot | Boulder AMEX | 10653 | NA | Credit Card | RIW-CFR-01-270
2025-07-02 | 1 | 11 | Jobsite Office - Recurring Rental | From Willscot | 817.83 | 0 | 817.83 |  |  |  | Jobsite Office Rental | Willscot | Boulder AMEX | 10632 | NA | Credit Card | RIW-CFR-01-271
2025-07-03 | 1 | 11 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10635 | NA | Credit Card | RIW-CFR-01-272
2025-07-04 | 1 | 11 | Jobsite Storage Container - Recurring Rental | From Willscot | 190.52 | 0 | 190.52 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10637 | NA | Credit Card | RIW-CFR-01-273
2025-07-04 | 1 | 11 | Jobsite Storage Container - Recurring Rental | From Willscot | 190.52 | 0 | 190.52 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10638 | NA | Credit Card | RIW-CFR-01-274
2025-07-04 | 1 | 11 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10636 | NA | Credit Card | RIW-CFR-01-275
2025-07-04 | 1 | 11 | Jobsite Storage Container - Recurring Rental | From Willscot | 150.74 | 0 | 150.74 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10633 | NA | Credit Card | RIW-CFR-01-276
2025-07-04 | 1 | 11 | Jobsite Storage Container - Recurring Rental | From Willscot | 150.74 | 0 | 150.74 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10634 | NA | Credit Card | RIW-CFR-01-277
2025-07-06 | 1 | 11 | Security Cameras | Birdseye Surveillance | 1515.5 | 0 | 1515.5 |  |  |  | Jobsite Material Expenses | Birdseye Surveillance | Jaimin AMEX | 10629 | NA | Credit Card | RIW-CFR-01-278
2025-07-08 | 1 | 11 | Temporary Toilets - Recurring Payment | A-1 Little John | 521.77 | 0 | 521.77 |  |  |  | Container Storage Rental | A-1 Little John | Boulder AMEX | 10641 | NA | Credit Card | RIW-CFR-01-279
2025-07-08 | 1 | 11 | Labor & Gas for Generators | From J&S7 Consulting | 410.74 | 0 | 410.74 |  |  |  | Gas/Oil/Travel | J&S7 Consulting | RI Waxahachie | 10670 | NA | Check | RIW-CFR-01-280
2025-07-09 | 1 | 11 | Misc. Jobsite Materials | From Home Depot - Multi-Surface Primer, Sealer, and Stain Blocker | 21.63 | 0 | 21.63 |  |  |  | Jobsite Material Expenses | Home Depot | Boulder AMEX | 10658 | NA | Credit Card | RIW-CFR-01-281
2025-07-18 | 1 | 11 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10682 | NA | Credit Card | RIW-CFR-01-282
2025-07-18 | 1 | 11 | Jobsite Dumpster | From Waste Connections | 1521.58 | 0 | 1521.58 |  |  |  | Waste Removal Services | Waste Connections | Boulder AMEX | 10681 | NA | Credit Card | RIW-CFR-01-283
2025-07-18 | 1 | 11 | Jobsite Labor | Clean Up & Other Misc. Tasks | 420 | 0 | 420 |  |  |  | Jobsite Labor | Rodolfo Rios | RI Waxahachie | 10691 | NA | ACH | RIW-CFR-01-284
2025-07-18 | 1 | 11 | Jobsite Labor | Clean Up & Other Misc. Tasks | 570 | 0 | 570 |  |  |  | Jobsite Labor | David Salinas | RI Waxahachie | 10692 | NA | ACH | RIW-CFR-01-285
2025-07-25 | 1 | 11 | Jobsite Labor | Clean Up & Other Misc. Tasks | 973.75 | 0 | 973.75 |  |  |  | Jobsite Labor | Rodolfo Rios | RI Waxahachie | 10693 | NA | ACH | RIW-CFR-01-286
2025-07-25 | 1 | 11 | Jobsite Labor | Clean Up & Other Misc. Tasks | 330 | 0 | 330 |  |  |  | Jobsite Labor | David Salinas | RI Waxahachie | 10694 | NA | ACH | RIW-CFR-01-287
2025-07-27 | 1 | 11 | Security Cameras | Birdseye Surveillance | 1515.5 | 0 | 1515.5 |  |  |  | Jobsite Material Expenses | Birdseye Surveillance | Jaimin AMEX | 10709 | NA | Credit Card | RIW-CFR-01-288
2025-07-27 | 1 | 11 | Security Cameras | Birdseye Surveillance | 1515.5 | 0 | 1515.5 |  |  |  | Jobsite Material Expenses | Birdseye Surveillance | Jaimin AMEX | 10710 | NA | Credit Card | RIW-CFR-01-289
2025-07-27 | 1 | 11 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10711 | NA | Credit Card | RIW-CFR-01-290
2025-07-27 | 1 | 11 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10712 | NA | Credit Card | RIW-CFR-01-291
2025-07-06 | 1 | 11 | Cornerstone Safety | Per Ownership Requirements | 1500 | 0 | 1500 |  |  |  | Safety | Cornerstone Safety | [Confirm] | 10663 | NA | Credit Card | RIW-CFR-01-292
2025-07-06 | 1 | 11 | Cornerstone Safety | Per Ownership Requirements | 1500 | 0 | 1500 |  |  |  | Safety | Cornerstone Safety | [Confirm] | 10664 | NA | Credit Card | RIW-CFR-01-293
[To Be Paid] | 1 | 11 | Job Supervisor | For July 2025 | 10000 | 0 | 10000 |  |  |  | Superintendent | Boulder Construction | [To Be Paid] | NA | NA | [To Be Paid] | RIW-CFR-01-294
[To Be Paid] | 1 | 11 | Project Manager | Boulder Construction - For July 2025 | 3888.8889 | 0 | 3888.8889 |  |  |  | General Superintendent/PM | Boulder Construction | [To Be Paid] | NA | NA | [To Be Paid] | RIW-CFR-01-295
[To Be Paid] | 1 | 11 | Job Accounting / Administration | Boulder Construction - For July 2025 | 3611.1111 | 0 | 3611.1111 |  |  |  | Job Accounting/Administration | Boulder Construction | [To Be Paid] | NA | NA | [To Be Paid] | RIW-CFR-01-296
2025-05-27 | 1 | 11 | Misc. Jobsite Materials | From Home Depot - Bucket | 124.6 | 0 | 124.6 |  |  |  | Jobsite Material Expenses | Home Depot | Boulder AMEX | 10570 | NA | Credit Card | RIW-CFR-01-297
2025-07-18 | 1 | 11 | Jobsite Labor | Clean Up & Other Misc. Tasks | 330 | 0 | 330 |  |  |  | Jobsite Labor | Gloria Vargas | Boulder | 10714 | No | Check | RIW-CFR-01-298
2025-07-21 | 1 | 11 | Labor & Gas for Generators | From J&S7 Consulting | 312.21 | 0 | 312.21 |  |  |  | Gas/Oil/Travel | J&S7 Consulting | Boulder | 10715 | No | Check | RIW-CFR-01-299
2025-02-11 | 1 | 11 | Monthly Plan Printing Expense | From Great America Financial Services | 1035.14 | 0 | 1035.14 |  |  |  | Plan Reproduction/Postage | Great America Financial Services | Boulder | [TBD] | NA | [TBD] | RIW-CFR-01-300
2025-04-07 | 1 | 11 | Monthly Plan Printing Expense | From Great America Financial Services | 665.18 | 0 | 665.18 |  |  |  | Plan Reproduction/Postage | Great America Financial Services | Boulder | [TBD] | NA | [TBD] | RIW-CFR-01-301
2025-05-30 | 1 | 11 | Monthly Plan Printing Expense | From Great America Financial Services | 302.35 | 0 | 302.35 |  |  |  | Plan Reproduction/Postage | Great America Financial Services | Boulder | [TBD] | NA | [TBD] | RIW-CFR-01-302
2025-05-30 | 1 | 11 | Monthly Plan Printing Expense | From Great America Financial Services | 302.35 | 0 | 302.35 |  |  |  | Plan Reproduction/Postage | Great America Financial Services | Boulder | [TBD] | NA | [TBD] | RIW-CFR-01-303
2025-07-07 | 1 | 11 | Monthly Plan Printing Expense | From Great America Financial Services | 332.59 | 0 | 332.59 |  |  |  | Plan Reproduction/Postage | Great America Financial Services | Boulder | [TBD] | NA | [TBD] | RIW-CFR-01-304
Various | 1 | 11 | Misc. Wire and ACH Fees for RIW - True Up | From Austin Bank for Wires and ACH | 1212.8 | 0 | 1212.8 |  |  |  | Plan Reproduction/Postage | Austin Bank | RI Waxahachie | NA | NA | Bank Fees | RIW-CFR-01-305
2025-02-11 | 1 | 11 | Bank Fees for Checks | From Austin Bank for Checks | 112.82 | 0 | 112.82 |  |  |  | Plan Reproduction/Postage | Austin Bank | RI Waxahachie | NA | NA | Bank Fees | RIW-CFR-01-306
2025-05-11 | 1 | 11 | Misc. Jobsite Office Expenses (Computer, etc.) | From Micro Center | 1674.52 | 0 | 1674.52 |  |  |  | Jobsite Office Rental | Micro Center | Boulder AMEX | NA | NA | Credit Card | RIW-CFR-01-307
2025-02-11 | 1 | 11 | Misc. Jobsite Office Expenses (Radios) | From Rapid Radios | 699 | 0 | 699 |  |  |  | Jobsite Office Rental | Rapid Radios | Boulder AMEX | NA | NA | Credit Card | RIW-CFR-01-308
2024-11-30 | 1 | 11 | OpenSpace - Camera Accessories | Testing and Inspection Services - Monitoring | 200.29 | 0 | 200.29 |  |  |  | Testing and Inspection Services | OpenSpace | Boulder AMEX | NA | NA | Credit Card | RIW-CFR-01-309
Various | 1 | 11 | Cellular Data & WiFi for Jobsite Office - True Up | From Google Fi | 1427.16 | 0 | 1427.16 |  |  |  | Jobsite Office Rental | Google | Boulder AMEX | NA | NA | Credit Card | RIW-CFR-01-310
2025-07-29 | 1 | 12 | Jobsite Office - Recurring Rental | From Willscot | 817.83 | 0 | 817.83 |  |  |  | Jobsite Office Rental | Willscot | Boulder AMEX | 10767 | NA | Credit Card | RIW-CFR-01-311
2025-07-31 | 1 | 12 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10768 | NA | Credit Card | RIW-CFR-01-312
2025-08-01 | 1 | 12 | Jobsite Storage Container - Recurring Rental | From Willscot | 190.52 | 0 | 190.52 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10769 | NA | Credit Card | RIW-CFR-01-313
2025-08-01 | 1 | 12 | Jobsite Storage Container - Recurring Rental | From Willscot | 190.52 | 0 | 190.52 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10770 | NA | Credit Card | RIW-CFR-01-314
2025-08-01 | 1 | 12 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10771 | NA | Credit Card | RIW-CFR-01-315
2025-08-14 | 1 | 12 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10772 | NA | Credit Card | RIW-CFR-01-316
2025-08-01 | 1 | 12 | Jobsite Storage Container - Recurring Rental | From Willscot | 150.74 | 0 | 150.74 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10773 | NA | Credit Card | RIW-CFR-01-317
2025-08-01 | 1 | 12 | Jobsite Storage Container - Recurring Rental | From Willscot | 150.74 | 0 | 150.74 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10774 | NA | Credit Card | RIW-CFR-01-318
2025-08-01 | 1 | 12 | Temporary Toilets - Recurring Payment | A-1 Little John | 521.77 | 0 | 521.77 |  |  |  | Container Storage Rental | A-1 Little John | Boulder AMEX | 10778 | NA | Credit Card | RIW-CFR-01-319
2025-08-01 | 1 | 12 | Notary Fees | For Draw | 10 | 0 | 10 |  |  |  | Plan Reproduction/Postage | The UPS Store | Boulder AMEX | 10779 | NA | Credit Card | RIW-CFR-01-320
2025-08-04 | 1 | 12 | Jobsite Dumpster | From Waste Connections | 1521.58 | 0 | 1521.58 |  |  |  | Waste Removal Services | Waste Connections | Boulder AMEX | 10780 | NA | Credit Card | RIW-CFR-01-321
2025-08-11 | 1 | 12 | Misc. Jobsite Materials | From Home Depot - Sprayer, Saftey Vest, Combo Lock, Refill and Hard Hat | 307.42 | 0 | 307.42 |  |  |  | Jobsite Material Expenses | Home Depot | Boulder AMEX | 10789 | NA | Credit Card | RIW-CFR-01-322
2025-08-14 | 1 | 12 | Misc. Jobsite Materials | From Home Depot - Black Diamond Trimmer Line | 25.3 | 0 | 25.3 |  |  |  | Jobsite Material Expenses | Home Depot | Boulder AMEX | 10791 | NA | Credit Card | RIW-CFR-01-323
2025-08-22 | 1 | 12 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10806 | NA | Credit Card | RIW-CFR-01-324
2025-08-22 | 1 | 12 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10807 | NA | Credit Card | RIW-CFR-01-325
2025-08-20 | 1 | 12 | Misc. Jobsite Materials | From Home Depot - Caution Sign | 14.99 | 0 | 14.99 |  |  |  | Jobsite Material Expenses | Home Depot | Boulder AMEX | 10810 | NA | Credit Card | RIW-CFR-01-326
2025-08-21 | 1 | 12 | Diesel for Equipment | From Racetrac | 27.08 | 0 | 27.08 |  |  |  | Gas/Oil/Travel | Racetrac | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-327
2024-11-04 | 1 | 12 | Misc. Jobsite Expenses (Softwares, etc.) | From Docusign | 300 | 0 | 300 |  |  |  | Jobsite Office Rental | Docusign | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-328
Various | 1 | 12 | Misc. Jobsite Expenses - True Up | From Togal | 1263 | 0 | 1263 |  |  |  | Jobsite Office Rental | Togal | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-329
2025-01-07 | 1 | 12 | Misc. Jobsite Expenses (Softwares, etc.) | From Loom | 180 | 0 | 180 |  |  |  | Jobsite Office Rental | Loom | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-330
Various | 1 | 12 | Misc. Jobsite Expenses - True Up | From Lydul | 186 | 0 | 186 |  |  |  | Jobsite Office Rental | Lydul | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-331
2025-07-12 | 1 | 12 | Cellular Data & WiFi for Jobsite Office | From Google Fi | 3.19 | 0 | 3.19 |  |  |  | Jobsite Office Rental | Google Fi | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-332
2025-08-09 | 1 | 12 | Diesel for Generator | From Sunoco Gas | 12.18 | 0 | 12.18 |  |  |  | Gas/Oil/Travel | Sunoco Gas | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-333
2025-08-11 | 1 | 12 | Diesel for Generator | From Circle K | 31.59 | 0 | 31.59 |  |  |  | Gas/Oil/Travel | Circle K | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-334
2025-08-11 | 1 | 12 | Diesel for Generator | From Circle K | 28.27 | 0 | 28.27 |  |  |  | Gas/Oil/Travel | Circle K | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-335
2025-07-08 | 1 | 12 | Residence Backpack | From Amazon | 69.26 | 0 | 69.26 |  |  |  | Jobsite Material Expenses | Amazon | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-336
2025-07-19 | 1 | 12 | Residence Backpack | From Amazon | 108.22 | 0 | 108.22 |  |  |  | Jobsite Material Expenses | Amazon | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-337
2025-05-20 | 1 | 12 | Residence Backpack | From Amazon | 35.71 | 0 | 35.71 |  |  |  | Jobsite Material Expenses | Amazon | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-338
2025-07-16 | 1 | 12 | Cellular Data & WiFi for Jobsite Office | From AT&T | 37.11 | 0 | 37.11 |  |  |  | Jobsite Office Rental | AT&T | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-339
Various | 1 | 12 | Cellular Data & WiFi for Jobsite Office - True Up | From AT&T | 308.904 | 0 | 308.904 |  |  |  | Jobsite Office Rental | AT&T | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-340
Various | 1 | 12 | Misc. Jobsite Expenses | Takeoffs, Scheduling / Forecasting, Punch Lists, etc. - True Up | 2948.85 | 0 | 2948.85 |  |  |  | Jobsite Office Rental | Various | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-341
[To Be Paid] | 1 | 12 | Job Supervisor | For August 2025 | 10000 | 0 | 10000 |  |  |  | Superintendent | Boulder Construction | [To Be Paid] | NA | NA | [To Be Paid] | RIW-CFR-01-342
[To Be Paid] | 1 | 12 | Project Manager | Boulder Construction - For August 2025 | 3888.8889 | 0 | 3888.8889 |  |  |  | General Superintendent/PM | Boulder Construction | [To Be Paid] | NA | NA | [To Be Paid] | RIW-CFR-01-343
[To Be Paid] | 1 | 12 | Job Accounting / Administration | Boulder Construction - For August 2025 | 3611.1111 | 0 | 3611.1111 |  |  |  | Job Accounting/Administration | Boulder Construction | [To Be Paid] | NA | NA | [To Be Paid] | RIW-CFR-01-344
2025-08-07 | 1 | 13 | Cornerstone Safety | Per Ownership Requirements | 1500 | 0 | 1500 |  |  |  | Safety | Cornerstone Safety | [To Be Confirmed] | 10793 | NA | Credit Card | RIW-CFR-01-345
2025-08-25 | 1 | 13 | Jobsite Dumpster | From Waste Connections | 1521.58 | 0 | 1521.58 |  |  |  | Waste Removal Services | Waste Connections | Boulder AMEX | 10832 | NA | Credit Card | RIW-CFR-01-346
2025-08-26 | 1 | 13 | Jobsite Office - Recurring Rental | From Willscot | 817.83 | 0 | 817.83 |  |  |  | Jobsite Office Rental | Willscot | Boulder AMEX | 10859 | NA | Credit Card | RIW-CFR-01-347
2025-08-28 | 1 | 13 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10860 | NA | Credit Card | RIW-CFR-01-348
2025-08-29 | 1 | 13 | Jobsite Storage Container - Recurring Rental | From Willscot | 190.52 | 0 | 190.52 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10861 | NA | Credit Card | RIW-CFR-01-349
2025-08-29 | 1 | 13 | Jobsite Storage Container - Recurring Rental | From Willscot | 190.52 | 0 | 190.52 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10862 | NA | Credit Card | RIW-CFR-01-350
2025-08-29 | 1 | 13 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10863 | NA | Credit Card | RIW-CFR-01-351
2025-08-29 | 1 | 13 | Jobsite Storage Container - Recurring Rental | From Willscot | 172.33 | 0 | 172.33 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10864 | NA | Credit Card | RIW-CFR-01-352
2025-08-29 | 1 | 13 | Jobsite Storage Container - Recurring Rental | From Willscot | 172.33 | 0 | 172.33 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10865 | NA | Credit Card | RIW-CFR-01-353
2025-09-02 | 1 | 13 | Jobsite Dumpster | From Waste Connections | 1521.58 | 0 | 1521.58 |  |  |  | Waste Removal Services | Waste Connections | Boulder AMEX | 10870 | NA | Credit Card | RIW-CFR-01-354
2025-09-04 | 1 | 13 | Jobsite Dumpster | From Waste Connections | 538 | 0 | 538 |  |  |  | Waste Removal Services | Waste Connections | Boulder AMEX | 10871 | NA | Credit Card | RIW-CFR-01-355
2025-09-02 | 1 | 13 | Notary Fees | For Draw | 10 | 0 | 10 |  |  |  | Plan Reproduction/Postage | The UPS Store | Boulder AMEX | 10872 | NA | Credit Card | RIW-CFR-01-356
2025-08-29 | 1 | 13 | Temporary Toilets - Recurring Payment | A-1 Little John | 521.77 | 0 | 521.77 |  |  |  | Container Storage Rental | A-1 Little John | Boulder AMEX | 10873 | NA | Credit Card | RIW-CFR-01-357
2025-09-19 | 1 | 13 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10875 | NA | Credit Card | RIW-CFR-01-358
2025-09-19 | 1 | 13 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10876 | NA | Credit Card | RIW-CFR-01-359
2025-09-19 | 1 | 13 | Misc. Jobsite Materials | From Home Depot - Ripstop, Permanent Marker & Spray Paint | 32.33 | 0 | 32.33 |  |  |  | Jobsite Material Expenses | Home Depot | Boulder AMEX | 10877 | NA | Credit Card | RIW-CFR-01-360
2025-09-17 | 1 | 13 | Jobsite Dumpster | From Waste Connections | 1521.58 | 0 | 1521.58 |  |  |  | Waste Removal Services | Waste Connections | Boulder AMEX | 10879 | NA | Credit Card | RIW-CFR-01-361
Various | 1 | 13 | Misc. Jobsite Expenses | Takeoffs, Scheduling / Forecasting, Punch Lists, etc. - True Up | 1385.92 | 0 | 1385.92 |  |  |  | Jobsite Office Rental | Various | Boulder AMEX | Various | NA | Credit Card | RIW-CFR-01-362
2025-09-19 | 1 | 13 | Jobsite Labor | Clean Up & Other Misc. Tasks | 1068.75 | 0 | 1068.75 |  |  |  | Jobsite Labor | Rodolfo Rios | RI Waxahachie | 10881 | NA | ACH | RIW-CFR-01-363
2025-09-12 | 1 | 13 | Jobsite Labor | Clean Up & Other Misc. Tasks | 1068.75 | 0 | 1068.75 |  |  |  | Jobsite Labor | Rodolfo Rios | RI Waxahachie | 10882 | NA | ACH | RIW-CFR-01-364
2025-09-16 | 1 | 13 | Misc. Jobsite Materials | From Home Depot - Lock, Gloves, Clean-Up Bags, Safety Vest, Tow Chains | 540.3 | 0 | 540.3 |  |  |  | Jobsite Material Expenses | Home Depot | Boulder AMEX | 10885 | NA | Credit Card | RIW-CFR-01-365
2025-09-15 | 1 | 13 | Misc. Jobsite Materials | From Home Depot - Master Lock, Staple & Door Hinge | 63.17 | 0 | 63.17 |  |  |  | Jobsite Material Expenses | Home Depot | Boulder AMEX | 10886 | NA | Credit Card | RIW-CFR-01-366
2025-09-09 | 1 | 13 | Misc. Jobsite Expenses | From J&S7 Consulting | 460.73 | 0 | 460.73 |  |  |  | Jobsite Material Expenses | J&S7 Consulting | Boulder | 10889 | NA | Check | RIW-CFR-01-367
2025-09-05 | 1 | 13 | Jobsite Labor | Clean Up & Other Misc. Tasks | 160 | 0 | 160 |  |  |  | Jobsite Labor | Gloria Vargas | RI Waxahachie | 10894 | NA | Check | RIW-CFR-01-368
2025-09-15 | 1 | 13 | Monthly Plan Printing Expense | From Great America Financial Services | 634.94 | 0 | 634.94 |  |  |  | Plan Reproduction/Postage | Great America Financial Services | Boulder | 10896 | NA | Credit Card | RIW-CFR-01-369
2025-09-12 | 1 | 13 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10924 | NA | Credit Card | RIW-CFR-01-370
2025-09-26 | 1 | 13 | Jobsite Labor | Clean Up & Other Misc. Tasks | 1068.75 | 0 | 1068.75 |  |  |  | Jobsite Labor | Rodolfo Rios | RI Waxahachie | 10937 | NA | ACH | RIW-CFR-01-371
2025-07-31 | 1 | 13 | Fuel | From Interstate | 136.67 | 0 | 136.67 |  |  |  | Gas/Oil/Travel | Interstate | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-372
2025-08-07 | 1 | 13 | Lunch | From Interstate | 18.25 | 0 | 18.25 |  |  |  | Gas/Oil/Travel | Interstate | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-373
2025-08-21 | 1 | 13 | Lunch | From Interstate | 19.49 | 0 | 19.49 |  |  |  | Gas/Oil/Travel | Interstate | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-374
2025-08-21 | 1 | 13 | Hydration | From N Highway | 26.11 | 0 | 26.11 |  |  |  | Gas/Oil/Travel | N Highway | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-375
2025-08-29 | 1 | 13 | Hydration | From N Highway | 35.29 | 0 | 35.29 |  |  |  | Gas/Oil/Travel | N Highway | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-376
Various | 1 | 13 | Cellular Data & WiFi for Jobsite Office - True Up | From AT&T | 719.44 | 0 | 719.44 |  |  |  | Jobsite Office Rental | AT&T | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-377
Various | 1 | 13 | Misc. Jobsite Expenses | From Plaud | 215.99 | 0 | 215.99 |  |  |  | Jobsite Office Rental | Plaud | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-378
Various | 1 | 13 | Gas/Fuel/Travel Expenses - True Up | Meals/Gas/Fuel/Travel Expenses - True Up | 1094.01 | 0 | 1094.01 |  |  |  | Gas/Oil/Travel | Various | Boulder AMEX | Various | NA | Credit Card | RIW-CFR-01-379
[To Be Paid] | 1 | 13 | Job Supervisor | For September 2025 | 10000 | 0 | 10000 |  |  |  | Superintendent | Boulder Construction | [To Be Paid] | NA | NA | [To Be Paid] | RIW-CFR-01-380
[To Be Paid] | 1 | 13 | Project Manager | Boulder Construction - For September 2025 | 3888.8889 | 0 | 3888.8889 |  |  |  | General Superintendent/PM | Boulder Construction | [To Be Paid] | NA | NA | [To Be Paid] | RIW-CFR-01-381
[To Be Paid] | 1 | 13 | Job Accounting / Administration | Boulder Construction - For September 2025 | 3611.1111 | 0 | 3611.1111 |  |  |  | Job Accounting/Administration | Boulder Construction | [To Be Paid] | NA | NA | [To Be Paid] | RIW-CFR-01-382
2025-09-23 | 1 | 14 | Jobsite Office - Recurring Rental | From Willscot | 921.75 | 0 | 921.75 |  |  |  | Jobsite Office Rental | Willscot | Boulder AMEX | 10939 | NA | Credit Card | RIW-CFR-01-383
2025-09-25 | 1 | 14 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10940 | NA | Credit Card | RIW-CFR-01-384
2025-09-26 | 1 | 14 | Jobsite Storage Container - Recurring Rental | From Willscot | 190.52 | 0 | 190.52 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10941 | NA | Credit Card | RIW-CFR-01-385
2025-09-26 | 1 | 14 | Jobsite Storage Container - Recurring Rental | From Willscot | 190.52 | 0 | 190.52 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10942 | NA | Credit Card | RIW-CFR-01-386
2025-09-26 | 1 | 14 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10943 | NA | Credit Card | RIW-CFR-01-387
2025-09-26 | 1 | 14 | Jobsite Storage Container - Recurring Rental | From Willscot | 172.33 | 0 | 172.33 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10944 | NA | Credit Card | RIW-CFR-01-388
2025-09-26 | 1 | 14 | Jobsite Storage Container - Recurring Rental | From Willscot | 172.33 | 0 | 172.33 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10945 | NA | Credit Card | RIW-CFR-01-389
2025-10-09 | 1 | 14 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10946 | NA | Credit Card | RIW-CFR-01-390
2025-10-17 | 1 | 14 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10947 | NA | Credit Card | RIW-CFR-01-391
2025-10-17 | 1 | 14 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 10948 | NA | Credit Card | RIW-CFR-01-392
2025-10-21 | 1 | 14 | Jobsite Office - Recurring Rental | From Willscot | 921.75 | 0 | 921.75 |  |  |  | Jobsite Office Rental | Willscot | Boulder AMEX | 10949 | NA | Credit Card | RIW-CFR-01-393
2025-09-23 | 1 | 14 | Jobsite Dumpster | From Waste Connections | 1521.58 | 0 | 1521.58 |  |  |  | Waste Removal Services | Waste Connections | Boulder AMEX | 10950 | NA | Credit Card | RIW-CFR-01-394
2025-10-09 | 1 | 14 | Jobsite Dumpster | From Waste Connections | 1521.58 | 0 | 1521.58 |  |  |  | Waste Removal Services | Waste Connections | Boulder AMEX | 10951 | NA | Credit Card | RIW-CFR-01-395
2025-10-21 | 1 | 14 | Jobsite Dumpster | From Waste Connections | 1696.89 | 0 | 1696.89 |  |  |  | Waste Removal Services | Waste Connections | Boulder AMEX | 10952 | NA | Credit Card | RIW-CFR-01-396
2025-09-02 | 1 | 14 | Notary Fees | For Draw | 10 | 0 | 10 |  |  |  | Plan Reproduction/Postage | The UPS Store | Boulder AMEX | 10872 | NA | Credit Card | RIW-CFR-01-397
2025-09-26 | 1 | 14 | Temporary Toilets - Recurring Payment | A-1 Little John | 521.77 | 0 | 521.77 |  |  |  | Container Storage Rental | A-1 Little John | Boulder AMEX | 10954 | NA | Credit Card | RIW-CFR-01-398
2025-09-19 | 1 | 14 | Security Cameras | Birdseye Surveillance | 1515.5 | 0 | 1515.5 |  |  |  | Jobsite Material Expenses | Birdseye Surveillance | Jaimin AMEX | 10955 | NA | Credit Card | RIW-CFR-01-399
2025-09-19 | 1 | 14 | Security Cameras | Birdseye Surveillance | 1515.5 | 0 | 1515.5 |  |  |  | Jobsite Material Expenses | Birdseye Surveillance | Jaimin AMEX | 10956 | NA | Credit Card | RIW-CFR-01-400
2025-10-24 | 1 | 14 | Temporary Toilets - Recurring Payment | A-1 Little John | 521.77 | 0 | 521.77 |  |  |  | Container Storage Rental | A-1 Little John | Boulder AMEX | 11000 | NA | Credit Card | RIW-CFR-01-401
2025-10-10 | 1 | 14 | Misc. Jobsite Expenses | From J&S7 Consulting | 1325.69 | 0 | 1325.69 |  |  |  | Gas/Oil/Travel | J&S7 Consulting | Boulder | 11006 | NA | Check | RIW-CFR-01-402
2025-10-24 | 1 | 14 | OpenSpace - Subscription | Testing and Inspection Services - Monitoring | 6156.15 | 0 | 6156.15 |  |  |  | Testing and Inspection Services | OpenSpace | Boulder AMEX | 11013 | NA | Credit Card | RIW-CFR-01-403
2025-10-24 | 1 | 14 | Temporary Toilets - Recurring Payment | A-1 Little John | 521.77 | 0 | 521.77 |  |  |  | Container Storage Rental | A-1 Little John | Boulder AMEX | 11014 | NA | Credit Card | RIW-CFR-01-404
2025-10-23 | 1 | 14 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 11016 | NA | Credit Card | RIW-CFR-01-405
2025-10-24 | 1 | 14 | Jobsite Storage Container - Recurring Rental | From Willscot | 190.52 | 0 | 190.52 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 11017 | NA | Credit Card | RIW-CFR-01-406
2025-10-24 | 1 | 14 | Jobsite Storage Container - Recurring Rental | From Willscot | 190.52 | 0 | 190.52 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 11018 | NA | Credit Card | RIW-CFR-01-407
2025-10-24 | 1 | 14 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 11019 | NA | Credit Card | RIW-CFR-01-408
2025-10-24 | 1 | 14 | Jobsite Storage Container - Recurring Rental | From Willscot | 172.33 | 0 | 172.33 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 11020 | NA | Credit Card | RIW-CFR-01-409
2025-10-24 | 1 | 14 | Jobsite Storage Container - Recurring Rental | From Willscot | 172.33 | 0 | 172.33 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 11021 | NA | Credit Card | RIW-CFR-01-410
2025-10-30 | 1 | 14 | Jobsite Dumpster | From Waste Connections | 1521.58 | 0 | 1521.58 |  |  |  | Waste Removal Services | Waste Connections | Boulder AMEX | 11023 | NA | Credit Card | RIW-CFR-01-411
2025-08-01 | 1 | 14 | Cornerstone Safety | Per Ownership Requirements | 1500 | 0 | 1500 |  |  |  | Safety | Cornerstone Safety | Jai | 11025 | NA | Credit Card | RIW-CFR-01-412
2025-09-01 | 1 | 14 | Cornerstone Safety | Per Ownership Requirements | 1500 | 0 | 1500 |  |  |  | Safety | Cornerstone Safety | Jai | 11026 | NA | Credit Card | RIW-CFR-01-413
2025-10-01 | 1 | 14 | Cornerstone Safety | Per Ownership Requirements | 1500 | 0 | 1500 |  |  |  | Safety | Cornerstone Safety | Jai | 11027 | NA | Credit Card | RIW-CFR-01-414
2025-11-01 | 1 | 14 | Cornerstone Safety | Per Ownership Requirements | 1500 | 0 | 1500 |  |  |  | Safety | Cornerstone Safety | Jai | 11028 | NA | Credit Card | RIW-CFR-01-415
2025-10-01 | 1 | 14 | Meals | From Ohana | 39.5 | 0 | 39.5 |  |  |  | Gas/Oil/Travel | Ohana | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-416
2025-10-17 | 1 | 14 | Fuel | From Exxon | 115.61 | 0 | 115.61 |  |  |  | Gas/Oil/Travel | Exxon | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-417
2025-10-10 | 1 | 14 | Fuel | From [200S Interstate] | 121.22 | 0 | 121.22 |  |  |  | Gas/Oil/Travel | [200S Interstate] | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-418
2025-09-19 | 1 | 14 | Misc. Jobsite Materials | From Plaud | 129.594 | 0 | 129.594 |  |  |  | Jobsite Material Expenses | Plaud | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-419
2025-07-30 | 1 | 14 | Cellular Data & WiFi for Jobsite Office | From AT&T | 37.11 | 0 | 37.11 |  |  |  | Jobsite Office Rental | AT&T | Jaimin AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-420
2025-07-16 | 1 | 14 | Cellular Data & WiFi for Jobsite Office - True Up | From AT&T | 22.266 | 0 | 22.266 |  |  |  | Jobsite Office Rental | AT&T | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-421
Various | 1 | 14 | Misc. Jobsite Expenses (Softwares, etc.) - True Up | Takeoffs, Scheduling / Forecasting, Punch Lists, etc. | 1155.67 | 0 | 1155.67 |  |  |  | Jobsite Office Rental | Various | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-422
Various | 1 | 14 | Cellular Data & WiFi for Jobsite Office | From Google Fi | 537.72 | 0 | 537.72 |  |  |  | Jobsite Office Rental | Google Fi | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-423
[To Be Paid] | 1 | 14 | Job Supervisor | For October 2025 | 10000 | 0 | 10000 |  |  |  | Superintendent | Boulder Construction | [To Be Paid] | NA | NA | [To Be Paid] | RIW-CFR-01-424
[To Be Paid] | 1 | 14 | Project Manager | Boulder Construction - For October 2025 | 3888.8889 | 0 | 3888.8889 |  |  |  | General Superintendent/PM | Boulder Construction | [To Be Paid] | NA | NA | [To Be Paid] | RIW-CFR-01-425
[To Be Paid] | 1 | 14 | Job Accounting / Administration | Boulder Construction - For October 2025 | 3611.1111 | 0 | 3611.1111 |  |  |  | Job Accounting/Administration | Boulder Construction | [To Be Paid] | NA | NA | [To Be Paid] | RIW-CFR-01-426
2025-11-13 | 1 | 15 | Notary Fees | For Draw | 10 | 0 | 10 |  |  |  | Plan Reproduction/Postage | The UPS Store | Boulder AMEX | 11063 | NA | Credit Card | RIW-CFR-01-427
2025-11-06 | 1 | 15 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscott | Boulder AMEX | 11066 | NA | Credit Card | RIW-CFR-01-428
2025-11-10 | 1 | 15 | Jobsite Material Expenses | From Home Depot - Rust-Oleum Stops Rust 5 in 1 Custom Spray | 32.39 | 0 | 32.39 |  |  |  | Jobsite Material Expenses | Home Depot | Boulder AMEX | 11070 | NA | Credit Card | RIW-CFR-01-429
2025-11-13 | 1 | 15 | Jobsite Dumpster | From Waste Connections | 1521.58 | 0 | 1521.58 |  |  |  | Waste Removal Services | Waste Connections | Boulder AMEX | 11073 | NA | Credit Card | RIW-CFR-01-430
2025-11-14 | 1 | 15 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscott | Boulder AMEX | 11077 | NA | Credit Card | RIW-CFR-01-431
2025-11-14 | 1 | 15 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscott | Boulder AMEX | 11078 | NA | Credit Card | RIW-CFR-01-432
2025-11-18 | 1 | 15 | Jobsite Office - Recurring Rental | From Willscot | 921.75 | 0 | 921.75 |  |  |  | Jobsite Office Rental | Willscott | Boulder AMEX | 11079 | NA | Credit Card | RIW-CFR-01-433
2025-11-20 | 1 | 15 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscott | Boulder AMEX | 11080 | NA | Credit Card | RIW-CFR-01-434
2025-11-21 | 1 | 15 | Jobsite Storage Container - Recurring Rental | From Willscot | 190.52 | 0 | 190.52 |  |  |  | Container Storage Rental | Willscott | Boulder AMEX | 11081 | NA | Credit Card | RIW-CFR-01-435
2025-11-21 | 1 | 15 | Jobsite Storage Container - Recurring Rental | From Willscot | 190.52 | 0 | 190.52 |  |  |  | Container Storage Rental | Willscott | Boulder AMEX | 11082 | NA | Credit Card | RIW-CFR-01-436
2025-11-21 | 1 | 15 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscott | Boulder AMEX | 11083 | NA | Credit Card | RIW-CFR-01-437
2025-11-21 | 1 | 15 | Jobsite Storage Container - Recurring Rental | From Willscot | 172.33 | 0 | 172.33 |  |  |  | Container Storage Rental | Willscott | Boulder AMEX | 11084 | NA | Credit Card | RIW-CFR-01-438
2025-11-21 | 1 | 15 | Jobsite Storage Container - Recurring Rental | From Willscot | 172.33 | 0 | 172.33 |  |  |  | Container Storage Rental | Willscott | Boulder AMEX | 11085 | NA | Credit Card | RIW-CFR-01-439
2025-11-25 | 1 | 15 | Jobsite Storage Container - Recurring Rental | From Willscott | 1038.12 | 0 | 1038.12 |  |  |  | Container Storage Rental | Willscott | Boulder AMEX | 11086 | NA | Credit Card | RIW-CFR-01-440
2025-12-04 | 1 | 15 | Jobsite Storage Container - Recurring Rental | From Willscott | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscott | Boulder AMEX | 11087 | NA | Credit Card | RIW-CFR-01-441
2025-11-26 | 1 | 15 | Jobsite Dumpster | From Waste Connections | 1521.58 | 0 | 1521.58 |  |  |  | Waste Removal Services | Waste Connections | Boulder AMEX | 11088 | NA | Credit Card | RIW-CFR-01-442
2025-12-02 | 1 | 15 | Jobsite Dumpster | From Waste Connections | 1613.43 | 0 | 1613.43 |  |  |  | Waste Removal Services | Waste Connections | Boulder AMEX | 11089 | NA | Credit Card | RIW-CFR-01-443
2025-11-21 | 1 | 15 | Jobsite Material Expenses | From Home Depot - Washer Head Drill-Point Screw & Padlock with Key | 60.65 | 0 | 60.65 |  |  |  | Jobsite Material Expenses | Home Depot | Boulder AMEX | 11096 | NA | Credit Card | RIW-CFR-01-444
2025-11-24 | 1 | 15 | Temporary Toilets - Recurring Payment | A-1 Little John | 521.77 | 0 | 521.77 |  |  |  | Container Storage Rental | A-1 Little John | Boulder AMEX | 11097 | NA | Credit Card | RIW-CFR-01-445
2025-11-26 | 1 | 15 | Jobsite Material Expenses | From Home Depot - Contractor Bags | 64.89 | 0 | 64.89 |  |  |  | Jobsite Material Expenses | Home Depot | Boulder AMEX | 11106 | NA | Credit Card | RIW-CFR-01-446
2025-12-05 | 1 | 15 | Jobsite Material Expenses | From Home Depot - Black Large Chisel Tip Jobsite Permanent Marker | 21.01 | 0 | 21.01 |  |  |  | Jobsite Material Expenses | Home Depot | Boulder AMEX | 11119 | NA | Credit Card | RIW-CFR-01-447
2025-12-05 | 1 | 15 | Blueprint Printing | Stewart Engineering | 277.66 | 0 | 277.66 |  |  |  | Plan Reproduction/Postage | Stewart Engineering | Boulder AMEX | 11142 | NA | Credit Card | RIW-CFR-01-448
2025-11-24 | 1 | 15 | Monthly Plan Printing Expense | From Great America Financial Services | 1108.25 | 0 | 1108.25 |  |  |  | Plan Reproduction/Postage | Great America Financial Services | Boulder | [TBD] | No | Check | RIW-CFR-01-449
2025-12-19 | 1 | 15 | Temporary Toilets - Recurring Payment | A-1 Little John | 521.77 | 0 | 521.77 |  |  |  | Container Storage Rental | A-1 Little John | Boulder AMEX | 11154 | NA | Credit Card | RIW-CFR-01-450
2025-12-10 | 1 | 15 | Misc. Jobsite Expenses | From J&S7 Consulting | 1586.97 | 0 | 1586.97 |  |  |  | Gas/Oil/Travel | J&S7 Consulting | Boulder | 11159 | NA | Check | RIW-CFR-01-451
2025-12-08 | 1 | 15 | Jobsite Dumpster | From Waste Connections | 2105.22 | 0 | 2105.22 |  |  |  | Waste Removal Services | Waste Connections | Boulder AMEX | 11165 | NA | Credit Card | RIW-CFR-01-452
2025-12-12 | 1 | 15 | Jobsite Storage Container - Recurring Rental | From Willscott | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscott | Boulder AMEX | 11175 | NA | Credit Card | RIW-CFR-01-453
2025-12-12 | 1 | 15 | Jobsite Storage Container - Recurring Rental | From Willscott | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscott | Boulder AMEX | 11176 | NA | Credit Card | RIW-CFR-01-454
2025-12-13 | 1 | 15 | Jobsite Material Expenses | From Home Depot - Vacuum with Filter, Hose and Accessories | 108.23 | 0 | 108.23 |  |  |  | Jobsite Material Expenses | Home Depot | Boulder AMEX | 11178 | NA | Credit Card | RIW-CFR-01-455
2025-12-15 | 1 | 15 | Jobsite Dumpster | From Waste Connections | 1052.61 | 0 | 1052.61 |  |  |  | Waste Removal Services | Waste Connections | Boulder AMEX | 11185 | NA | Credit Card | RIW-CFR-01-456
2025-12-15 | 1 | 15 | Jobsite Dumpster | From Waste Connections | 491.79 | 0 | 491.79 |  |  |  | Waste Removal Services | Waste Connections | Boulder AMEX | 11186 | NA | Credit Card | RIW-CFR-01-457
2025-12-16 | 1 | 15 | Jobsite Material Expenses | From Home Depot - Contractor Bags | 64.89 | 0 | 64.89 |  |  |  | Jobsite Material Expenses | Home Depot | Boulder AMEX | 11189 | NA | Credit Card | RIW-CFR-01-458
2025-12-16 | 1 | 15 | Jobsite Office - Recurring Rental | From Willscott | 921.75 | 0 | 921.75 |  |  |  | Jobsite Office Rental | Willscott | Boulder AMEX | 11190 | NA | Credit Card | RIW-CFR-01-459
2025-12-18 | 1 | 15 | Jobsite Storage Container - Recurring Rental | From Willscott | 214.06 | 0 | 214.06 |  |  |  | Container Storage Rental | Willscott | Boulder AMEX | 11197 | NA | Credit Card | RIW-CFR-01-460
2025-12-19 | 1 | 15 | Jobsite Storage Container - Recurring Rental | From Willscott | 214.06 | 0 | 214.06 |  |  |  | Container Storage Rental | Willscott | Boulder AMEX | 11199 | NA | Credit Card | RIW-CFR-01-461
2025-12-19 | 1 | 15 | Jobsite Storage Container - Recurring Rental | From Willscott | 190.52 | 0 | 190.52 |  |  |  | Container Storage Rental | Willscott | Boulder AMEX | 11200 | NA | Credit Card | RIW-CFR-01-462
2025-12-19 | 1 | 15 | Jobsite Storage Container - Recurring Rental | From Willscott | 190.52 | 0 | 190.52 |  |  |  | Container Storage Rental | Willscott | Boulder AMEX | 11201 | NA | Credit Card | RIW-CFR-01-463
2025-12-19 | 1 | 15 | Jobsite Storage Container - Recurring Rental | From Willscott | 172.33 | 0 | 172.33 |  |  |  | Container Storage Rental | Willscott | Boulder AMEX | 11202 | NA | Credit Card | RIW-CFR-01-464
2025-12-19 | 1 | 15 | Jobsite Storage Container - Recurring Rental | From Willscott | 172.33 | 0 | 172.33 |  |  |  | Container Storage Rental | Willscott | Boulder AMEX | 11203 | NA | Credit Card | RIW-CFR-01-465
2025-12-19 | 1 | 15 | Temporary Toilets - Recurring Payment | From A-1 Little John | 521.77 | 0 | 521.77 |  |  |  | Container Storage Rental | A-1 Little John | Boulder AMEX | 11204 | NA | Credit Card | RIW-CFR-01-466
2025-12-22 | 1 | 15 | Jobsite Storage Container - Recurring Rental | From Willscott | 190.52 | 0 | 190.52 |  |  |  | Container Storage Rental | Willscott | Boulder AMEX | 11210 | NA | Credit Card | RIW-CFR-01-467
2025-12-22 | 1 | 15 | Jobsite Dumpster | From Waste Connections | 2105.22 | 0 | 2105.22 |  |  |  | Waste Removal Services | Waste Connections | Boulder AMEX | 11215 | NA | Credit Card | RIW-CFR-01-468
2025-10-24 | 1 | 15 | Fuel | From Lovers | 126.64 | 0 | 126.64 |  |  |  | Gas/Oil/Travel | Lovers | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-469
2025-10-27 | 1 | 15 | Fuel | From Texaco | 13.45 | 0 | 13.45 |  |  |  | Gas/Oil/Travel | Texaco | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-470
2025-11-10 | 1 | 15 | Fuel | From Interstate | 10.47 | 0 | 10.47 |  |  |  | Gas/Oil/Travel | Interstate | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-471
2025-11-18 | 1 | 15 | Fuel | From Racetrac | 35.51 | 0 | 35.51 |  |  |  | Gas/Oil/Travel | Racetrac | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-472
2025-11-29 | 1 | 15 | Fuel | From Racetrac | 24.9 | 0 | 24.9 |  |  |  | Gas/Oil/Travel | Racetrac | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-473
2025-12-02 | 1 | 15 | Fuel | From QT | 19.68 | 0 | 19.68 |  |  |  | Gas/Oil/Travel | QT | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-474
2025-11-07 | 1 | 15 | Fuel | From Circle K | 18.34 | 0 | 18.34 |  |  |  | Gas/Oil/Travel | Circle K | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-475
2024-12-23 | 1 | 15 | Diesel for Equipment | Job Supervisor | 1000 | 0 | 1000 |  |  |  | Gas/Oil/Travel | Maddox Sullivan | RI Waxahachie | [TBD] | NA | ACH | RIW-CFR-01-476
2025-10-24 | 1 | 15 | Meal | From Dairy Queen | 19.06 | 0 | 19.06 |  |  |  | Gas/Oil/Travel | Dairy Queen | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-477
2025-11-08 | 1 | 15 | Fuel | From N Highway | 92.95 | 0 | 92.95 |  |  |  | Gas/Oil/Travel | N Highway | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-478
2025-12-03 | 1 | 15 | Fuel | From Exxon | 25.48 | 0 | 25.48 |  |  |  | Gas/Oil/Travel | Exxon | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-479
2025-11-17 | 1 | 15 | Notary Fees | For Draw | 10 | 0 | 10 |  |  |  | Plan Reproduction/Postage | The UPS Store | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-480
2025-08-14 | 1 | 15 | Fuel/Vehicle | From Take 5 | 325.12 | 0 | 325.12 |  |  |  | Gas/Oil/Travel | Take 5 | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-481
Various | 1 | 15 | Misc. Jobsite Expenses (Softwares, etc.) - True Up | Takeoffs, Scheduling / Forecasting, Punch Lists, etc. | 2123.79 | 0 | 2123.79 |  |  |  | Jobsite Office Rental | Various | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-482
2025-11-27 | 1 | 15 | Cellular Data & WiFi for Jobsite Office | From Google Fi | 269.16 | 0 | 269.16 |  |  |  | Jobsite Office Rental | Google Fi | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-483
Various | 1 | 15 | Cellular Data & WiFi for Jobsite Office | From AT&T | 1470.87 | 0 | 1470.87 |  |  |  | Jobsite Office Rental | AT&T | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-484
2025-11-12 | 1 | 15 | Misc. Jobsite Expenses | From Google One | 10.65 | 0 | 10.65 |  |  |  | Jobsite Office Rental | Google One | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-485
2025-12-12 | 1 | 15 | Misc. Jobsite Expenses | From Google One | 10.65 | 0 | 10.65 |  |  |  | Jobsite Office Rental | Google One | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-486
2025-11-10 | 1 | 15 | Misc. Jobsite Expenses | From S P Plaud | 179 | 0 | 179 |  |  |  | Jobsite Office Rental | S P Plaud | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-487
2025-11-10 | 1 | 15 | Misc. Jobsite Expenses | From S P Plaud | 169 | 0 | 169 |  |  |  | Jobsite Office Rental | S P Plaud | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-488
2025-08-08 | 1 | 15 | Monthly Plan Printing Expense | From Great America Financial Services | 302.35 | 0 | 302.35 |  |  |  | Plan Reproduction/Postage | Great America Financial Services | Boulder | [TBD] | NA | Direct Pay | RIW-CFR-01-489
2025-12-16 | 1 | 15 | Monthly Plan Printing Expense | From Great America Financial Services | 1108.25 | 0 | 1108.25 |  |  |  | Plan Reproduction/Postage | Great America Financial Services | Boulder | 11151 | No | Direct Pay | RIW-CFR-01-490
Various | 1 | 15 | Misc. Wire and ACH Fees for RIW | From Austin Bank for Wires and ACH | 766.3 | 0 | 766.3 |  |  |  | Plan Reproduction/Postage | Austin Bank | RI Waxahachie | NA | NA | Bank Fees | RIW-CFR-01-491
[To Be Paid] | 1 | 15 | Job Supervisor | For November 2025 | 10000 | 0 | 10000 |  |  |  | Superintendent | Boulder Construction | [To Be Paid] | NA | NA | [To Be Paid] | RIW-CFR-01-492
[To Be Paid] | 1 | 15 | Project Manager | Boulder Construction - For November 2025 | 3888.8889 | 0 | 3888.8889 |  |  |  | General Superintendent/PM | Boulder Construction | [To Be Paid] | NA | NA | [To Be Paid] | RIW-CFR-01-493
[To Be Paid] | 1 | 15 | Job Accounting / Administration | Boulder Construction - For November 2025 | 3611.1111 | 0 | 3611.1111 |  |  |  | Job Accounting/Administration | Boulder Construction | [To Be Paid] | NA | NA | [To Be Paid] | RIW-CFR-01-494
[To Be Paid] | 1 | 15 | Job Supervisor | For December 2025 | 10000 | 0 | 10000 |  |  |  | Superintendent | Boulder Construction | [To Be Paid] | NA | NA | [To Be Paid] | RIW-CFR-01-495
[To Be Paid] | 1 | 15 | Project Manager | Boulder Construction - For December 2025 | 3888.8889 | 0 | 3888.8889 |  |  |  | General Superintendent/PM | Boulder Construction | [To Be Paid] | NA | NA | [To Be Paid] | RIW-CFR-01-496
[To Be Paid] | 1 | 15 | Job Accounting / Administration | Boulder Construction - For December 2025 | 3611.1111 | 0 | 3611.1111 |  |  |  | Job Accounting/Administration | Boulder Construction | [To Be Paid] | NA | NA | [To Be Paid] | RIW-CFR-01-497
2025-12-04 | 1 | 16 | Misc. Jobsite Material Expenses | From Home Depot - Diesel Exhaust Fluid | 20.52 | 0 | 20.52 |  |  |  | Jobsite Material Expenses | Home Depot | [To Be Confirmed] | 11136 | NA | Credit Card | RIW-CFR-01-498
2025-12-22 | 1 | 16 | Jobsite Storage Container - Recurring Rental | From Willscott | 190.52 | 0 | 190.52 |  |  |  | Container Storage Rental | Willscott | Boulder AMEX | 11210 | NA | Credit Card | RIW-CFR-01-499
2026-01-13 | 1 | 16 | Jobsite Office - Recurring Rental | From Willscott | 921.75 | 0 | 921.75 |  |  |  | Jobsite Office Rental | Willscott | Boulder AMEX | 11226 | NA | Credit Card | RIW-CFR-01-500
2026-01-15 | 1 | 16 | Jobsite Storage Container - Recurring Rental | From Willscott | 214.06 | 0 | 214.06 |  |  |  | Container Storage Rental | Willscott | Boulder AMEX | 11229 | NA | Credit Card | RIW-CFR-01-501
2026-01-16 | 1 | 16 | Temporary Toilets | From A-1 Little John | 954.77 | 0 | 954.77 |  |  |  | Container Storage Rental | A-1 Little John | Boulder AMEX | 11230 | NA | Credit Card | RIW-CFR-01-502
2026-01-01 | 1 | 16 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscott | Boulder AMEX | 11236 | NA | Credit Card | RIW-CFR-01-503
2026-01-09 | 1 | 16 | Jobsite Storage Container - Recurring Rental | From Willscott | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscott | Boulder AMEX | 11248 | NA | Credit Card | RIW-CFR-01-504
2026-01-09 | 1 | 16 | Jobsite Storage Container - Recurring Rental | From Willscott | 187.27 | 0 | 187.27 |  |  |  | Container Storage Rental | Willscott | Boulder AMEX | 11249 | NA | Credit Card | RIW-CFR-01-505
2026-01-05 | 1 | 16 | Jobsite Dumpster | From City of Waxahachie | 3439.37 | 0 | 3439.37 |  |  |  | Waste Removal Services | Waste Connections | Boulder AMEX | 11272 | NA | Credit Card | RIW-CFR-01-506
01-25-25 | 1 | 16 | Construction Site Camera | From Birdseye Surveillance LLC | 1299 | 0 | 1299 |  |  |  | Jobsite Material Expenses | Birdseye Surveillance LLC | Jaimin AMEX | 11274 | NA | Credit Card | RIW-CFR-01-507
01-25-25 | 1 | 16 | Construction Site Camera | From Birdseye Surveillance LLC | 1299 | 0 | 1299 |  |  |  | Jobsite Material Expenses | Birdseye Surveillance LLC | Jaimin AMEX | 11275 | NA | Credit Card | RIW-CFR-01-508
01-25-25 | 1 | 16 | Construction Site Camera | From Birdseye Surveillance LLC | 1515.5 | 0 | 1515.5 |  |  |  | Jobsite Material Expenses | Birdseye Surveillance LLC | Jaimin AMEX | 11277 | NA | Credit Card | RIW-CFR-01-509
2026-01-23 | 1 | 16 | Jobsite Labor | From Rodolfo Rios | 1187.5 | 0 | 1187.5 |  |  |  | Jobsite Labor | Rodolfo Rios | RI Waxahachie | 11293 | NA | ACH | RIW-CFR-01-510
2026-01-16 | 1 | 16 | Jobsite Labor | From Rodolfo Rios | 1306.25 | 0 | 1306.25 |  |  |  | Jobsite Labor | Rodolfo Rios | RI Waxahachie | 12170 | NA | ACH | RIW-CFR-01-511
2026-01-16 | 1 | 16 | Jobsite Labor | From David Salinas | 795 | 0 | 795 |  |  |  | Jobsite Labor | David Salinas | RI Waxahachie | 12171 | NA | ACH | RIW-CFR-01-512
2026-01-30 | 1 | 16 | Jobsite Labor | From Rodolfo Rios | 1068.75 | 0 | 1068.75 |  |  |  | Jobsite Labor | Rodolfo Rios | RI Waxahachie | 12172 | NA | ACH | RIW-CFR-01-513
2026-01-30 | 1 | 16 | Jobsite Labor | From David Salinas | 525.5 | 0 | 525.5 |  |  |  | Jobsite Labor | David Salinas | RI Waxahachie | 12173 | NA | ACH | RIW-CFR-01-514
[TBC] | 1 | 16 | Procore | For Jobsite Reporting | 8859.8 | 0 | 8859.8 |  |  |  | Jobsite Material Expenses | Procore | [To Be Paid] | 12180 | NA | [To Be Paid] | RIW-CFR-01-515
2026-01-16 | 1 | 16 | Jobsite Storage Container - Recurring Rental | From Willscott | 214.06 | 0 | 214.06 |  |  |  | Container Storage Rental | Willscott | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-516
2026-01-16 | 1 | 16 | Jobsite Storage Container - Recurring Rental | From Willscott | 190.52 | 0 | 190.52 |  |  |  | Container Storage Rental | Willscott | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-517
2026-01-16 | 1 | 16 | Jobsite Storage Container - Recurring Rental | From Willscott | 190.52 | 0 | 190.52 |  |  |  | Container Storage Rental | Willscott | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-518
2026-01-16 | 1 | 16 | Jobsite Storage Container - Recurring Rental | From Willscott | 172.33 | 0 | 172.33 |  |  |  | Container Storage Rental | Willscott | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-519
2026-01-16 | 1 | 16 | Jobsite Storage Container - Recurring Rental | From Willscott | 172.33 | 0 | 172.33 |  |  |  | Container Storage Rental | Willscott | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-520
2026-01-15 | 1 | 16 | Misc. Jobsite Material Expenses | From Lowe's | 41.09 | 0 | 41.09 |  |  |  | Jobsite Material Expenses | Lowe's | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-521
2026-01-19 | 1 | 16 | Jobsite Storage Container - Recurring Rental | From Willscott | 190.52 | 0 | 190.52 |  |  |  | Container Storage Rental | Willscott | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-522
2026-01-20 | 1 | 16 | Jobsite Dumpster | From City of Waxahachie | 2105.22 | 0 | 2105.22 |  |  |  | Waste Removal Services | Waste Connections | Boulder AMEX | 12272 | NA | Credit Card | RIW-CFR-01-523
2024-12-07 | 1 | 16 | OpenSpace Camera - Battery | From Amazon | 86.58 | 0 | 86.58 |  |  |  | Jobsite Material Expenses | Amazon | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-524
2024-12-07 | 1 | 16 | OpenSpace Camera - SD Card | From Amazon | 123.08 | 0 | 123.08 |  |  |  | Jobsite Material Expenses | Amazon | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-525
2024-12-08 | 1 | 16 | OpenSpace Camera - Cover | From Amazon | 6.48 | 0 | 6.48 |  |  |  | Jobsite Material Expenses | Amazon | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-526
2025-09-12 | 1 | 16 | Jobs Supervisor Equipment Accessories | From Amazon | 37.88 | 0 | 37.88 |  |  |  | Jobsite Material Expenses | Amazon | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-527
2025-09-16 | 1 | 16 | OpenSpace Camera - Stick | From Amazon | 20.56 | 0 | 20.56 |  |  |  | Jobsite Material Expenses | Amazon | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-528
Various | 1 | 16 | Meals & Fuel | For Jobsite Travel | 818.96 | 0 | 818.96 |  |  |  | Gas/Oil/Travel | Various | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-529
Various | 1 | 16 | Misc. Jobsite Expenses (Softwares, etc.) - True Up | Takeoffs, Scheduling / Forecasting, Punch Lists, etc. | 948.46 | 0 | 948.46 |  |  |  | Jobsite Office Rental | Various | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-530
2026-01-27 | 1 | 16 | Cellular Data & WiFi for Jobsite Office | From Google Fi | 269.16 | 0 | 269.16 |  |  |  | Jobsite Office Rental | Google Fi | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-531
2025-12-27 | 1 | 16 | Cellular Data & WiFi for Jobsite Office | From Google Fi | 269.16 | 0 | 269.16 |  |  |  | Jobsite Office Rental | Google Fi | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-532
Various | 1 | 16 | Cellular Data & WiFi for Jobsite Office | From AT&T | 412.84 | 0 | 412.84 |  |  |  | Jobsite Office Rental | AT&T | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-533
2026-01-12 | 1 | 16 | Misc. Jobsite Expenses | From Google One | 10.65 | 0 | 10.65 |  |  |  | Jobsite Office Rental | Google One | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-534
2025-12-19 | 1 | 16 | Fuel | From Racetrac | 99.63 | 0 | 99.63 |  |  |  | Gas/Oil/Travel | Racetrac | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-535
2025-12-30 | 1 | 16 | Fuel | From Racetrac | 94.54 | 0 | 94.54 |  |  |  | Gas/Oil/Travel | Racetrac | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-536
Various | 1 | 16 | Fuel | From QT | 184.66 | 0 | 184.66 |  |  |  | Gas/Oil/Travel | QT | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-537
Various | 1 | 16 | Meals & Fuel | For Jobsite Travel | 162.59 | 0 | 162.59 |  |  |  | Gas/Oil/Travel | Various | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-538
2025-12-11 | 1 | 16 | Fuel | From Circle K | 91.62 | 0 | 91.62 |  |  |  | Gas/Oil/Travel | Circle K | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-01-539
Various | 1 | 16 | Misc. Wire and ACH Fees for RIW | From Austin Bank for Wires and ACH | 153.6 | 0 | 153.6 |  |  |  | Plan Reproduction/Postage | Austin Bank | RI Waxahachie | NA | NA | Bank Fees | RIW-CFR-01-540
[To Be Paid] | 1 | 16 | Job Supervisor | For January 2026 | 10000 | 0 | 10000 |  |  |  | Superintendent | Boulder Construction | [To Be Paid] | NA | NA | [To Be Paid] | RIW-CFR-01-541
2026-02-05 | 1 | 17 | Jobsite Office - Recurring Rental | From Willscott | 160.4 | 0 | 160.4 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 12205 | NA | Credit Card
2026-02-11 | 1 | 17 | Misc. Jobsite Material Expenses | From Home Depot - Mount Starter Kit with Ball and Lock | 72.47 | 0 | 72.47 |  |  |  | Jobsite Material Expenses | Home Depot | Boulder AMEX | 12212 | NA | Credit Card
2026-02-18 | 1 | 17 | Misc. Jobsite Material Expenses | From Home Depot - Bottled Water And Utility Knife, Blades | 60.9 | 0 | 60.9 |  |  |  | Jobsite Material Expenses | Home Depot | Boulder AMEX | 12221 | NA | Credit Card
2026-02-16 | 1 | 17 | Final Cleaning Supplies | From Home Depot - Jobsite Cleaning SuppliesCleaning Wipes and Cleaners | 104.83 | 0 | 104.83 |  |  |  | Jobsite Material Expenses | Home Depot | Boulder AMEX | 12248 | NA | Credit Card
2026-02-13 | 1 | 17 | Temporary Toilets - Recurring Payment | A-1 Little John | 954.77 | 0 | 954.77 |  |  |  | Container Storage Rental | A-1 Little John | Boulder AMEX | 12258 | NA | Credit Card
2026-02-12 | 1 | 17 | Jobsite Dumpster | From Advantage Waste Disposal | 1449.48 | 0 | 1449.48 |  |  |  | Waste Removal Services | Advantage Waste Disposal | Boulder AMEX | 12260 | NA | Credit Card
2026-02-11 | 1 | 17 | Jobsite Office - Recurring Rental | From Willscott | 677.87 | 0 | 677.87 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 12269 | NA | Credit Card
2026-02-11 | 1 | 17 | Jobsite Office - Recurring Rental | From Willscott | 136.31 | 0 | 136.31 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 12270 | NA | Credit Card
2026-02-11 | 1 | 17 | Jobsite Office - Recurring Rental | From Willscott | 420.28 | 0 | 420.28 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 12271 | NA | Credit Card
2026-02-03 | 1 | 17 | Jobsite Dumpster | From Waste Connections | 2105.22 | 0 | 2105.22 |  |  |  | Waste Removal Services | Waste Connections | Boulder AMEX | 12274 | NA | Credit Card
2026-02-12 | 1 | 17 | Jobsite Dumpster | From Waste Connections | 1613.43 | 0 | 1613.43 |  |  |  | Waste Removal Services | Waste Connections | Boulder AMEX | 12275 | NA | Credit Card
2026-02-09 | 1 | 17 | Jobsite Office - Recurring Rental | From Willscott | 24.09 | 0 | 24.09 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 12286 | NA | Credit Card
2026-01-29 | 1 | 17 | Jobsite Office - Recurring Rental | From Willscott | 214.06 | 0 | 214.06 |  |  |  | Container Storage Rental | Willscot | Boulder AMEX | 12307 | NA | Credit Card
2026-02-24 | 1 | 17 | Misc. Jobsite Material Expenses | From Home Depot | 87.35 | 0 | 87.35 |  |  |  | Jobsite Material Expenses | Home Depot | Boulder AMEX | 12356 | NA | Credit Card
2026-02-11 | 1 | 17 | Misc. Jobsite Material Expenses | From Home Depot | 1 | 0 | 1 |  |  |  | Jobsite Material Expenses | Home Depot | Boulder AMEX | 12358 | NA | Credit Card
2026-02-23 | 1 | 17 | Jobsite Dumpster | From Waste Connections | 1613.43 | 0 | 1613.43 |  |  |  | Waste Removal Services | Waste Connections | Boulder AMEX | 12461 | NA | Credit Card
2026-02-24 | 1 | 17 | Jobsite Dumpster | From Advantage Waste Disposal | 1449.48 | 0 | 1449.48 |  |  |  | Waste Removal Services | Advantage Waste Disposal | Boulder AMEX | 12492 | NA | Credit Card
2026-02-05 | 1 | 17 | Notary Fees | For Draw | 13.46 | 0 | 13.46 |  |  |  | Plan Reproduction/Postage | The UPS Store | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-23 | 1 | 17 | Jobsite Dumpster | From Waste Connections | -491.79 | 0 | -491.79 |  |  |  | Waste Removal Services | Waste Connections | Boulder AMEX | [TBD] | NA | Credit Card
2025-10-14 | 1 | 17 | Jobsite Material Refund | From Home Depot - Refund | -11.08 | 0 | -11.08 |  |  |  | Jobsite Material Expenses | Home Depot | Jaimin AMEX | [TBD] | NA | Credit Card
2026-02-05 | 1 | 17 | Jobsite Material Refund | From Home Depot - Refund | -57.68 | 0 | -57.68 |  |  |  | Jobsite Material Expenses | Home Depot | Jaimin AMEX | [TBD] | NA | Credit Card
2026-02-05 | 1 | 17 | Jobsite Material Refund | From Home Depot - Refund | -855.97 | 0 | -855.97 |  |  |  | Jobsite Material Expenses | Home Depot | Jaimin AMEX | [TBD] | NA | Credit Card
2026-02-11 | 1 | 17 | Notary Fees | For Draw | 25 | 0 | 25 |  |  |  | Plan Reproduction/Postage | One9 | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-05 | 1 | 17 | Notary Fees | For Draw | 25 | 0 | 25 |  |  |  | Plan Reproduction/Postage | Notarize | Boulder AMEX | [TBD] | NA | Credit Card
2026-01-27 | 1 | 17 | Travel for Labor During Ice Storm | From Lyft | 66.95 | 0 | 66.95 |  |  |  | Gas/Oil/Travel | Lyft | Boulder AMEX | [TBD] | NA | Credit Card
2026-01-27 | 1 | 17 | Travel for Labor During Ice Storm | From Lyft | 44.94 | 0 | 44.94 |  |  |  | Gas/Oil/Travel | Lyft | Boulder AMEX | [TBD] | NA | Credit Card
2026-01-28 | 1 | 17 | Travel for Labor During Ice Storm | From Lyft | 46.96 | 0 | 46.96 |  |  |  | Gas/Oil/Travel | Lyft | Boulder AMEX | [TBD] | NA | Credit Card
2026-01-29 | 1 | 17 | Travel for Labor During Ice Storm | From Lyft | 63.93 | 0 | 63.93 |  |  |  | Gas/Oil/Travel | Lyft | Boulder AMEX | [TBD] | NA | Credit Card
2026-01-29 | 1 | 17 | Travel for Labor During Ice Storm | From Lyft | 49.93 | 0 | 49.93 |  |  |  | Gas/Oil/Travel | Lyft | Boulder AMEX | [TBD] | NA | Credit Card
2026-01-29 | 1 | 17 | Travel for Labor During Ice Storm | From Lyft | 47.98 | 0 | 47.98 |  |  |  | Gas/Oil/Travel | Lyft | Boulder AMEX | [TBD] | NA | Credit Card
2026-01-23 | 1 | 17 | Booking for Security/Labor During Ice Storm | From Expedia | 571.56 | 0 | 571.56 |  |  |  | Gas/Oil/Travel | Expedia | Boulder AMEX | [TBD] | NA | Credit Card
2026-01-26 | 1 | 17 | Booking for Security/Labor During Ice Storm | From Expedia | 179.67 | 0 | 179.67 |  |  |  | Gas/Oil/Travel | Expedia | Boulder AMEX | [TBD] | NA | Credit Card
2026-01-27 | 1 | 17 | Booking for Security/Labor During Ice Storm | From Expedia | 213.57 | 0 | 213.57 |  |  |  | Gas/Oil/Travel | Expedia | Boulder AMEX | [TBD] | NA | Credit Card
2026-01-29 | 1 | 17 | Booking for Security/Labor During Ice Storm | From Expedia | 161.76 | 0 | 161.76 |  |  |  | Gas/Oil/Travel | Expedia | Boulder AMEX | [TBD] | NA | Credit Card
Various | 1 | 17 | Meals | For Jobsite Travel | 491.43 | 0 | 491.43 |  |  |  | Gas/Oil/Travel | Various | Boulder AMEX | [TBD] | NA | Credit Card
Various | 1 | 17 | Fuel | For Jobsite | 711.24 | 0 | 711.24 |  |  |  | Gas/Oil/Travel | Various | Boulder AMEX | [TBD] | NA | Credit Card
2026-01-06 | 1 | 17 | Notary Fees | For Draw | 10 | 0 | 10 |  |  |  | Plan Reproduction/Postage | The UPS Store | Boulder AMEX | [TBD] | NA | Credit Card
2026-01-29 | 1 | 17 | David Salinas - Jobsite Labor | From Waltons Muffler | 1844.35 | 0 | 1844.35 |  |  |  | Jobsite Labor | Waltons Muffler | Boulder AMEX | [TBD] | NA | Credit Card
Various | 1 | 17 | Misc. Wire and ACH Fees for RIW | From Austin Bank for Wires and ACH | 130.3 | 0 | 130.3 |  |  |  | Plan Reproduction/Postage | Austin Bank | RI Waxahachie | [TBD] | NA | Bank Fees
Various | 1 | 17 | Misc. Jobsite Expenses (Softwares, etc.) - True Up | Takeoffs, Scheduling / Forecasting, Punch Lists, etc. | 1202.23 | 0 | 1202.23 |  |  |  | Jobsite Office Rental | Various | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-27 | 1 | 17 | Cellular Data & WiFi for Jobsite Office | From Google One | 269.04 | 0 | 269.04 |  |  |  | Jobsite Office Rental | Google One | Boulder AMEX | [TBD] | NA | Credit Card
Various | 1 | 17 | Cellular Data & WiFi for Jobsite Office - True Up | From AT&T | 303.81 | 0 | 303.81 |  |  |  | Jobsite Office Rental | AT&T | Boulder AMEX | [TBD] | NA | Credit Card
[To Be Paid] | 1 | 17 | Job Supervisor | For February 2026 | 10000 | 0 | 10000 |  |  |  | Superintendent | Boulder Construction | [To Be Paid] | NA | NA | [To Be Paid] | RIW-CFR-01-541
2. Sitework
| 2 | 1 | Water Meter Payment | Reimbursement for Payment to the City of Waxahachie |  |  |  | 2233 | 0 | 2233
| 2 | 1 | Temporary Fencing (Dirt Screening for Sitework) | Reimbursement for Payment to Viking Fence Co |  |  |  | 4830.6658 | 0 | 4830.6658
| 2 | 1 | Earthwork - SW3P / Site Clearing | Reimbursement for Payment to Raul Sandoval Construction |  |  |  | 10000 | 1000 | 9000
| 2 | 1 | Earthwork - Mobilization | Reimbursement for Payment to Raul Sandoval Construction |  |  |  | 12000 | 1200 | 10800
| 2 | 1 | Utility - Sanitary Sewer & Water Material | Reimbursement for Payment to Ferguson Waterworks |  |  |  | 81563.63 | 0 | 81563.63
| 2 | 1 | Earthwork - SW3P | Reimbursement for Payment to Cardinal Strategies |  |  |  | 1100 | 0 | 1100
| 2 | 1 | Sitework - Surveyor | AIM Construction Services |  |  |  | 1140 | 0 | 1140
| 2 | 1 | Earthwork - Import Dirt Material | Superman Trucking and Delivery Inc |  |  |  | 3500 | 0 | 3500
| 2 | 1 | Earthwork - Import Dirt Material | Superman Trucking and Delivery Inc |  |  |  | 20995 | 0 | 20995
| 2 | 1 | Order Storm Sewer Material | Ferguson Waterworks |  |  |  | 35700 | 0 | 35700
| 2 | 1 | Earthwork - Import Dirt & Gravel Material | Trucking and Material |  |  |  | 35000 | 0 | 35000
| 2 | 1 | Sitework - Earthwork | Raul Sandoval Construction - August 2024 Forecasted Payments |  |  |  | 58000 | 5800 | 52200
| 2 | 1 | Sitework - Utilities | Raul Sandoval Construction - August 2024 Forecasted Payments |  |  |  | 50000 | 5000 | 45000
| 2 | 1 | Sitework - Equipment | Equipment Share - August 2024 Forecasted Cost |  |  |  | 25000 | 0 | 25000
| 2 | 2 | Sitework - Forecast | Site Utilities + Paving + Remaining Dirt Work |  |  |  | 211391.1 | 0 | 211391.1
| 2 | 6 | Equipment Rental + Purchase of Safety Platforms | EquipmentShare |  |  |  | 8660.01 | 0 | 8660.01
| 2 | 7 | Draw 7 Funds - Reimbursements |  |  |  |  | 46407.513 | 0 | 46407.513
| 2 | 7 | Draw 7 Funds - To Be Paid |  |  |  |  | 14971.34 | 0 | 14971.34
| 2 | 8 | Draw 8 Funds - Reimbursements |  |  |  |  | 15541.24 | 0 | 15541.24
| 2 | 8 | Draw 8 Funds - To Be Paid |  |  |  |  | 14252.69 | 0 | 14252.69
| 2 | 9 | Draw 9 Funds - Reimbursements |  |  |  |  | 1353.85 | 0 | 1353.85
| 2 | 9 | Draw 9 Funds - To Be Paid |  |  |  |  | 8910.79 | 0 | 8910.79
| 2 | 10 | Draw 10 Funds - Reimbursements |  |  |  |  | 375 | 0 | 375
| 2 | 10 | Draw 10 Funds - To Be Paid |  |  |  |  | 10962.19 | 0 | 10962.19
| 2 | 11 | Draw 11 Funds - Reimbursements |  |  |  |  | 822.9 | 0 | 822.9
| 2 | 11 | Draw 11 Funds - To Be Paid |  |  |  |  | 9030.42 | 0 | 9030.42
| 2 | 12 | Draw 12 Funds - Reimbursements |  |  |  |  | 2156.31 | 0 | 2156.31
| 2 | 12 | Draw 12 Funds - To Be Paid |  |  |  |  | 8886.04 | 0 | 8886.04
| 2 | 13 | Draw 13 Funds - Reimbursements |  |  |  |  | 1064 | 0 | 1064
| 2 | 13 | Draw 13 Funds - To Be Paid |  |  |  |  | 17889.34 | 0 | 17889.34
| 2 | 14 | Draw 14 Funds - Reimbursements |  |  |  |  | 3619.56 | 0 | 3619.56
| 2 | 14 | Draw 14 Funds - To Be Paid |  |  |  |  | 10182.47 | 0 | 10182.47
| 2 | 15 | Draw 15 Funds - Reimbursements |  |  |  |  | 4755.27 | 347.75 | 4407.52
| 2 | 16 | Draw 16 Funds - Reimbursements |  |  |  |  | 153705.68 | 0 | 153705.68
2024-08-02 | 2 | 1 | Water Meter Payment | The City of Waxahachie | 2233 | 0 | 2233 |  |  |  | Earthwork | City of Waxahachie | Rush | 10024 | NA | Credit Card | RIW-CFR-02-001
2024-08-07 | 2 | 1 | Temporary Fencing (Dirt Screening for Sitework) | Viking Fence Co | 4830.6658 | 0 | 4830.6658 |  |  |  | Earthwork | Viking Fence | Jai | 10004 | NA | Credit Card | RIW-CFR-02-002
2024-08-07 | 2 | 1 | Earthwork - SW3P / Site Clearing | Raul Sandoval Construction | 10000 | 1000 | 9000 |  |  |  | Earthwork | Raul Sandoval Construction | Boulder | 10025 | Yes | Check | RIW-CFR-02-003
2024-07-31 | 2 | 1 | Earthwork - Mobilization | Raul Sandoval Construction | 12000 | 1200 | 10800 |  |  |  | Earthwork | Raul Sandoval Construction | Boulder | 10023 | Yes | Check | RIW-CFR-02-004
2024-08-09 | 2 | 1 | Utility - Sanitary Sewer & Water Material | Ferguson Waterworks | 81563.62 | 0 | 81563.62 |  |  |  | Utilities | Ferguson Waterworks | Jaimin Uncle | 10026 | NA | Credit Card | RIW-CFR-02-005
2024-07-11 | 2 | 1 | Earthwork - SW3P | Cardinal Strategies | 1100 | 0 | 1100 |  |  |  | Earthwork | Cardinal Strategies | Rush | 10021 | NA | Credit Card | RIW-CFR-02-006
2024-09-04 | 2 | 1 | Earthwork - Surveyor | AIM Construction Services | 1140 | 0 | 1140 |  |  |  | Earthwork | AIM Construction Services | Rush | 10022 | NA | Credit Card | RIW-CFR-02-007
2024-09-13 | 2 | 1 | Earthwork - Import Dirt Material | Superman Trucking and Delivery Inc | 3500 | 0 | 3500 |  |  |  | Earthwork | Superman Trucking | Boulder | 10029 | NA | Check | RIW-CFR-02-008
2024-09-13 | 2 | 1 | Earthwork - Import Dirt Material | Superman Trucking and Delivery Inc | 20995 | 0 | 20995 |  |  |  | Earthwork | Superman Trucking | Boulder | 10030 | NA | Check | RIW-CFR-02-009
2024-09-13 | 2 | 1/2 | Earthwork - Construction Entrance Material | Superman Trucking and Delivery Inc | 2790 | 0 | 2790 |  |  |  | Earthwork | Superman Trucking | Boulder | 10031 | NA | Check | RIW-CFR-02-010
2024-09-13 | 2 | 1/2 | Utility - Gravel Material for Trench | Superman Trucking and Delivery Inc | 3735 | 0 | 3735 |  |  |  | Utilities | Superman Trucking | Boulder | 10032 | NA | Check | RIW-CFR-02-011
2024-09-13 | 2 | 1/2 | Utility - Gravel Material for Trench | Superman Trucking and Delivery Inc | 4980 | 0 | 4980 |  |  |  | Utilities | Superman Trucking | Boulder | 10031 | NA | Check | RIW-CFR-02-012
2024-08-20 | 2 | 1 | Earthwork - Dirt Work | Raul Sandoval Construction (Final Payment) | 7637.5 | 763.75 | 6873.75 |  |  |  | Earthwork | Raul Sandoval Construction | Boulder | 10033 | Yes | Check | RIW-CFR-02-013
2024-08-15 | 2 | 1/2 | Water Meter Payment | The City of Waxahachie | 2233 | 0 | 2233 |  |  |  | Earthwork | City of Waxahachie | Rush |  | NA | Credit Card | RIW-CFR-02-014
2024-08-24 | 2 | 1/2 | Earthwork - Labor | Boulder Construction | 1645 | 0 | 1645 |  |  |  | Earthwork | Boulder Construction | Boulder | 10034 | Yes | Credit Card | RIW-CFR-02-015
2024-08-24 | 2 | 1/2 | Earthwork - Diesel for Equipment | Boulder Construction | 1500 | 0 | 1500 |  |  |  | Earthwork | Boulder Construction | Boulder | 10036 | Yes | Check | RIW-CFR-02-016
2024-08-24 | 2 | 1/2 | Earthwork - Labor | Boulder Construction | 1645 | 0 | 1645 |  |  |  | Earthwork | Boulder Construction | Boulder | 10035 | Yes | Check | RIW-CFR-02-017
2024-08-29 | 2 | 1/2 | Earthwork - Diesel for Equipment | Boulder Construction | 1500 | 0 | 1500 |  |  |  | Earthwork | Boulder Construction | Boulder | 10037 | Yes | Check | RIW-CFR-02-018
2024-08-31 | 2 | 1/2 | Earthwork - Labor | Boulder Construction | 7800 | 0 | 7800 |  |  |  | Earthwork | Boulder Construction | Boulder | 10038 | Yes | Check | RIW-CFR-02-019
2024-09-09 | 2 | 1/2 | Earthwork - Diesel for Equipment | Boulder Construction | 1500 | 0 | 1500 |  |  |  | Earthwork | Boulder Construction | Boulder | 10039 | Yes | Check | RIW-CFR-02-020
2024-09-12 | 2 | 1/2 | Earthwork - Dirt Haul Off | Ricardo Cardena | 80 | 0 | 80 |  |  |  | Earthwork | Ricardo Cardena | Boulder | 10040 | NA |  | RIW-CFR-02-021
2024-09-12 | 2 | 1/2 | Earthwork - Dirt Haul Off | Aneudy Marte | 80 | 0 | 80 |  |  |  | Earthwork | Aneudy Marte | Boulder | 10041 | NA |  | RIW-CFR-02-022
2024-09-12 | 2 | 1/2 | Earthwork - Dirt Haul Off | Aneudy Marte | 80 | 0 | 80 |  |  |  | Earthwork | Aneudy Marte | Boulder | 10042 | NA |  | RIW-CFR-02-023
2024-09-14 | 2 | 1/2 | Earthwork - Dirt Haul Off | Ricardo Cardena | 480 | 0 | 480 |  |  |  | Earthwork | Ricardo Cardena | Boulder | 10043 | NA |  | RIW-CFR-02-024
2024-09-23 | 2 | 1/2 | Earthwork - Labor | Boulder Construction | 655 | 0 | 655 |  |  |  | Earthwork | Boulder Construction | Boulder | 10044 | Yes | Check | RIW-CFR-02-025
2024-09-06 | 2 | 1/2 | Earthwork - Labor | Boulder Construction | 5460 | 0 | 5460 |  |  |  | Earthwork | Boulder Construction | RI Waxahachie | 10045 | Yes | Wire Transfer | RIW-CFR-02-026
2024-09-13 | 2 | 1/2 | Earthwork - Labor | Boulder Construction | 6734 | 0 | 6734 |  |  |  | Earthwork | Boulder Construction | RI Waxahachie | 10046 | Yes | Wire Transfer | RIW-CFR-02-027
2024-09-13 | 2 | 1/2 | Earthwork - Import Dirt Material | Alliance Trucking | 31660 | 0 | 31660 |  |  |  | Earthwork | Alliance Trucking | Boulder | 10049 | NA |  | RIW-CFR-02-028
2024-10-08 | 2 | 1/2 | Earthwork - Import Dirt Material | Alliance Trucking | 34460 | 0 | 34460 |  |  |  | Earthwork | Alliance Trucking | RI Waxahachie | 10050 | NA |  | RIW-CFR-02-029
Various | 2 | 1/2 | Earthwork - Misc. Wire Fees | From Austin Bank for Wires | 90 | 0 | 90 |  |  |  | Earthwork | Austin Bank | RI Waxahachie |  | NA |  | RIW-CFR-02-030
2024-09-14 | 2 | 1/2 | Earthwork - Testing | Geoscience Engineers | 3675 | 0 | 3675 |  |  |  | Earthwork | Geoscience Engineers | Jai | 10048 | NA |  | RIW-CFR-02-031
2024-08-24 | 2 | 1/2 | [Amazon Payment - Need Receipt] |  | 60.52 | 0 | 60.52 |  |  |  | Earthwork | Amazon | Jai |  | NA |  | RIW-CFR-02-032
2024-08-21 | 2 | 1/2 | Water/Fire Hoses | Midwest Hose in Dallas | 522.41 | 0 | 522.41 |  |  |  | Earthwork | Midwest Hose | Rush |  | NA |  | RIW-CFR-02-033
2024-08-23 | 2 | 1/2 | Water/Fire Hoses | Midwest Hose in Dallas | 1693.51 | 0 | 1693.51 |  |  |  | Earthwork | Midwest Hose | Rush |  | NA |  | RIW-CFR-02-034
2024-08-30 | 2 | 1/2 | Meal for Moisture Conditioning Crew | PizzaHut | 125.69 | 0 | 125.69 |  |  |  | Earthwork | PizzaHut | Rush |  | NA |  | RIW-CFR-02-035
| 2 | 1/2 | Utility - Sanitary Sewer & Water Material | Fortiline Waterworks | 37837.05 | 0 | 37837.05 |  |  |  | Utilities | Fortiline Waterworks | Jaimin Uncle | 10026 | NA |  | RIW-CFR-02-036
2024-08-30 | 2 | 1 | Utility - Sanitary Sewer Labor | MA Williams Plumbing | 20000 | 2000 | 18000 |  |  |  | Utilities | MA Williams Plumbing | Boulder | 10027 | Yes | Check | RIW-CFR-02-037
2024-08-30 | 2 | 1/2 | Utility - Sanitary Sewer Material | MA Williams Plumbing | 350 | 0 | 350 |  |  |  | Utilities | MA Williams Plumbing | Boulder | 10027 | Yes | Check | RIW-CFR-02-038
2024-09-04 | 2 | 1/2 | Utility - Additional Material | Fortiline Waterworks | 2363.23 | 0 | 2363.23 |  |  |  | Utilities | Fortiline Waterworks | Rush |  | NA |  | RIW-CFR-02-039
2024-09-05 | 2 | 1/2 | Earthwork - Surveyor | AIM Construction Services | 900 | 0 | 900 |  |  |  | Earthwork | AIM Construction Services | Rush | 10047 | NA |  | RIW-CFR-02-040
2024-09-30 | 2 | 1/2 | Earthwork - Surveyor | AIM Construction Services | 1280 | 0 | 1280 |  |  |  | Earthwork | AIM Construction Services | Rush | 10028 | NA |  | RIW-CFR-02-041
2024-09-30 | 2 | 1/2 | Earthwork - Surveyor | AIM Construction Services | 962.52 | 0 | 962.52 |  |  |  | Earthwork | AIM Construction Services | Rush | 10112 | NA |  | RIW-CFR-02-042
2024-08-16 | 2 | 1/2 | Utilities - Misc. Material | From Home Depot | 134.55 | 0 | 134.55 |  |  |  | Utilities | Home Depot | Rush |  | NA |  | RIW-CFR-02-043
2024-08-23 | 2 | 1/2 | Utilities - Misc. Material | From Home Depot | 29.2 | 0 | 29.2 |  |  |  | Utilities | Home Depot | Rush |  | NA |  | RIW-CFR-02-044
2024-08-23 | 2 | 1/2 | Utilities - Misc. Material | From Home Depot | 215.02 | 0 | 215.02 |  |  |  | Utilities | Home Depot | Rush |  | NA |  | RIW-CFR-02-045
2024-09-04 | 2 | 1/2 | Utilities - Misc. Material | From Home Depot | 271.66 | 0 | 271.66 |  |  |  | Utilities | Home Depot | Rush |  | NA |  | RIW-CFR-02-046
2024-07-09 | 2 | 1/2 | Earthwork - Engineering | From Lev Engineering | 600 | 0 | 600 |  |  |  | Earthwork | Lev Engineering | Rush |  | NA |  | RIW-CFR-02-047
2024-10-30 | 2 | 1/2 | Equipment Allocation - Earthwork | EquipmentShare | 58967.392 | 0 | 58967.392 |  |  |  | Earthwork | EquipmentShare | Jaimin Uncle | 10062 | NA |  | RIW-CFR-02-048
2024-10-30 | 2 | 1/2 | Equipment Allocation - Utilities | EquipmentShare | 14741.848 | 0 | 14741.848 |  |  |  | Utilities | EquipmentShare | Jaimin Uncle | 10062 | NA |  | RIW-CFR-02-049
2024-11-26 | 2 | 1 | Utilities - Labor | MA Williams Plumbing | 20000 | 2000 | 18000 |  |  |  | Utilities | MA Williams Plumbing | RI Waxahachie | 10146 | Yes | Check | RIW-CFR-02-050
2024-11-26 | 2 | 1/2 | Utilities - Diesel and Material | Mark Williams | 371.36 | 0 | 371.36 |  |  |  | Utilities | Mark Williams | RI Waxahachie | 10147 | Yes | Check | RIW-CFR-02-051
2024-11-26 | 2 | 1/2 | Earthwork - SW3P | Cardinal Strategies | 750 | 0 | 750 |  |  |  | Earthwork | Cardinal Strategies | RI Waxahachie | 10087 | NA |  | RIW-CFR-02-052
2024-11-20 | 2 | 1/2 | Import Common Fill Material | Alliance Trucking - Partial Allocation | 1039.8 | 0 | 1039.8 |  |  |  | Earthwork | Alliance Trucking | RI Waxahachie | 10100 | NA |  | RIW-CFR-02-053
2024-11-20 | 2 | 1/2 | Import Cushion Sand Material | Alliance Trucking - Partial Allocation | 7380 | 0 | 7380 |  |  |  | Utilities | Alliance Trucking | RI Waxahachie | 10101 | NA |  | RIW-CFR-02-054
2024-11-26 | 2 | 1/2 | Import Select Fill Material | Superman Trucking and Delivery Inc | 1600 | 0 | 1600 |  |  |  | Earthwork | Superman Trucking | RI Waxahachie | 10102 | NA | Check | RIW-CFR-02-055
2024-11-26 | 2 | 1/2 | Import Limestone and Crushed Rock Material | Superman Trucking and Delivery Inc | 7470 | 0 | 7470 |  |  |  | Utilities | Superman Trucking | RI Waxahachie | 10103 | NA | Check | RIW-CFR-02-056
2024-11-27 | 2 | 1/2 | Water Meter Usage | City of Waxahachie | 1779.333 | 0 | 1779.333 |  |  |  | Earthwork | City of Waxahachie | Boulder AMEX | 10097 | NA |  | RIW-CFR-02-057
2024-11-21 | 2 | 1/2 | Earthwork - Testing | Geoscience Engineers | 5578.3 | 0 | 5578.3 |  |  |  | Earthwork | Geoscience Engineers | Boulder AMEX | 10057 | NA |  | RIW-CFR-02-058
2024-11-12 | 2 | 1/2 | Signage for Temporary Fence | Project Information / Overview Signage | 185.08 | 0 | 185.08 |  |  |  | Earthwork | Alibaba | Boulder AMEX | 10156 | NA |  | RIW-CFR-02-059
2024-11-11 | 2 | 1/2 | Utility and Paving Surveying/Staking | AIM Construction Services | 1810 | 0 | 1810 |  |  |  | Utilities | AIM Construction Services | Boulder AMEX | 10110 | NA |  | RIW-CFR-02-060
2024-12-04 | 2 | 1/2 | Earthwork - Testing | Geoscience Engineers | 4873 | 0 | 4873 |  |  |  | Earthwork | Geoscience Engineers | Boulder AMEX | 10058 | NA |  | RIW-CFR-02-061
2024-11-11 | 2 | 1/2 | Utilities - Crane for Lifting Vaults in Place | From Blue's Crane Service | 4150 | 0 | 4150 |  |  |  | Utilities | Blue's Crane Service | Rush |  | NA |  | RIW-CFR-02-062
2024-10-23 | 2 | 1/2 | Utilities - Surveyor | AIM Construction Services | 700 | 0 | 700 |  |  |  | Utilities | AIM Construction Services | Jai | 10105 | NA |  | RIW-CFR-02-063
2024-10-23 | 2 | 1/2 | Earthwork - Surveyor | AIM Construction Services | 1420 | 0 | 1420 |  |  |  | Earthwork | AIM Construction Services | Jai | 10106 | NA |  | RIW-CFR-02-064
2024-10-23 | 2 | 1/2 | Earthwork - Surveyor | AIM Construction Services | 1500 | 0 | 1500 |  |  |  | Earthwork | AIM Construction Services | Jai | 10107 | NA |  | RIW-CFR-02-065
2024-10-23 | 2 | 1/2 | Earthwork - Surveyor | AIM Construction Services | 2690 | 0 | 2690 |  |  |  | Earthwork | AIM Construction Services | Jai | 10108 | NA |  | RIW-CFR-02-066
2024-10-23 | 2 | 1/2 | Flow Test for Fire Hydrant | Fire Hydrant Servicing | 535 | 0 | 535 |  |  |  | Utilities | Fire Hydrant Servicing | Jai | 10061 | NA |  | RIW-CFR-02-067
2024-12-02 | 2 | 1/2 | Utilities - Surveyor | AIM Construction Services | 1600 | 0 | 1600 |  |  |  | Utilities | AIM Construction Services | Boulder AMEX | 10109 | NA |  | RIW-CFR-02-068
2024-11-21 | 2 | 1/2 | Misc. Jobsite Materials | From Home Depot | 260.02 | 0 | 260.02 |  |  |  | Utilities | Home Depot | Boulder AMEX | 10092 | NA |  | RIW-CFR-02-069
2025-01-12 | 2 | 1/2 | Utilities - Equipment | EquipmentShare | 25416.13 | 0 | 25416.13 |  |  |  | Utilities | EquipmentShare | RI Waxahachie | 10157 | NA |  | RIW-CFR-02-070
2024-12-13 | 2 | 1/2 | Utilities - Surveyor | AIM Construction Services | 700 | 0 | 700 |  |  |  | Utilities | AIM Construction Services | Boulder AMEX | 10165 | NA |  | RIW-CFR-02-071
2024-12-10 | 2 | 1/2 | Water Meter Usage | City of Waxahachie | 1236.37 | 0 | 1236.37 |  |  |  | Earthwork | City of Waxahachie | Boulder AMEX | 10209 | NA |  | RIW-CFR-02-072
2025-01-10 | 2 | 2/7 | Water Meter Usage | City of Waxahachie | 451 | 0 | 451 |  |  |  | Earthwork | City of Waxahachie | Boulder AMEX | 10210 | NA |  | RIW-CFR-02-073
2025-01-10 | 2 | 7 | Water Meter Usage | City of Waxahachie | 771.09 | 0 | 771.09 |  |  |  | Earthwork | City of Waxahachie | Boulder AMEX | 10210 | NA |  | RIW-CFR-02-074
2025-01-27 | 2 | 7 | Import Washed Rock | Superman Trucking and Delivery Inc | 2490 | 0 | 2490 |  |  |  | Utilities | Superman Trucking | RI Waxahachie | 10213 | NA | Check | RIW-CFR-02-075
2025-01-27 | 2 | 7 | Import Washed Rock | Superman Trucking and Delivery Inc | 1245 | 0 | 1245 |  |  |  | Utilities | Superman Trucking | RI Waxahachie | 10214 | NA | Check | RIW-CFR-02-076
2025-01-27 | 2 | 7 | Import Washed Rock | Superman Trucking and Delivery Inc | 1245 | 0 | 1245 |  |  |  | Utilities | Superman Trucking | RI Waxahachie | 10215 | NA | Check | RIW-CFR-02-077
2025-01-13 | 2 | 7 | Traffic Control Plan | For Utility Tie-In | 162.38 | 0 | 162.38 |  |  |  | Utilities | Buyers Barricades | Boulder AMEX | 10240 | NA | Credit Card | RIW-CFR-02-078
2025-01-21 | 2 | 7 | Utilities - Misc. Material | From Home Depot - Hose and Pump for Drainage | 214.77 | 0 | 214.77 |  |  |  | Utilities | Home Depot | Boulder AMEX | 10257 | NA | Credit Card | RIW-CFR-02-079
2025-03-04 | 2 | 7 | Earthwork - Misc. Material | From Home Depot - Zip Ties | 47.93 | 0 | 47.93 |  |  |  | Earthwork | Home Depot | Boulder AMEX | 10276 | NA | Credit Card | RIW-CFR-02-080
2025-03-05 | 2 | 7 | Earthwork - Misc. Material | From Home Depot - Zip Ties and Silt Fence | 259.12 | 0 | 259.12 |  |  |  | Earthwork | Home Depot | Boulder AMEX | 10277 | NA | Credit Card | RIW-CFR-02-081
2025-02-18 | 2 | 7 | Earthwork - Testing | Geoscience Engineers | 3219 | 0 | 3219 |  |  |  | Earthwork | Geoscience Engineers | Owner (JP) AMEX | 10287 | NA | Credit Card | RIW-CFR-02-082
2025-02-20 | 2 | 7 | Utilities - Additional Material | From Moore Supply - Allocated Payment (Excl. Plumbing Allocation) | 11829.93 | 0 | 11829.93 |  |  |  | Utilities | Moore Supply | Owner (JP) AMEX | 10288 | NA | Credit Card | RIW-CFR-02-083
2025-02-13 | 2 | 1 | Earthwork - Excavation and Grading | From M D Bowles Construction | 6000 | 600 | 5400 |  |  |  | Earthwork | M D Bowles Construction | RI Waxahachie | 10307 | Yes | Check | RIW-CFR-02-084
2025-01-28 | 2 | 7 | Earthwork - SW3P | Cardinal Strategies | 1125 | 0 | 1125 |  |  |  | Earthwork | Cardinal Strategies | RI Waxahachie | 10319 | NA | ACH | RIW-CFR-02-085
[Confirm] | 2 | 6 | Equipment Rental + Purchase of Safety Platforms | EquipmentShare | 8660.01 | 0 | 8660.01 |  |  |  | Equipment Rental | EquipmentShare | [Confirm] | 10335 | NA |  | RIW-CFR-02-086
2025-03-14 | 2 | 7 | Material for Utility Tie In on Rae Blvd | From Britton Meter Supply | 19170.76 | 0 | 19170.76 |  |  |  | Utilities | Britton Meter Supply | Owner (JP) AMEX | 10386 | NA | Credit Card | RIW-CFR-02-087
2025-03-31 | 2 | 7 | Water Meter Usage | City of Waxahachie | 985.24 | 0 | 985.24 |  |  |  | Earthwork | City of Waxahachie | Owner (JP) AMEX | 10389 | NA | Credit Card | RIW-CFR-02-088
2025-03-18 | 2 | 7 | Trench Safety Boxes for Utility Tie In | From National Trench Safety | 2966.4 | 0 | 2966.4 |  |  |  | Utilities | National Trench Safety | Owner (JP) AMEX | 10390 | NA | Credit Card | RIW-CFR-02-089
2025-03-31 | 2 | 7 | Trench Safety Boxes for Utility Tie In | From National Trench Safety | -662.91 | 0 | -662.91 |  |  |  | Utilities | National Trench Safety | Owner (JP) AMEX | 10390 | NA | Credit Card | RIW-CFR-02-090
2025-03-20 | 2 | 7 | Traffic Control Material for the Utility Tie In | From Buyers Barricades | 347.92 | 0 | 347.92 |  |  |  | Utilities | Buyers Barricades | Boulder AMEX | 10391 | NA | Credit Card | RIW-CFR-02-091
2025-03-31 | 2 | 7 | Earthwork - SW3P | Cardinal Strategies | 375 | 0 | 375 |  |  |  | Earthwork | Cardinal Strategies | RI Waxahachie | 10393 | NA | ACH | RIW-CFR-02-092
2025-03-31 | 2 | 7 | Earthwork - SW3P | Cardinal Strategies | 375 | 0 | 375 |  |  |  | Earthwork | Cardinal Strategies | RI Waxahachie | 10394 | NA | ACH | RIW-CFR-02-093
2025-05-02 | 2 | 7 | Equipment Rentals (For Utility) | EquipmentShare | 5536.28 | 0 | 5536.28 |  |  |  | Utilities | EquipmentShare | RI Waxahachie | 10443 | NA | [TBD] | RIW-CFR-02-094
2025-05-02 | 2 | 7 | Equipment Rentals (For General) | EquipmentShare | 9435.06 | 0 | 9435.06 |  |  |  | Equipment Rental | EquipmentShare | RI Waxahachie | 10444 | NA | [TBD] | RIW-CFR-02-095
2025-04-14 | 2 | 8 | Material for Utility Tie In on Rae Blvd | From Britton Meter Supply | 13163.61 | 0 | 13163.61 |  |  |  | Utilities | Britton Meter Supply | Boulder AMEX | 10409 | NA | Credit Card | RIW-CFR-02-096
2025-04-14 | 2 | 8 | Traffic Control Material for the Utility Tie In | From Buyers Barricades | 2002.63 | 0 | 2002.63 |  |  |  | Utilities | Buyers Barricades | Boulder AMEX | 10410 | NA | Credit Card | RIW-CFR-02-097
| 2 | 1 | Utilities - Labor | MA Williams Plumbing | 5555.5556 | 555.5556 | 5000 |  |  |  | Utilities | Mark Williams | MJR | 10447 | No | Check | RIW-CFR-02-098
2025-05-02 | 2 | 1 | Utilities - Labor | MA Williams Plumbing | 14444.4444 | 1444.4444 | 13000 |  |  |  | Utilities | MA Williams Plumbing | RI Waxahachie | 10447 | No | Check | RIW-CFR-02-099
2025-05-02 | 2 | 8 | Earthwork - SW3P | Cardinal Strategies | 375 | 0 | 375 |  |  |  | Earthwork | Cardinal Strategies | Owner (JP) AMEX | 10453 | NA | Credit Card | RIW-CFR-02-100
[To Be Paid] | 2 | 8 | Import Limestone and Cushion Sand Material | Superman Trucking and Delivery Inc | 1710 | 0 | 1710 |  |  |  | Utilities | Superman Trucking | [To Be Paid] |  |  |  | RIW-CFR-02-101
2025-05-27 | 2 | 8 | Equipment Rentals (For Utility) | EquipmentShare - Allocated to General (Due to Budget) | 3625.58 | 0 | 3625.58 |  |  |  | Equipment Rental | EquipmentShare | RI Waxahachie | 10515 | NA |  | RIW-CFR-02-102
2025-05-27 | 2 | 8 | Equipment Rentals (For General) | EquipmentShare | 8917.11 | 0 | 8917.11 |  |  |  | Equipment Rental | EquipmentShare | RI Waxahachie | 10517 | NA |  | RIW-CFR-02-103
2025-05-13 | 2 | 9 | Earthwork - SW3P | Cardinal Strategies | 375 | 0 | 375 |  |  |  | Earthwork | Cardinal Strategies | Owner (JP) AMEX | 10483 | NA | Credit Card | RIW-CFR-02-104
2025-05-21 | 2 | 9 | Water Meter Usage | City of Waxahachie | 978.85 | 0 | 978.85 |  |  |  | Earthwork | City of Waxahachie | Owner (JP) AMEX | 10507 | NA | Credit Card | RIW-CFR-02-105
2025-07-02 | 2 | 9 | Equipment Rentals (For General) | EquipmentShare | 8910.79 | 0 | 8910.79 |  |  |  | Equipment Rental | EquipmentShare | RI Waxahachie | 10524 | NA | Wire | RIW-CFR-02-106
2025-06-25 | 2 | 10 | Earthwork - SW3P | Cardinal Strategies | 375 | 0 | 375 |  |  |  | Earthwork | Cardinal Strategies | Jaimin AMEX | 10590 | NA | Credit Card | RIW-CFR-02-107
2025-07-18 | 2 | 10 | Equipment Rentals (For General) | EquipmentShare | 10962.19 | 0 | 10962.19 |  |  |  | Equipment Rental | EquipmentShare | RI Waxahachie | 10673 | NA | Wire | RIW-CFR-02-108
2025-06-27 | 2 | 11 | Inlet Protection | From White Cap | 255.23 | 0 | 255.23 |  |  |  | Utilities | White Cap | Boulder AMEX | 10628 | NA | Credit Card | RIW-CFR-02-109
2025-07-14 | 2 | 11 | Water Meter Usage | City of Waxahachie | 321.36 | 0 | 321.36 |  |  |  | Earthwork | City of Waxahachie | Jaimin AMEX | 10669 | NA | Credit Card | RIW-CFR-02-110
2025-07-01 | 2 | 11 | Water Meter Usage | City of Waxahachie | 246.31 | 0 | 246.31 |  |  |  | Earthwork | City of Waxahachie | Jaimin AMEX | 10639 | NA | Credit Card | RIW-CFR-02-111
2025-08-18 | 2 | 11 | Equipment Rentals (For General) | EquipmentShare | 9030.42 | 0 | 9030.42 |  |  |  | Equipment Rental | EquipmentShare | RI Waxahachie | 10727 | NA | ACH | RIW-CFR-02-112
2025-08-06 | 2 | 12 | Earthwork - SW3P | Cardinal Strategies | 375 | 0 | 375 |  |  |  | Earthwork | Cardinal Strategies | Jaimin AMEX | 10775 | NA | Credit Card | RIW-CFR-02-113
2025-08-18 | 2 | 12 | Earthwork - SW3P | Cardinal Strategies | 375 | 0 | 375 |  |  |  | Earthwork | Cardinal Strategies | Jaimin AMEX | 10792 | NA | Credit Card | RIW-CFR-02-114
2025-07-25 | 2 | 12 | Water Hose for Water Meter | From Stuart Hose & Pipe | 1243.18 | 0 | 1243.18 |  |  |  | Utilities | Stuart Hose & Pipe | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-02-115
2025-08-11 | 2 | 12 | Inlet Protection | From White Cap | 34.31 | 0 | 34.31 |  |  |  | Utilities | White Cap | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-02-116
2025-08-06 | 2 | 12 | Utilities - Misc. Material | From Home Depot - Plastic Utility Pump | 128.82 | 0 | 128.82 |  |  |  | Utilities | Home Depot | Boulder AMEX | 10786 | NA | Credit Card | RIW-CFR-02-117
2025-09-23 | 2 | 12 | Equipment Rentals (For General) | EquipmentShare | 8886.04 | 0 | 8886.04 |  |  |  | Equipment Rental | EquipmentShare | RI Waxahachie | 10851 | NA | ACH | RIW-CFR-02-118
2025-08-25 | 2 | 13 | Water Meter Usage | From City of Waxahachie | 440.22 | 0 | 440.22 |  |  |  | Earthwork | City of Waxahachie | Jaimin AMEX | 10831 | NA | Credit Card | RIW-CFR-02-119
2025-09-16 | 2 | 13 | Water Meter Usage | From City of Waxahachie | 248.78 | 0 | 248.78 |  |  |  | Earthwork | City of Waxahachie | Jaimin AMEX | 10895 | NA | Credit Card | RIW-CFR-02-120
2025-09-16 | 2 | 13 | Earthwork - SW3P | Cardinal Strategies | 375 | 0 | 375 |  |  |  | Earthwork | Cardinal Strategies | Jaimin AMEX | 10888 | NA | Credit Card | RIW-CFR-02-121
2025-11-07 | 2 | 13 | Equipment Rentals (For General) | EquipmentShare | 11583.68 | 0 | 11583.68 |  |  |  | Equipment Rental | EquipmentShare | RI Waxahachie | 10933 | NA | Direct Pay | RIW-CFR-02-122
2025-11-07 | 2 | 13 | Elevator Generator - Equipment | EquipmentShare | 6305.66 | 0 | 6305.66 |  |  |  | Equipment Rental | EquipmentShare | RI Waxahachie | 10936 | NA | Direct Pay | RIW-CFR-02-123
2025-09-29 | 2 | 14 | Import Dirt Material | From Alliance Trucking | 2340 | 0 | 2340 |  |  |  | Landscaping and Irrigation | Alliance Trucking | RI Waxahachie | 10998 | NA | ACH | RIW-CFR-02-124
2025-10-23 | 2 | 14 | Earthwork - SW3P | Cardinal Strategies | 375 | 0 | 375 |  |  |  | Earthwork | Cardinal Strategies | Jaimin AMEX | 11003 | NA | Credit Card | RIW-CFR-02-125
2025-10-26 | 2 | 14 | Misc. Jobsite Materials | From Home Depot - Coat Welded Wire, Metal T-Post & Clips & Post Driver | 491.1 | 0 | 491.1 |  |  |  | Landscaping and Irrigation | Home Depot | Boulder AMEX | 11033 | NA | Credit Card | RIW-CFR-02-126
2025-10-27 | 2 | 14 | Jobsite Equipment | From Harbor Freight | 413.46 | 0 | 413.46 |  |  |  | Equipment Rental | Harbor Freight | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-02-127
2025-12-09 | 2 | 14 | Equipment Rentals (For General) | From EquipmentShare | 10182.47 | 0 | 10182.47 |  |  |  | Equipment Rental | EquipmentShare | RI Waxahachie | 11057 | NA | Direct Pay | RIW-CFR-02-128
2025-11-11 | 2 | 15 | Earthwork - SW3P | Cardinal Strategies | 375 | 0 | 375 |  |  |  | Earthwork | Cardinal Strategies | Jaimin AMEX | 11062 | NA | Credit Card | RIW-CFR-02-129
2025-12-08 | 2 | 1/15 | Landscaping Deposit | From 4 Nature Landscape | 20839.9556 | 2083.9956 | 18755.96 |  |  |  | Landscaping and Irrigation | 4 Nature Landscape | Jaimin AMEX | 11143 | NA | Credit Card | RIW-CFR-02-130
2025-12-18 | 2 | 15 | Utility Material | From Britton Meter Supply | 902.81 | 0 | 902.81 |  |  |  | Utilities | Britton Meter Supply | Boulder AMEX | 11207 | NA | Credit Card | RIW-CFR-02-131
2025-12-23 | 2 | 15 | Utility Labor | From MA Williams Plumbing - Partial Adjusted in Prior Forecast | 3477.4556 | 347.7456 | 3129.71 |  |  |  | Utilities | MA Williams Plumbing | RI Waxahachie | 11222 | NA | Credit Card | RIW-CFR-02-132
2025-12-23 | 2 | 1/15 | Utility Labor | From MA Williams Plumbing - Partial Adjusted in Prior Forecast | 13522.5444 | 1352.2544 | 12170.29 |  |  |  | Utilities | MA Williams Plumbing | RI Waxahachie | 11222 | NA | Credit Card | RIW-CFR-02-133
2026-01-25 | 2 | 16 | Earthwork - SW3P | From Cardinal Strategies | 375 | 0 | 375 |  |  |  | Earthwork | Cardinal Strategies | Jaimin AMEX | 11252 | NA | Credit Card | RIW-CFR-02-134
2026-01-25 | 2 | 16 | Earthwork - SW3P | From Cardinal Strategies | 375 | 0 | 375 |  |  |  | Earthwork | Cardinal Strategies | Jaimin AMEX | 11253 | NA | Credit Card | RIW-CFR-02-135
2026-01-08 | 2 | 16 | Sitework - Grade Stakes | From AIM Construction Services | 940 | 0 | 940 |  |  |  | Earthwork | AIM Construction Services | Jaimin AMEX | 11263 | NA | Credit Card | RIW-CFR-02-136
2026-01-02 | 2 | 16 | Landscaping Pay App 01 | From 4 Nature Landscape | 16000 | 0 | 16000 |  |  |  | Landscaping and Irrigation | 4 Nature Landscape | Jaimin AMEX | 11270 | NA | Credit Card | RIW-CFR-02-137
2026-01-30 | 2 | 16 | Landscaping Pay App 03 | From 4 Nature Landscape | 65000 | 0 | 65000 |  |  |  | Landscaping and Irrigation | 4 Nature Landscape | Jaimin AMEX | 12190 | NA | Credit Card | RIW-CFR-02-138
2026-01-29 | 2 | 16 | Viking Fence Invoices | From Viking Fence | 576.43 | 0 | 576.43 |  |  |  | Earthwork | Viking Fence | Jaimin AMEX | 12191 | NA | Credit Card | RIW-CFR-02-139
2026-01-29 | 2 | 16 | Viking Fence Invoices | From Viking Fence | 457.36 | 0 | 457.36 |  |  |  | Earthwork | Viking Fence | Jaimin AMEX | 12192 | NA | Credit Card | RIW-CFR-02-140
2026-01-14 | 2 | 16 | Landscaping Pay App 02 | From 4 Nature Landscape | 4234 | 0 | 4234 |  |  |  | Landscaping and Irrigation | 4 Nature Landscape | Jaimin AMEX | 12193 | NA | Credit Card | RIW-CFR-02-141
2026-01-28 | 2 | 16 | Jobsite Equipment | From EquipmentShare | 65747.89 | 0 | 65747.89 |  |  |  | Equipment Rental | EquipmentShare | Jaimin AMEX | 12203 | NA | Credit Card | RIW-CFR-02-142
3. Concrete
| 3 | 2 | Draw 2 Funds |  |  |  |  | 570500 | 0 | 570500
| 3 | 4 | Draw 4 Funds |  |  |  |  | 51859.47 | 15000 | 36859.47
| 3 | 5 | Draw 5 Funds |  |  |  |  | 8600 | 0 | 8600
| 3 | 6 | Draw 6 Funds - Reimbursements |  |  |  |  | 3560.8 | 0 | 3560.8
| 3 | 6 | Draw 6 Funds - To Be Paid |  |  |  |  | 110300 | 10200 | 100100
| 3 | 6 | Draw 6 Funds - Future Forecast |  |  |  |  | 50000 | 5000 | 45000
| 3 | 7 | Draw 7 Funds - Reimbursements |  |  |  |  | 8766 | 0 | 8766
| 3 | 8 | Draw 8 Funds - Reimbursements |  |  |  |  | 3060 | 0 | 3060
| 3 | 10 | Draw 10 Funds - Reimbursements |  |  |  |  | 2625 | 0 | 2625
| 3 | 10 | Draw 10 Funds - To Be Paid |  |  |  |  | 33080 | 1168 | 31912
| 3 | 11 | Draw 11 Funds - Reimbursements |  |  |  |  | 1400 | 0 | 1400
| 3 | 12 | Draw 12 Funds - Reimbursements |  |  |  |  | 1239.47 | 0 | 1239.47
| 3 | 13 | Draw 13 Funds - Reimbursements |  |  |  |  | 781.53 | 0 | 781.53
| 3 | 13 | Draw 13 Funds - To Be Paid |  |  |  |  | 1200.32 | 0 | 1200.32
| 3 | 14 | Draw 14 Funds - Reimbursements |  |  |  |  | 6321.46 | 0 | 6321.46
| 3 | 14 | Draw 14 Funds - To Be Paid |  |  |  |  | 69000 | 6900 | 62100
| 3 | 15 | Draw 15 Funds - To Be Paid |  |  |  |  | 587.67 | 0 | 587.67
| 3 | 16 | Draw 16 Funds - Reimbursements |  |  |  |  | 900 | 0 | 900
| 3 | 16 | Draw 16 Funds - To Be Paid |  |  |  |  | 28855 | 750 | 28105
| 3 | 17 | Draw 17 Funds - Reimbursements |  |  |  |  | 1260.29 | 0 | 1260.29
| 3 | 17 | Draw 17 Funds - To Be Paid |  |  |  |  | 83450 | 8345 | 75105
2024-09-09 | 3 | 4 | Concrete - Misc. Material | From Home Depot | 91.84 | 0 | 91.84 |  |  |  | Concrete | Home Depot | Rush |  | NA |  | RIW-CFR-03-001
2024-09-10 | 3 | 4 | Concrete - Misc. Material | From Home Depot | 183.55 | 0 | 183.55 |  |  |  | Concrete | Home Depot | Rush |  | NA |  | RIW-CFR-03-002
2024-10-17 | 3 | 4 | Rebar | From Ready Cable | 621.36 | 0 | 621.36 |  |  |  | Concrete | Ready Cable | Rush | 10148 | NA |  | RIW-CFR-03-003
2024-11-05 | 3 | 2 | Concrete - Material + Labor | Building Pad + 50% of Paving | 386500 | 10000 | 376500 |  |  |  | Concrete | M D Bowles Construction | RI Waxahachie | 10060 | Yes | Check | RIW-CFR-03-004
2024-10-17 | 3 | 4 | Concrete - Misc. Material | From Home Depot - Purchase | 412.1 | 0 | 412.1 |  |  |  | Concrete | Home Depot | Rush | 10150 | NA |  | RIW-CFR-03-005
2024-11-03 | 3 | 4 | Concrete - Misc. Material | From Home Depot - Return | -412.1 | 0 | -412.1 |  |  |  | Concrete | Home Depot | Rush | 10150 | NA |  | RIW-CFR-03-006
2024-09-30 | 3 | 4 | Concrete - Misc. Material | From Home Depot | 70.22 | 0 | 70.22 |  |  |  | Concrete | Home Depot | Rush | 10124 | NA |  | RIW-CFR-03-007
2024-12-02 | 3 | 4 | Concrete - Light Pole Locations | AIM Construction Services | 700 | 0 | 700 |  |  |  | Concrete | AIM Construction Services | Boulder AMEX | 10104 | NA |  | RIW-CFR-03-008
| 3 | 4 | Concrete - Termite Control | From Bug Stop Pest Solutions (Reimbursement to MD Bowles Const.) | 5412.5 | 0 | 5412.5 |  |  |  | Termite Control | M D Bowles Construction | RI Waxahachie | 10163 | No | Check | RIW-CFR-03-009
| 3 | 2/4 | Concrete - Material + Labor | Partial Paving | 215000 | 5000 | 210000 |  |  |  | Concrete | M D Bowles Construction | RI Waxahachie | 10166 | Yes | Check | RIW-CFR-03-010
2024-12-27 | 3 | 4 | Concrete - Clearing Area for Paving | Haul Off Excess Dirt/Rock | 13080 | 0 | 13080 |  |  |  | Concrete | M D Bowles Construction | RI Waxahachie | 10199 | No | Check | RIW-CFR-03-011
2025-02-13 | 3 | 4 | Concrete - Rock for Pump Truck on Dirt | Import Rock | 700 | 0 | 700 |  |  |  | Concrete | M D Bowles Construction | RI Waxahachie | 10221 | Yes | Check | RIW-CFR-03-012
2025-02-13 | 3 | 5 | Concrete - Pour Temporary Approach / Clean Up | Change Order | 8600 | 0 | 8600 |  |  |  | Concrete | M D Bowles Construction | RI Waxahachie | 10306 | Yes | Check | RIW-CFR-03-013
2025-02-03 | 3 | 6 | Concrete - Surveyor to Stake Out Paving | AIM Construction Services | 700 | 0 | 700 |  |  |  | Concrete | AIM Construction Services | Boulder AMEX | 10274 | NA | Credit Card | RIW-CFR-03-014
2025-02-10 | 3 | 6 | Concrete - Surveyor to Stake Out Multiple Areas | AIM Construction Services | 1460 | 0 | 1460 |  |  |  | Concrete | AIM Construction Services | Owner (JP) AMEX | 10280 | NA | Credit Card | RIW-CFR-03-015
2025-02-10 | 3 | 6 | Rebar Shop Drawings | From Post-Tension Services | 1400.8 | 0 | 1400.8 |  |  |  | Concrete | Post-Tension Services | Owner (JP) AMEX | 10281 | NA | Credit Card | RIW-CFR-03-016
2025-03-18 | 3 | 6 | As Built Drawings - First Payment | From A U Design (For Confirmation of Slab/Other Dimensions) | 4200 | 0 | 4200 |  |  |  | Concrete | A U Design | RI Waxahachie | 10337 | NA | Check | RIW-CFR-03-017
2025-08-08 | 3 | 6 | As Built Drawings - Second Payment | From A U Design (For Confirmation of Slab/Other Dimensions) | 3000 | 0 | 3000 |  |  |  | Concrete | A U Design | RI Waxahachie | 10337 | NA | Check | RIW-CFR-03-018
2025-03-26 | 3 | 6 | Concrete - Additional Paving Section | From M D Bowles Construction | 102000 | 10200 | 91800 |  |  |  | Concrete | M D Bowles Construction | RI Waxahachie | 10338 | Yes | Check | RIW-CFR-03-019
2025-03-26 | 3 | 6 | Concrete - Select Fill Material to Grade Paving | From M D Bowles Construction | 1100 | 0 | 1100 |  |  |  | Concrete | M D Bowles Construction | RI Waxahachie | 10339 | Yes | Check | RIW-CFR-03-020
2025-03-14 | 3 | 7 | Dirt Import to Backfill Curbs | From Alliance Trucking | 5566 | 0 | 5566 |  |  |  | Concrete | Alliance Trucking | RI Waxahachie | 10401 | NA | ACH | RIW-CFR-03-021
2025-03-14 | 3 | 7 | Pouring and Forming Inlet Lids for Utilities | From Americo Concrete | 3200 | 0 | 3200 |  |  |  | Concrete | Americo Concrete | RI Waxahachie | 10402 | Yes | Check | RIW-CFR-03-022
2025-05-02 | 3 | 8 | Concrete - Testing | Geoscience Engineers | 3060 | 0 | 3060 |  |  |  | Concrete | Geoscience Engineers | Owner (JP) AMEX | 10454 | NA | Credit Card | RIW-CFR-03-023
2025-05-12 | 3 | 6 | Concrete - Cut and Re-Pour for Utilities on Rae | Change Order | 16680 | 1668 | 15012 |  |  |  | Concrete | M D Bowles Construction | RI Waxahachie | 10475 | Yes | Check | RIW-CFR-03-024
2025-06-11 | 3 | 10 | Import Dirt Material for Concrete | Alliance Trucking | 2625 | 0 | 2625 |  |  |  | Concrete | Alliance Trucking | RI Waxahachie | 10558 | Yes | ACH | RIW-CFR-03-025
2025-08-08 | 3 | 6/10 | Flume, Sidewalk and CO | From MD Bowles Construction - Pay App 09 | 66400 | 4500 | 61900 |  |  |  | Concrete | M D Bowles Construction | RI Waxahachie | 10615 | No | ACH | RIW-CFR-03-026
2025-07-14 | 3 | 11 | Staking Sidewalk, Flume, & Light Poles | AIM Construction Services | 1400 | 0 | 1400 |  |  |  | Concrete | AIM Construction Services | Jaimin AMEX | 10668 | NA | Credit Card | RIW-CFR-03-027
2025-08-06 | 3 | 12 | Concrete and Density Testing | Geoscience Engineers | 1222 | 0 | 1222 |  |  |  | Concrete | Geoscience Engineers | Jaimin AMEX | 10776 | NA | Credit Card | RIW-CFR-03-028
2025-08-12 | 3 | 12 | Quikcrete Concrete Mix | From Home Depot - Concrete Mix | 17.47 | 0 | 17.47 |  |  |  | Concrete | Home Depot | Boulder AMEX | 10790 | NA | Credit Card | RIW-CFR-03-029
2025-09-02 | 3 | 13 | Concrete Mix | From Home Depot | 81.53 | 0 | 81.53 |  |  |  | Concrete | Home Depot | Boulder AMEX | 10866 | NA | Credit Card | RIW-CFR-03-030
2025-09-22 | 3 | 13 | Concrete - Surveyor to Stake Out Paving | For AIM CS Inc | 700 | 0 | 700 |  |  |  | Concrete | AIM Construction Services | [To Be Confirmed] | 10880 | NA | Credit Card | RIW-CFR-03-031
2025-11-07 | 3 | 13 | Concrete - Equipment | EquipmentShare | 1200.32 | 0 | 1200.32 |  |  |  | Concrete | EquipmentShare | RI Waxahachie | 10934 | NA | Direct Pay | RIW-CFR-03-032
2025-09-30 | 3 | 14 | Quikcrete Concrete Mix | From Home Depot | 174.72 | 0 | 174.72 |  |  |  | Concrete | Home Depot | Boulder AMEX | 10959 | NA | Credit Card | RIW-CFR-03-033
2025-09-30 | 3 | 14 | Quikcrete Concrete Mix | From Home Depot | 99.01 | 0 | 99.01 |  |  |  | Concrete | Home Depot | Boulder AMEX | 10960 | NA | Credit Card | RIW-CFR-03-034
2025-10-01 | 3 | 14 | Misc. Jobsite Materials | From Home Depot - Degreaser Concrete Pressure Wash & Concrete | 15.67 | 0 | 15.67 |  |  |  | Concrete | Home Depot | Boulder AMEX | 10961 | NA | Credit Card | RIW-CFR-03-035
2025-10-21 | 3 | 14 | Bore for PVC | From Alpha Directional Drilling | 4500 | 0 | 4500 |  |  |  | Concrete | Alpha Directional Drilling | RI Waxahachie | 10996 | NA | Check | RIW-CFR-03-036
2025-10-10 | 3 | 14 | Elevator Concrete Work | From POR Construction | 300 | 0 | 300 |  |  |  | Concrete | POR Construction | Boulder | 11005 | NA | Wire | RIW-CFR-03-037
2025-10-27 | 3 | 14 | Concrete & Masonry Waterproofer | From Lowe's | 477.21 | 0 | 477.21 |  |  |  | Concrete | Lowe's | Boulder AMEX | 11015 | NA | Credit Card | RIW-CFR-03-038
2025-10-27 | 3 | 14 | Misc. Jobsite Materials | From Home Depot - Aerosol Liquid Rubber Sealant Coating | 389.18 | 0 | 389.18 |  |  |  | Concrete | Home Depot | Boulder AMEX | 11034 | NA | Credit Card | RIW-CFR-03-039
2025-10-27 | 3 | 14 | Misc. Jobsite Materials | From Home Depot - Waterproof Patch and Seal Tape Black, Insect Repellent | 43.75 | 0 | 43.75 |  |  |  | Concrete | Home Depot | Boulder AMEX | 11036 | NA | Credit Card | RIW-CFR-03-040
2025-10-28 | 3 | 14 | Misc. Jobsite Materials | From Home Depot - Window and Door Sealant Clear | 321.92 | 0 | 321.92 |  |  |  | Concrete | Home Depot | Boulder AMEX | 11039 | NA | Credit Card | RIW-CFR-03-041
2025-11-20 | 3 | 14 | Gypcrete | From Kent Companies | 69000 | 6900 | 62100 |  |  |  | Gypcrete | Kent Companies | RI Waxahachie | 11059 | NA | [To Be Paid] | RIW-CFR-03-042
2025-11-04 | 3 | 15 | Concrete Material | From Home Depot - Black Large Chisel Tip Jobsite Permanent Marker | 21.01 | 0 | 21.01 |  |  |  | Concrete | Home Depot | Boulder AMEX | 11045 | NA | Credit Card | RIW-CFR-03-043
2025-11-11 | 3 | 15 | Concrete Material | From Home Depot - Rotary Hammer & Carbide Drill Bit | 505.35 | 0 | 505.35 |  |  |  | Concrete | Home Depot | Boulder AMEX | 11071 | NA | Credit Card | RIW-CFR-03-044
2025-11-12 | 3 | 15 | Concrete Material | From Home Depot - Turbo Diamond Blade & Diamond Grit | 61.31 | 0 | 61.31 |  |  |  | Concrete | Home Depot | Boulder AMEX | 11072 | NA | Credit Card | RIW-CFR-03-045
2026-01-08 | 3 | 16 | Concrete - Retaining Walls & Perimeter Staking | From AIM Construction Services | 900 | 0 | 900 |  |  |  | Concrete | AIM Construction Services | Jaimin AMEX | 11262 | NA | Credit Card | RIW-CFR-03-046
[To Be Paid] | 3 | 16 | Concrete - Testing & Inspections | From Geoscience Engineers LLC | 855 | 0 | 855 |  |  |  | Concrete | Geoscience Engineers | [To Be Paid] | 12179 | NA | [To Be Paid] | RIW-CFR-03-047
2026-02-17 | 3 | 16 | Backfill and Grading | From T18 Construction LLC | 7500 | 750 | 6750 |  |  |  | Concrete | T18 Construction LLC | RI Waxahachie | 12181 | NA | [To Be Paid] | RIW-CFR-03-048
[To Be Paid] | 3 | 16 | Concrete | From M D Bowles Construction - Pay App 10 | 20500 | 0 | 20500 |  |  |  | Concrete | M D Bowles Construction | [To Be Paid] | 12185 | NA | [To Be Paid] | RIW-CFR-03-049
2026-02-10 | 3 | 17 | Concrete Anchors | From Home Depot - Concrete Anchors, Drill Bit and Screws | 74.77 | 0 | 74.77 |  |  |  | Concrete | Home Depot | Boulder AMEX | 12216 | NA | Credit Card
2026-02-12 | 3 | 17 | Concrete Mix | From Home Depot - Concrete Mix And Snacks | 50.03 | 0 | 50.03 |  |  |  | Concrete | Home Depot | Boulder AMEX | 12218 | NA | Credit Card
2026-02-16 | 3 | 17 | Concrete Anchors | From Home Depot - LED Bulb, Cable, Zinc Washer and Concrete Anchors | 373.27 | 0 | 373.27 |  |  |  | Concrete | Home Depot | Boulder AMEX | 12247 | NA | Credit Card
2026-02-15 | 3 | 17 | Concrete Mix | From Home Depot - Concrete Mix | 213.69 | 0 | 213.69 |  |  |  | Concrete | Home Depot | Boulder AMEX | 12250 | NA | Credit Card
2026-02-10 | 3 | 17 | Concrete Block | From Home Depot - Concrete Block | 445.99 | 0 | 445.99 |  |  |  | Concrete | Home Depot | Boulder AMEX | 12287 | NA | Credit Card
2026-02-17 | 3 | 17 | Concrete Material | From Home Depot - Cement, Cutter and Glove | 102.54 | 0 | 102.54 |  |  |  | Concrete | Home Depot | Boulder AMEX | 12359 | NA | Credit Card
2026-03-12 | 3 | 17 | Concrete Labor | From MD Bowles Construction - Pay App 11 (First Payment) | 3450 | 345 | 3105 |  |  |  | Concrete | M D Bowles Construction | RI Waxahachie | 12556 | No | ACH
2026-03-12 | 3 | 17 | Concrete Labor | From MD Bowles Construction - Pay App 11 (Second Payment) | 80000 | 8000 | 72000 |  |  |  | Concrete | M D Bowles Construction | RI Waxahachie | 12556 | No | ACH
4. Masonry
| 4 | 7 | Draw 7 Funds - Reimbursements |  |  |  |  | 964.51 | 0 | 964.51
| 4 | 7 | Draw 7 Funds - To Be Paid |  |  |  |  | 8000 | 800 | 7200
2025-03-17 | 4 | 7 | CMU Block Material | From Home Depot - Concrete Block | 964.51 | 0 | 964.51 |  |  |  | CMU | Home Depot | Boulder AMEX | 10362 | NA | Credit Card | RIW-CFR-04-001
2025-04-15 | 4 | 7 | Dumpster Block Install | For VG Stucco - First Invoice | 8000 | 800 | 7200 |  |  |  | CMU | VG Stucco | RI Waxahachie | 10433 | Yes | Check | RIW-CFR-04-002
5. Metals
| 5 | 1 | Order Structural Steel Material | Norton Metals |  |  |  | 20032.34 | 0 | 20032.34
| 5 | 1 | Structural Steel Fabrication | Go Construction |  |  |  | 12000 | 1200 | 10800
| 5 | 2 | Metals - Forecast | Structural Steel Erection + Materials |  |  |  | 60000 | 2600 | 57400
| 5 | 16 | Structural Steel Fabrication | Go Construction |  |  |  | 320 | 320 | 0
| 5 | 17 | Draw 17 Funds - Reimbursements |  |  |  |  | 8284.57 | 1047.5 | 7237.07
2024-08-22 | 5 | 1 | Structural Steel Material | Norton Metals | 20032.33 | 0 | 20032.33 |  |  |  | Structural Steel Material | Norton Metals | Jaimin Uncle | 10026 | NA |  | RIW-CFR-05-001
2024-09-22 | 5 | 1 | Steel Fabrication of Base Plates + Columns | Go Construction | 4000 | 400 | 3600 |  |  |  | Structural Steel Material | Go Construction | Boulder | 10020 | Yes | Check | RIW-CFR-05-002
2024-07-05 | 5 | 2 | Structural Steel Takeoff | Joe Cruz | 360.5 | 0 | 360.5 |  |  |  | Structural Steel Material | Joe Cruz | Rush |  | NA |  | RIW-CFR-05-003
2024-09-12 | 5 | 2 | Structural Steel Material | Norton Metals | 3601.48 | 0 | 3601.48 |  |  |  | Structural Steel Material | Norton Metals | Rush |  | NA |  | RIW-CFR-05-004
2024-09-13 | 5 | 2 | Structural Steel Material | Norton Metals | 33.24 | 0 | 33.24 |  |  |  | Structural Steel Material | Norton Metals | Rush |  | NA |  | RIW-CFR-05-005
2024-09-13 | 5 | 2 | Structural Steel Material | Norton Metals | 10.82 | 0 | 10.82 |  |  |  | Structural Steel Material | Norton Metals | Rush |  | NA |  | RIW-CFR-05-006
2024-11-05 | 5 | 2 | Structural Steel Labor - Install Base Plate/Columns | Go Construction | 6500 | 650 | 5850 |  |  |  | Structural Steel Material | Go Construction | Boulder | 10098 | Yes | Check | RIW-CFR-05-007
2024-11-26 | 5 | 2 | Structural Steel Material | Home Depot | 304.01 | 0 | 304.01 |  |  |  | Structural Steel Material | Home Depot | Boulder AMEX | 10128 | NA |  | RIW-CFR-05-008
2024-11-18 | 5 | 2 | Structural Steel Material | Home Depot | 407.95 | 0 | 407.95 |  |  |  | Structural Steel Material | Home Depot | Boulder AMEX | 10088 | NA |  | RIW-CFR-05-009
2025-01-12 | 5 | 2 | Structural Steel - Equipment | EquipmentShare | 929.52 | 0 | 929.52 |  |  |  | Structural Steel Material | EquipmentShare | RI Waxahachie | 10158 | NA |  | RIW-CFR-05-010
2024-12-26 | 5 | 2 | Structural Steel Material | Norton Metals | 2266.76 | 0 | 2266.76 |  |  |  | Structural Steel Material | Norton Metals | Rush | 10205 | NA |  | RIW-CFR-05-011
2024-01-06 | 5 | 2 | Structural Steel Material | Norton Metals | 522.24 | 0 | 522.24 |  |  |  | Structural Steel Material | Norton Metals | Rush | 10206 | NA |  | RIW-CFR-05-012
[Confirm] | 5 | 2 | Structural Steel - Equipment | EquipmentShare | 397.1 | 0 | 397.1 |  |  |  | Structural Steel Material | EquipmentShare | [Confirm] | 10211 | NA |  | RIW-CFR-05-013
2025-02-10 | 5 | 2 | Shop Drawings - Initial Payment | From Nedes LLC | 1000 | 0 | 1000 |  |  |  | Misc. Steel | Nedes | Owner (JP) AMEX | 10282 | NA | Credit Card | RIW-CFR-05-014
2025-02-18 | 5 | 2 | Structural Steel Inspection | From Geoscience Engineers (Through Steel Inspectors of Texas) | 500 | 0 | 500 |  |  |  | Misc. Steel | Geoscience Engineers | Owner (JP) AMEX | 10286 | NA | Credit Card | RIW-CFR-05-015
2025-01-28 | 5 | 2 | Structural Steel Labor | Go Construction - Install Columns/Beams/Supports | 5000 | 500 | 4500 |  |  |  | Structural Steel Material | Go Construction | RI Waxahachie | 10311 | Yes | Check | RIW-CFR-05-016
2025-03-29 | 5 | 2 | Structural Steel Labor | Go Construction - Install Columns/Beams/Supports | 4000 | 400 | 3600 |  |  |  | Structural Steel Material | Go Construction | RI Waxahachie | 10439 | No | Check | RIW-CFR-05-017
2025-06-03 | 5 | 2 | Structural Steel Labor | Go Construction - Install Elevator Steel | 5000 | 500 | 4500 |  |  |  | Structural Steel Material | Go Construction | RI Waxahachie | 10557 | Yes | ACH | RIW-CFR-05-018
2025-06-26 | 5 | 2 | Structural Steel Material | From Norton Metals | 1042.36 | 0 | 1042.36 |  |  |  | Structural Steel Material | Norton Metals | Boulder AMEX | 10595 | NA | Credit Card | RIW-CFR-05-019
2025-05-08 | 5 | 2 | Additional Elevator Steel Material | From Maverick Metal | 437.98 | 0 | 437.98 |  |  |  | Structural Steel Material | Maverick Metal | Boulder AMEX |  | NA | Credit Card | RIW-CFR-05-020
2025-08-07 | 5 | 2 | Dumpster Gate Material | From My Cedar | 1248 | 0 | 1248 |  |  |  | Misc. Steel | My Cedar | Boulder AMEX | 10801 | NA | Credit Card | RIW-CFR-05-021
2025-08-12 | 5 | 1 | Structural Steel | Go Construction - Dumpster Gate & Steel | 8000 | 800 | 7200 |  |  |  | Structural Steel Material | Go Construction | RI Waxahachie | 10805 | No | ACH | RIW-CFR-05-022
2025-08-20 | 5 | 2 | Additional Elevator Steel Material | From Maverick Metal | 2948.73 | 0 | 2948.73 |  |  |  | Structural Steel Material | Maverick Metal | Boulder AMEX | 10842 | NA | Credit Card | RIW-CFR-05-023
2025-08-21 | 5 | 2 | Elevator Welding | From Joel Pineda | 2300 | 0 | 2300 |  |  |  | Structural Steel Material | Joel Pineda | RI Waxahachie | 10840 | NA | Check | RIW-CFR-05-024
2025-09-15 | 5 | 2 | Metal Handrails Sidewalk | For Go Construction | 1200 | 120 | 1080 |  |  |  | Structural Steel Material | Go Construction | RI Waxahachie | 10892 | NA | ACH | RIW-CFR-05-025
2025-08-25 | 5 | 2 | Structural Steel Testing | Geoscience Engineers | 1000 | 0 | 1000 |  |  |  | Misc. Steel | Geoscience Engineers | [To Be Confirmed] | 10828 | NA | Credit Card | RIW-CFR-05-026
2025-12-16 | 5 | 2 | Metal Material | From Norton Metals | 2528.18 | 0 | 2528.18 |  |  |  | Structural Steel Material | Norton Metals | Boulder AMEX | 11160 | NA | Credit Card | RIW-CFR-05-027
2025-01-24 | 5 | 2 | Metal Material | From Sherwin Williams | 1033.25 | 0 | 1033.25 |  |  |  | Structural Steel Material | Sherwin Williams | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-05-028
2025-12-26 | 5 | 2 | Metal Material | From Home Depot - Steel Hex Bolt, Magnetic Nut Driver & Spade Drill | 57.56 | 0 | 57.56 |  |  |  | Structural Steel Material | Home Depot | Boulder AMEX | 11258 | NA | Credit Card | RIW-CFR-05-029
2026-01-09 | 5 | 2 | Base Plate & Elbow | From Maverick Metal Trading Inc | 967.12 | 0 | 967.12 |  |  |  | Structural Steel Material | Maverick Metal | Jaimin AMEX | 11286 | NA | Credit Card | RIW-CFR-05-030
2026-02-04 | 5 | 2 | Metal Handrails For Stairs | For Go Construction - Pay App 08 | 7180 | 430 | 6750 |  |  |  | Structural Steel Material | Go Construction | RI Waxahachie | 12189 | NA | ACH | RIW-CFR-05-031
2026-02-04 | 5 | 16 | Metal Handrails For Stairs | For Go Construction - Pay App 08 | 320 | 320 | 0 |  |  |  | Structural Steel Material | Go Construction | RI Waxahachie | 12189 | NA | ACH | RIW-CFR-05-032
2026-02-18 | 5 | 2 | Metal Material | From Home Depot - Misc. Jobsite SuppliesSteel Sheet Metal Screws | 32.78 | 0 | 32.78 |  |  |  | Structural Steel Material | Home Depot | Boulder AMEX | 12223 | NA | Credit Card
2026-02-20 | 5 | 2 | Metal Railing Labor (CO) | From J&S7 Consulting | 5000 | 0 | 5000 |  |  |  | Structural Steel Material | J&S7 Consulting | RI Waxahachie | 12314 | NA | ACH
2026-02-10 | 5 | 2 | Structural Steel Labor (CO) | From Go Construction - Pay App 09 (Split) | 2190.43 | 0 | 2190.43 |  |  |  | Structural Steel Material | Go Construction LLC | RI Waxahachie | 12344 | NA | ACH
2026-02-10 | 5 | 17 | Structural Steel Labor (CO) | From Go Construction - Pay App 09 (Split) | 1609.57 | 380 | 1229.57 |  |  |  | Structural Steel Material | Go Construction LLC | RI Waxahachie | 12344 | NA | ACH
2026-02-03 | 5 | 17 | Structural Steel Labor (CO) | From Go Construction - Pay App 10 & 11 | 6675 | 667.5 | 6007.5 |  |  |  | Structural Steel Material | Go Construction LLC | RI Waxahachie | 12345 | NA | ACH
6. Wood, Plastics, and Composites
| 6 | 2 | Draw 2 Funds - Labor |  |  |  |  | 50000 | 5000 | 45000
| 6 | 3 | Draw 3 Funds - Material & Other |  |  |  |  | 403754.85 | 0 | 403754.85
| 6 | 3 | Draw 3 Funds - Labor |  |  |  |  | 47927 | 4792.7 | 43134.3
| 6 | 4 | Draw 4 Funds - Material & Other |  |  |  |  | 123802.85 | 0 | 123802.85
| 6 | 4 | Draw 4 Funds - Labor |  |  |  |  | 129348 | 12934.8 | 116413.2
| 6 | 5 | Draw 5 Funds - Material & Other |  |  |  |  | 78653.15 | 0 | 78653.15
| 6 | 5 | Draw 5 Funds - Labor |  |  |  |  | 47960 | 4796 | 43164
| 6 | 6 | Draw 6 Funds - Material & Other |  |  |  |  | 45809.32 | 0 | 45809.32
| 6 | 6 | Draw 6 Funds - Labor |  |  |  |  | 25113.33 | 2511.333 | 22601.997
| 6 | 6 | Draw 6 Funds - Equipment |  |  |  |  | 18343.82 | 0 | 18343.82
| 6 | 7 | Draw 7 Funds - Labor |  |  |  |  | 16475 | 1647.5 | 14827.5
| 6 | 7 | Draw 7 Funds - Material & Other |  |  |  |  | 7066.83 | 0 | 7066.83
| 6 | 8 | Draw 8 Funds - Labor |  |  |  |  | 13900 | 1390 | 12510
| 6 | 8 | Draw 8 Funds - Material & Other |  |  |  |  | 15590.32 | 0 | 15590.32
| 6 | 9 | Draw 9 Funds - Material & Other |  |  |  |  | 40073.5 | 1725.5 | 38348
| 6 | 10 | Draw 10 Funds - Material & Other |  |  |  |  | 12139.19 | 261 | 11878.19
| 6 | 10 | Draw 10 Funds - To Be Paid |  |  |  |  | 15680 | 1568 | 14112
| 6 | 11 | Draw 11 Funds - Material & Other |  |  |  |  | 34592.66 | 520.98 | 34071.68
| 6 | 12 | Draw 12 Funds - Material & Other |  |  |  |  | 83128.28 | 0 | 83128.28
| 6 | 13 | Draw 13 Funds - Material & Other |  |  |  |  | 15486.87 | 0 | 15486.87
| 6 | 14 | Draw 14 Funds - Material & Other |  |  |  |  | 9680.29 | 0 | 9680.29
| 6 | 15 | Draw 15 Funds - Material & Other |  |  |  |  | 19594.32 | 0 | 19594.32
| 6 | 16 | Draw 16 Funds - Material & Other |  |  |  |  | 46880.42 | 0 | 46880.42
2024-09-04 | 6 | 3 | Lumber Takeoff | Joe Cruz | 1300 | 0 | 1300 |  |  |  | Framing Material | Joe Cruz | Boulder | 10051 | NA |  | RIW-CFR-06-001
2024-10-24 | 6 | 3 | Framing Efforts + Takeoff/Discussion | Go Construction | 5000 | 0 | 5000 |  |  |  | Framing Material | Go Construction | RI Waxahachie | 10099 | Yes | Check | RIW-CFR-06-002
2024-09-09 | 6 | 3 | Millwork Shop Drawings | Dreamwood | 3000 | 0 | 3000 |  |  |  | Public Area Millwork Material | Dreamwood | Boulder | 10052 | NA |  | RIW-CFR-06-003
2024-11-13 | 6 | 2/3 | Framing First Floor | For Reytex Framing Corporation | 2850 | 0 | 2850 |  |  |  | Framing Labor | Reytex Framing Corporation | Boulder | 10152 | Yes | Check | RIW-CFR-06-004
2024-10-29 | 6 | 2/3 | Framing Labor | For Reytex Framing Corporation | 7967 | 796.7 | 7170.3 |  |  |  | Framing Labor | Reytex Framing Corporation | RI Waxahachie | 10065 | Yes | Check | RIW-CFR-06-005
2024-11-05 | 6 | 2/3 | Framing Labor | For Reytex Framing Corporation | 7965 | 796.5 | 7168.5 |  |  |  | Framing Labor | Reytex Framing Corporation | RI Waxahachie | 10066 | Yes | Check | RIW-CFR-06-006
2024-11-26 | 6 | 2/3 | Framing Labor | For Reytex Framing Corporation | 24100 | 2410 | 21690 |  |  |  | Framing Labor | Reytex Framing Corporation | RI Waxahachie | 10067 | Yes | Check | RIW-CFR-06-007
2024-12-03 | 6 | 2/3 | Framing Labor | For Reytex Framing Corporation | 32895 | 3289.5 | 29605.5 |  |  |  | Framing Labor | Reytex Framing Corporation | RI Waxahachie | 10068 | Yes | Check | RIW-CFR-06-008
2024-12-06 | 6 | 2/3 | Framing Labor | For Reytex Framing Corporation | 25000 | 2500 | 22500 |  |  |  | Framing Labor | Reytex Framing Corporation | RI Waxahachie | 10069 | Yes | Check | RIW-CFR-06-009
2024-10-22 | 6 | 3 | Framing Material | From Home Depot | 98557.93 | 0 | 98557.93 |  |  |  | Framing Material | Home Depot | Jaimin Uncle | 10070 | NA |  | RIW-CFR-06-010
2024-11-27 | 6 | 3 | Framing Material | From Home Depot | 2753.19 | 0 | 2753.19 |  |  |  | Framing Material | Home Depot | Jaimin Uncle | 10071 | NA |  | RIW-CFR-06-011
2024-12-04 | 6 | 3 | Framing Material | From Home Depot | 723.28 | 0 | 723.28 |  |  |  | Framing Material | Home Depot | Jaimin Uncle | 10072 | NA |  | RIW-CFR-06-012
2024-11-25 | 6 | 3 | Framing Material | From Home Depot | 49749.95 | 0 | 49749.95 |  |  |  | Framing Material | Home Depot | Jaimin Uncle | 10073 | NA |  | RIW-CFR-06-013
2024-11-21 | 6 | 3 | Framing Material | From Home Depot | 6594.76 | 0 | 6594.76 |  |  |  | Framing Material | Home Depot | Jaimin Uncle | 10074 | NA |  | RIW-CFR-06-014
2024-11-19 | 6 | 3 | Framing Material | From Home Depot | 28345.61 | 0 | 28345.61 |  |  |  | Framing Material | Home Depot | Jaimin Uncle | 10075 | NA |  | RIW-CFR-06-015
2024-11-15 | 6 | 3 | Framing Material | From Home Depot | 2238.76 | 0 | 2238.76 |  |  |  | Framing Material | Home Depot | Jaimin Uncle | 10076 | NA |  | RIW-CFR-06-016
2024-12-07 | 6 | 3 | Framing Material | From Home Depot | 11690.87 | 0 | 11690.87 |  |  |  | Framing Material | Home Depot | Jaimin Uncle | 10077 | NA |  | RIW-CFR-06-017
2024-12-02 | 6 | 3 | Framing Material | From Home Depot | 37265.28 | 0 | 37265.28 |  |  |  | Framing Material | Home Depot | Jaimin Uncle | 10078 | NA |  | RIW-CFR-06-018
2024-11-20 | 6 | 3 | Framing Material | From Home Depot | 405.67 | 0 | 405.67 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10123 | NA |  | RIW-CFR-06-019
2024-11-21 | 6 | 3 | Framing Material | From Home Depot | 63 | 0 | 63 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10122 | NA |  | RIW-CFR-06-020
2024-11-20 | 6 | 3 | Framing Material | From Cowtown Materials | 453.76 | 0 | 453.76 |  |  |  | Framing Material | Cowtown Materials | Boulder AMEX |  | NA |  | RIW-CFR-06-021
2024-11-14 | 6 | 3 | Truss Material | From Ranger Truss | 49299.87 | 0 | 49299.87 |  |  |  | Trusses | Ranger Truss | RI Waxahachie | 10064 | NA |  | RIW-CFR-06-022
2025-01-12 | 6 | 3 | Framing - Equipment | EquipmentShare | 7083.62 | 0 | 7083.62 |  |  |  | Framing Material | EquipmentShare | RI Waxahachie | 10159 | NA |  | RIW-CFR-06-023
2024-12-24 | 6 | 3 | Truss Material | From Ranger Truss | 48189.65 | 0 | 48189.65 |  |  |  | Trusses | Ranger Truss | RI Waxahachie | 10160 | NA |  | RIW-CFR-06-024
2024-12-24 | 6 | 3 | Truss Material | From Ranger Truss | 48189.65 | 0 | 48189.65 |  |  |  | Trusses | Ranger Truss | RI Waxahachie | 10161 | NA |  | RIW-CFR-06-025
2024-12-11 | 6 | 4 | Framing Material | From Home Depot | 21398.51 | 0 | 21398.51 |  |  |  | Framing Material | Home Depot | Jaimin Uncle | 10167 | NA |  | RIW-CFR-06-026
2024-12-16 | 6 | 4 | Framing Material | From Home Depot | 17049.67 | 0 | 17049.67 |  |  |  | Framing Material | Home Depot | Jaimin Uncle | 10168 | NA |  | RIW-CFR-06-027
2024-12-23 | 6 | 4 | Framing Material | From Home Depot | 52825.48 | 0 | 52825.48 |  |  |  | Framing Material | Home Depot | Jaimin Uncle | 10169 | NA |  | RIW-CFR-06-028
2024-12-27 | 6 | 4 | Framing Material | From Home Depot | 9190.86 | 0 | 9190.86 |  |  |  | Framing Material | Home Depot | Jaimin Uncle | 10170 | NA |  | RIW-CFR-06-029
2025-01-07 | 6 | 4 | Framing Material | From Home Depot | 16716.45 | 0 | 16716.45 |  |  |  | Framing Material | Home Depot | Jaimin Uncle | 10171 | NA |  | RIW-CFR-06-030
2025-01-07 | 6 | 4 | Framing Material | From Home Depot | 1436.52 | 0 | 1436.52 |  |  |  | Framing Material | Home Depot | Jaimin Uncle | 10222 | NA |  | RIW-CFR-06-031
2024-12-13 | 6 | 4 | Framing Labor | For Reytex Framing Corporation | 23450 | 0 | 23450 |  |  |  | Framing Labor | Reytex Framing Corporation | RI Waxahachie | 10172 | Yes | Check | RIW-CFR-06-032
2024-12-20 | 6 | 4 | Framing Labor | For Reytex Framing Corporation | 28398 | 2839.8 | 25558.2 |  |  |  | Framing Labor | Reytex Framing Corporation | RI Waxahachie | 10173 | Yes | Check | RIW-CFR-06-033
2024-12-27 | 6 | 4 | Framing Labor | For Reytex Framing Corporation | 26250 | 4970 | 21280 |  |  |  | Framing Labor | Reytex Framing Corporation | RI Waxahachie | 10174 | Yes | Check | RIW-CFR-06-034
2025-01-03 | 6 | 4 | Framing Labor | For Reytex Framing Corporation | 28750 | 0 | 28750 |  |  |  | Framing Labor | Reytex Framing Corporation | RI Waxahachie | 10175 | Yes | Check | RIW-CFR-06-035
2025-01-11 | 6 | 4 | Framing Labor | For Reytex Framing Corporation | 22500 | 5125 | 17375 |  |  |  | Framing Labor | Reytex Framing Corporation | RI Waxahachie | 10216 | Yes | Check | RIW-CFR-06-036
2024-12-24 | 6 | 4 | Framing Material | From Home Depot | 912.07 | 0 | 912.07 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10202 | NA |  | RIW-CFR-06-037
2025-01-02 | 6 | 4 | Framing Material - Marking Material | From Home Depot | 110.29 | 0 | 110.29 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10203 | NA |  | RIW-CFR-06-038
2025-01-07 | 6 | 4 | Framing Material | From Home Depot | 412.57 | 0 | 412.57 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10204 | NA |  | RIW-CFR-06-039
[Confirm] | 6 | 4 | Framing - Equipment | EquipmentShare | 3750.43 | 0 | 3750.43 |  |  |  | Framing Material | EquipmentShare | [Confirm] | 10212 | NA |  | RIW-CFR-06-040
2025-03-11 | 6 | 5 | Truss Material - Partial Final Payment | From Ranger Truss | 53653 | 0 | 53653 |  |  |  | Trusses | Ranger Truss | RI Waxahachie | 10309 | NA | Wire Transfer | RIW-CFR-06-041
2025-06-27 | 6 | 5 | Truss Material - Partial Final Payment | From Ranger Truss | 25000.15 | 0 | 25000.15 |  |  |  | Trusses | Ranger Truss | RI Waxahachie | 10309 | NA | Wire | RIW-CFR-06-042
2025-01-17 | 6 | 5 | Framing Labor | For Reytex Framing Corporation - Invoice 12 | 22000 | 2200 | 19800 |  |  |  | Framing Labor | Reytex Framing Corporation | Boulder | 10320 | Yes | Check | RIW-CFR-06-043
2025-01-25 | 6 | 5 | Framing Labor | For Reytex Framing Corporation - Invoice 13 | 25960 | 2596 | 23364 |  |  |  | Framing Labor | Reytex Framing Corporation | RI Waxahachie | 10321 | Yes | Check | RIW-CFR-06-044
2025-01-13 | 6 | 6 | Framing - Required Fire Hydrants | From Texas Fire Extinguisher | 2776.29 | 0 | 2776.29 |  |  |  | Framing Material | Texas Fire Extinguisher | Boulder AMEX | 10241 | NA | Credit Card | RIW-CFR-06-045
2025-01-24 | 6 | 6 | Framing Material | From Home Depot - Fall Protection | 150.45 | 0 | 150.45 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10259 | NA | Credit Card | RIW-CFR-06-046
2025-01-28 | 6 | 6 | Framing Material | From Home Depot - Fall Protection & Anchor | 404.16 | 0 | 404.16 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10260 | NA | Credit Card | RIW-CFR-06-047
2025-01-28 | 6 | 6 | Framing Material | From Home Depot - Parawedge Anchor | 235.99 | 0 | 235.99 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10261 | NA | Credit Card | RIW-CFR-06-048
2025-01-31 | 6 | 6 | Framing Material | From Home Depot - Return for Parawedge Anchor | -353.98 | 0 | -353.98 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10262 | NA | Refund | RIW-CFR-06-049
2025-01-31 | 6 | 6 | Framing Material | From Home Depot - Misc. Return | -1.65 | 0 | -1.65 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10263 | NA | Refund | RIW-CFR-06-050
2025-01-31 | 6 | 6 | Framing Material | From Home Depot - Misc. | 100 | 0 | 100 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10263 | NA | Credit Card | RIW-CFR-06-051
2025-02-03 | 6 | 6 | Framing Material | From Home Depot - Washers and Screws | 85.7 | 0 | 85.7 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10264 | NA | Credit Card | RIW-CFR-06-052
2025-02-25 | 6 | 6 | Framing Material | From Home Depot - Hurricane Ties | 179.7 | 0 | 179.7 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10270 | NA | Credit Card | RIW-CFR-06-053
2025-02-26 | 6 | 6 | Framing Material | From Home Depot - Zip System Tape | 1329.71 | 0 | 1329.71 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10271 | NA | Credit Card | RIW-CFR-06-054
2025-03-05 | 6 | 6 | Framing Material | From Home Depot - Hex Nut | 90.75 | 0 | 90.75 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10278 | NA | Credit Card | RIW-CFR-06-055
2025-03-05 | 6 | 6 | Framing Material | From Home Depot - Het Nut and Washer | 51.9 | 0 | 51.9 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10279 | NA | Credit Card | RIW-CFR-06-056
2025-02-26 | 6 | 6 | Framing Material | From Office Depot - Truss Layout Pages | 40.85 | 0 | 40.85 |  |  |  | Framing Material | Office Depot | Owner (JP) AMEX | 10290 | NA | Credit Card | RIW-CFR-06-057
2025-01-16 | 6 | 6 | Framing Material | From Home Depot - Hex Nut and Dimensional Lumber | 1938.43 | 0 | 1938.43 |  |  |  | Framing Material | Home Depot | Jaimin Uncle | 10328 | NA | Credit Card | RIW-CFR-06-058
2025-01-20 | 6 | 6 | Framing Material | From Home Depot - Sheathing and Strand Board | 8551.62 | 0 | 8551.62 |  |  |  | Framing Material | Home Depot | Jaimin Uncle | 10298 | NA | Credit Card | RIW-CFR-06-059
2025-01-24 | 6 | 6 | Framing Material | From Home Depot - OSB Subfloor | 3384.41 | 0 | 3384.41 |  |  |  | Framing Material | Home Depot | Jaimin Uncle | 10299 | NA | Credit Card | RIW-CFR-06-060
2025-01-29 | 6 | 6 | Framing Material | From Home Depot - Simpson Strong-Ties | 1400.76 | 0 | 1400.76 |  |  |  | Framing Material | Home Depot | Jaimin Uncle | 10300 | NA | Credit Card | RIW-CFR-06-061
2025-02-04 | 6 | 6 | Framing Material | From Home Depot - LVL | 570.46 | 0 | 570.46 |  |  |  | Framing Material | Home Depot | Jaimin Uncle | 10301 | NA | Credit Card | RIW-CFR-06-062
2025-02-07 | 6 | 6 | Framing Material | From Home Depot - Standard and Treated Lumber | 2871.09 | 0 | 2871.09 |  |  |  | Framing Material | Home Depot | Jaimin Uncle | 10327 | NA | Credit Card | RIW-CFR-06-063
2025-02-12 | 6 | 6 | Framing Material | From Home Depot - OSB Subfloor | 2538.31 | 0 | 2538.31 |  |  |  | Framing Material | Home Depot | Jaimin Uncle | 10302 | NA | Credit Card | RIW-CFR-06-064
2025-02-19 | 6 | 6 | Framing Material | From Home Depot - Hurricane Ties | 1185.12 | 0 | 1185.12 |  |  |  | Framing Material | Home Depot | Jaimin Uncle | 10303 | NA | Credit Card | RIW-CFR-06-065
2025-02-27 | 6 | 6 | Framing Material | From Home Depot - Washer/Nuts, Strong Ties, Flashing Tape | 2792.31 | 0 | 2792.31 |  |  |  | Framing Material | Home Depot | Jaimin Uncle | 10304 | NA | Credit Card | RIW-CFR-06-066
2025-03-04 | 6 | 6 | Framing Material | From Home Depot - Anchor Bolts and Epoxy | 9937.53 | 0 | 9937.53 |  |  |  | Framing Material | Home Depot | Jaimin Uncle | 10305 | NA | Credit Card | RIW-CFR-06-067
2025-03-05 | 6 | 6 | Framing Material | From Home Depot - Sheathing and Dimensional Lumber | 5549.41 | 0 | 5549.41 |  |  |  | Framing Material | Home Depot | Jaimin Uncle | 10329 | NA | Credit Card | RIW-CFR-06-068
2025-02-03 | 6 | 6 | Framing Labor | For Reytex Framing Corporation - Invoice 14 | 5400 | 540 | 4860 |  |  |  | Framing Labor | Reytex Framing Corporation | RI Waxahachie | 10322 | Yes | Check | RIW-CFR-06-069
2025-02-08 | 6 | 6 | Framing Labor | For Reytex Framing Corporation - Revised Invoice 15 | 6380 | 638 | 5742 |  |  |  | Framing Labor | Reytex Framing Corporation | RI Waxahachie | 10323 | Yes | Check | RIW-CFR-06-070
2025-02-18 | 6 | 6 | Framing Labor | For Reytex Framing Corporation - Revised Invoice 17 | 4333.33 | 433.333 | 3899.997 |  |  |  | Framing Labor | Reytex Framing Corporation | RI Waxahachie | 10324 | Yes | Check | RIW-CFR-06-071
2025-03-03 | 6 | 6 | Framing Labor | For Reytex Framing Corporation - Invoice 18 | 4500 | 450 | 4050 |  |  |  | Framing Labor | Reytex Framing Corporation | RI Waxahachie | 10325 | No | Check | RIW-CFR-06-072
2025-03-10 | 6 | 6 | Framing Labor | For Reytex Framing Corporation - Invoice 19 (Partial Payment) | 4500 | 450 | 4050 |  |  |  | Framing Labor | Reytex Framing Corporation | RI Waxahachie | 10326 | Yes | Check | RIW-CFR-06-073
| 6 | 6 | Framing - Equipment | EquipmentShare | 18343.82 | 0 | 18343.82 |  |  |  | Framing Material | EquipmentShare |  | 10340 | NA |  | RIW-CFR-06-074
2025-03-11 | 6 | 7 | Framing Material | From Home Depot - Common Nails and Sheathing | 203.36 | 0 | 203.36 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10360 | NA | Credit Card | RIW-CFR-06-075
2025-03-13 | 6 | 7 | Framing Material | From Home Depot - Sheathing, Panel, and Step Stone | 105.18 | 0 | 105.18 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10361 | NA | Credit Card | RIW-CFR-06-076
2025-03-27 | 6 | 7 | Framing Material | From Home Depot - Window Sealant and Cutting Saws | 844.92 | 0 | 844.92 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10368 | NA | Credit Card | RIW-CFR-06-077
2025-04-01 | 6 | 7 | Framing Material | From Home Depot - Zip Tape | 880.72 | 0 | 880.72 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10370 | NA | Credit Card | RIW-CFR-06-078
2025-03-26 | 6 | 7 | Framing Material | From Home Depot - Joist Hanger | 108.94 | 0 | 108.94 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10371 | NA | Credit Card | RIW-CFR-06-079
2025-03-26 | 6 | 7 | Framing Material | From Home Depot - Hurricane Ties | 89.85 | 0 | 89.85 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10372 | NA | Credit Card | RIW-CFR-06-080
2025-03-19 | 6 | 7 | Framing Material | From Home Depot - Strong Ties, Hex Nuts, and Washers | 1255.09 | 0 | 1255.09 |  |  |  | Framing Material | Home Depot | Jaimin Uncle | 10403 | NA | Credit Card | RIW-CFR-06-081
2025-03-24 | 6 | 7 | Framing Material | From Home Depot - Dimensional Lumber | 1606.15 | 0 | 1606.15 |  |  |  | Framing Material | Home Depot | Jaimin Uncle | 10404 | NA | Credit Card | RIW-CFR-06-082
2025-04-01 | 6 | 7 | Framing Material | From Home Depot - Dimensional Lumber | 1972.62 | 0 | 1972.62 |  |  |  | Framing Material | Home Depot | Jaimin Uncle | 10405 | NA | Credit Card | RIW-CFR-06-083
2025-03-17 | 6 | 7 | Framing Labor | For Reytex Framing Corporation - Invoice 20 | 3500 | 350 | 3150 |  |  |  | Framing Labor | Reytex Framing Corporation | RI Waxahachie | 10399 | No | Check | RIW-CFR-06-084
2025-04-01 | 6 | 7 | Framing Labor | For Reytex Framing Corporation - Invoice 21/22 | 8500 | 850 | 7650 |  |  |  | Framing Labor | Reytex Framing Corporation | RI Waxahachie | 10400 | No | Check | RIW-CFR-06-085
2025-04-08 | 6 | 7 | Framing Labor | For Reytex Framing Corporation - Invoice 23 | 4475 | 447.5 | 4027.5 |  |  |  | Framing Labor | Reytex Framing Corporation | RI Waxahachie | 10406 | Yes | Check | RIW-CFR-06-086
2025-04-09 | 6 | 8 | Framing Material | From Home Depot - Hold Downs and Strong Ties | 5102.78 | 0 | 5102.78 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10417 | NA | Credit Card | RIW-CFR-06-087
2025-04-07 | 6 | 8 | Framing Material | From Home Depot - Drill Bit, Hex Nuts, and Washer | 138.99 | 0 | 138.99 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10414 | NA | Credit Card | RIW-CFR-06-088
2025-04-08 | 6 | 8 | Framing Material | From Home Depot - Nailing Hammer, Zip Tape, Extension Cord, Shovel | 253.74 | 0 | 253.74 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10415 | NA | Credit Card | RIW-CFR-06-089
2025-04-10 | 6 | 8 | Framing Material | From Home Depot - Washer, Hex Nuts, Bolts, Cooler | 130.66 | 0 | 130.66 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10420 | NA | Credit Card | RIW-CFR-06-090
2025-04-14 | 6 | 8 | Framing Material | From Home Depot - Washer, Hex Nuts, Rods | 912.43 | 0 | 912.43 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10413 | NA | Credit Card | RIW-CFR-06-091
2025-04-17 | 6 | 8 | Framing Material | From Home Depot - Hex Nuts | 70.74 | 0 | 70.74 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10412 | NA | Credit Card | RIW-CFR-06-092
2025-04-23 | 6 | 8 | Framing Material | From Home Depot - Zip Tape | 880.72 | 0 | 880.72 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10428 | NA | Credit Card | RIW-CFR-06-093
2025-04-25 | 6 | 8 | Framing Material | From Home Depot - Zip Tape | 535.3 | 0 | 535.3 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10429 | NA | Credit Card | RIW-CFR-06-094
2025-04-30 | 6 | 8 | Framing Material | From Home Depot - Zip Tape | 2159.56 | 0 | 2159.56 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10449 | NA | Credit Card | RIW-CFR-06-095
2025-05-01 | 6 | 8 | Truss Material - Dog Houses | From American Truss - 50% Deposit | 5405.4 | 0 | 5405.4 |  |  |  | Trusses | American Truss | Owner (JP) AMEX | 10450 | NA | Credit Card | RIW-CFR-06-096
2025-04-14 | 6 | 8 | Framing Labor | For Reytex Framing Corporation - Invoice 24 | 3000 | 300 | 2700 |  |  |  | Framing Labor | Reytex Framing Corporation | RI Waxahachie | 10431 | Yes | Check | RIW-CFR-06-097
2025-04-21 | 6 | 8 | Framing Labor | For Reytex Framing Corporation - Invoice 25 | 2800 | 280 | 2520 |  |  |  | Framing Labor | Reytex Framing Corporation | RI Waxahachie | 10432 | No | Check | RIW-CFR-06-098
2025-04-30 | 6 | 8 | Framing Labor | For Reytex Framing Corporation - Invoice 26 | 8100 | 810 | 7290 |  |  |  | Framing Labor | Reytex Framing Corporation | RI Waxahachie | 10441 | Yes | Check | RIW-CFR-06-099
2025-05-06 | 6 | 9 | Framing Material | From Home Depot - Lumber | 5499.57 | 0 | 5499.57 |  |  |  | Framing Material | Home Depot | Owner (JP) AMEX | 10457 | NA | Credit Card | RIW-CFR-06-100
2025-05-08 | 6 | 9 | Framing Material | From Home Depot - Hurricane Ties | 71.88 | 0 | 71.88 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10471 | NA | Credit Card | RIW-CFR-06-101
2025-05-09 | 6 | 9 | Framing Material | From Home Depot - Washers and Screws | 168.13 | 0 | 168.13 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10472 | NA | Credit Card | RIW-CFR-06-102
2025-05-13 | 6 | 9 | Framing Material | From Home Depot - Screws | 86.45 | 0 | 86.45 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10478 | NA | Credit Card | RIW-CFR-06-103
2025-05-15 | 6 | 9 | Framing Material | From Home Depot - Lumber | 1445.87 | 0 | 1445.87 |  |  |  | Framing Material | Home Depot | Owner (JP) AMEX | 10496 | NA | Credit Card | RIW-CFR-06-104
2025-05-15 | 6 | 9 | Framing Material | From Home Depot - Zip Tape | 749.41 | 0 | 749.41 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10497 | NA | Credit Card | RIW-CFR-06-105
2025-05-16 | 6 | 9 | Framing Material | From Home Depot - Zip Tape | 440.36 | 0 | 440.36 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10495 | NA | Credit Card | RIW-CFR-06-106
2025-05-19 | 6 | 9 | Framing Material | From Home Depot - OSB Subfloor | 1476.7 | 0 | 1476.7 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10502 | NA | Credit Card | RIW-CFR-06-107
2025-05-19 | 6 | 9 | Framing Labor | For Reytex Framing Corporation - Invoice 28 | 17275 | 1725.5 | 15549.5 |  |  |  | Framing Labor | Reytex Framing Corporation | RI Waxahachie | 10511 | No | Check | RIW-CFR-06-108
2025-05-26 | 6 | 9 | Framing Material | From Home Depot - RigidLam | 5129.91 | 0 | 5129.91 |  |  |  | Framing Material | Home Depot | Owner (JP) AMEX | 10512 | NA | Credit Card | RIW-CFR-06-109
2025-05-23 | 6 | 9 | Framing Material | From Home Depot - Hurricane Ties | 522.85 | 0 | 522.85 |  |  |  | Framing Material | Home Depot | Owner (JP) AMEX | 10518 | NA | Credit Card | RIW-CFR-06-110
2025-04-03 | 6 | 9 | Framing Material | From Home Depot - Lumber | 1801.97 | 0 | 1801.97 |  |  |  | Framing Material | Home Depot | Owner (JP) AMEX | 10519 | NA | Credit Card | RIW-CFR-06-111
2025-05-05 | 6 | 9 | Truss Material - Dog Houses | From American Truss - Remaining Payment | 5405.4 | 0 | 5405.4 |  |  |  | Trusses | American Truss | Owner (JP) AMEX | 10450 | NA | Credit Card | RIW-CFR-06-112
2025-05-28 | 6 | 10 | Framing Material | From Home Depot - Plastic Coated Framing Nails | 154.1 | 0 | 154.1 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10571 | NA | Credit Card | RIW-CFR-06-113
2025-05-29 | 6 | 10 | Framing Material | From Home Depot - Plastic Coated Framing Nails/Liquid Nails | 414.53 | 0 | 414.53 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10574 | NA | Credit Card | RIW-CFR-06-114
2025-05-29 | 6 | 10 | Framing Material | From Home Depot - Saw Blad/Dimensional Lumber | 79.07 | 0 | 79.07 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10573 | NA | Credit Card | RIW-CFR-06-115
2025-05-29 | 6 | 10 | Framing Material | From Home Depot - Utility Knife | 49.62 | 0 | 49.62 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10572 | NA | Credit Card | RIW-CFR-06-116
2025-05-30 | 6 | 10 | Framing Material | From Home Depot - Wood Dolly | 86.54 | 0 | 86.54 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10586 | NA | Credit Card | RIW-CFR-06-117
2025-05-31 | 6 | 10 | Framing Material | From Home Depot - Anchor/Hex Drive/Drill Bit/Cut Washer | 57.11 | 0 | 57.11 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10559 | NA | Credit Card | RIW-CFR-06-118
2025-05-31 | 6 | 10 | Framing Material | From Home Depot - Marking Paint for Trusses | 21.61 | 0 | 21.61 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10567 | NA | Credit Card | RIW-CFR-06-119
2025-06-04 | 6 | 10 | Framing Material | From Home Depot - Drill Bit/Screw/Dimensional Lumber | 217.21 | 0 | 217.21 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10575 | NA | Credit Card | RIW-CFR-06-120
2025-06-05 | 6 | 10 | Framing Material | From Home Depot - Dimensional Lumber/Spray Paint | 283.81 | 0 | 283.81 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10576 | NA | Credit Card | RIW-CFR-06-121
2025-06-13 | 6 | 10 | Framing Material | From Home Depot - Cedar Lumber/Wood Screw | 88.07 | 0 | 88.07 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10546 | NA | Credit Card | RIW-CFR-06-122
2025-06-07 | 6 | 10 | Framing Material | From Home Depot - Dimensional Lumber | 2305.64 | 0 | 2305.64 |  |  |  | Framing Material | Home Depot | Jaimin AMEX | 10542 | NA | Credit Card | RIW-CFR-06-123
2025-06-13 | 6 | 10 | Framing Material | From Home Depot - OSB Subfloor | 22.56 | 0 | 22.56 |  |  |  | Framing Material | Home Depot | Jaimin AMEX | 10543 | NA | Credit Card | RIW-CFR-06-124
2025-06-13 | 6 | 10 | Framing Material | From Lowe's | 167.33 | 0 | 167.33 |  |  |  | Framing Material | Lowe's | Jaimin AMEX | 10544 | NA | Credit Card | RIW-CFR-06-125
2025-06-11 | 6 | 10 | Framing Labor | For Reytex Framing Corporation - Truss Change Order | 3500 | 0 | 3500 |  |  |  | Framing Labor | Reytex Framing Corporation | RI Waxahachie | 10555 | No | Check | RIW-CFR-06-126
2025-06-16 | 6 | 10 | Framing Material | From Home Depot - Wood Screws & Lag Screws | 453.03 | 0 | 453.03 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10598 | NA | Credit Card | RIW-CFR-06-127
2025-06-16 | 6 | 10 | Framing Material | From Home Depot - Drywall Screws | 105.98 | 0 | 105.98 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10599 | NA | Credit Card | RIW-CFR-06-128
2025-06-17 | 6 | 10 | Framing Material | From Home Depot - Lag Screws | 87.28 | 0 | 87.28 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10606 | NA | Credit Card | RIW-CFR-06-129
2025-06-25 | 6 | 10 | Framing Labor | For Reytex Framing Corporation - Invoice 30 | 2610 | 261 | 2349 |  |  |  | Framing Labor | Reytex Framing Corporation | RI Waxahachie | 10594 | No | Check | RIW-CFR-06-130
2025-06-25 | 6 | 10 | Framing Material | From Home Depot - Galvanized Joist Hanger | 64.08 | 0 | 64.08 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10607 | NA | Credit Card | RIW-CFR-06-131
2025-06-26 | 6 | 10 | Framing Material | From Home Depot - OSB Wall Sheathing | 346.51 | 0 | 346.51 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10608 | NA | Credit Card | RIW-CFR-06-132
2025-06-27 | 6 | 10 | Framing Material | From Home Depot - OSB Wall Sheathing & Ratcheting Suspension | 627.88 | 0 | 627.88 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10609 | NA | Credit Card | RIW-CFR-06-133
2025-06-13 | 6 | 10 | Framing Material | From Harbor Freight | 397.23 | 0 | 397.23 |  |  |  | Framing Material | Harbor Freight | Jaimin AMEX | [TBD] | NA | Credit Card | RIW-CFR-06-134
2025-07-21 | 6 | 10 | Framing and Trusses Labor | From RFM Ventures | 15680 | 1568 | 14112 |  |  |  | Framing Labor | RFM Ventures | RI Waxahachie | 10674 | Yes | ACH | RIW-CFR-06-135
2025-07-18 | 6 | 11 | Framing Material | From Home Depot - Washers | 43.75 | 0 | 43.75 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10689 | NA | Credit Card | RIW-CFR-06-136
2025-07-15 | 6 | 11 | Framing Material | From Home Depot - Loose Lumber | 3604.86 | 0 | 3604.86 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10690 | NA | Credit Card | RIW-CFR-06-137
2025-07-15 | 6 | 11 | Framing Material | From Home Depot - Loose Lumber | 4059.6 | 0 | 4059.6 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10683 | NA | Credit Card | RIW-CFR-06-138
2025-07-15 | 6 | 11 | Framing Material | From Home Depot - Hex Nut, Washers, and Threaded Rods | 315.58 | 0 | 315.58 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10684 | NA | Credit Card | RIW-CFR-06-139
2025-07-17 | 6 | 11 | Framing Material | From Home Depot - Simpson Hold Downs | 4367.94 | 0 | 4367.94 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10685 | NA | Credit Card | RIW-CFR-06-140
2025-07-17 | 6 | 11 | Framing Material | From Home Depot - Washers | 291.41 | 0 | 291.41 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10686 | NA | Credit Card | RIW-CFR-06-141
2025-07-18 | 6 | 11 | Framing Material | From Home Depot - Loose Lumber | 2151.4 | 0 | 2151.4 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10687 | NA | Credit Card | RIW-CFR-06-142
2025-06-04 | 6 | 11 | Framing Material | From Home Depot - Sheathing and Loose Lumber | 3064.86 | 0 | 3064.86 |  |  |  | Framing Material | Home Depot | Jaimin AMEX | 10623 | NA | Credit Card | RIW-CFR-06-143
2025-06-04 | 6 | 11 | Framing Material | From Home Depot - Galvanized Nuts | 903.62 | 0 | 903.62 |  |  |  | Framing Material | Home Depot | Jaimin AMEX | 10624 | NA | Credit Card | RIW-CFR-06-144
2025-06-18 | 6 | 11 | Framing Material | From Home Depot - Loose Lumber | 243.13 | 0 | 243.13 |  |  |  | Framing Material | Home Depot | Jaimin AMEX | 10626 | NA | Credit Card | RIW-CFR-06-145
2025-07-07 | 6 | 11 | Framing Labor | For Reytex Framing Corporation - Invoice 32 | 1700 | 170 | 1530 |  |  |  | Framing Labor | Reytex Framing Corporation | RI Waxahachie | 10665 | No | Check | RIW-CFR-06-146
2025-07-09 | 6 | 11 | Framing Material | For Reytex Framing Corporation - Material Reimbursement | 350 | 0 | 350 |  |  |  | Framing Material | Reytex Framing Corporation | RI Waxahachie | 10667 | Yes | Check | RIW-CFR-06-147
2025-07-07 | 6 | 11 | Framing Material | From Home Depot - Zip Tape | 440.36 | 0 | 440.36 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10654 | NA | Credit Card | RIW-CFR-06-148
2025-07-07 | 6 | 11 | Framing Material | From Home Depot - Framing Nails | 133.36 | 0 | 133.36 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10656 | NA | Credit Card | RIW-CFR-06-149
2025-07-08 | 6 | 11 | Framing Material | From Home Depot - Zip Tape | 440.36 | 0 | 440.36 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10655 | NA | Credit Card | RIW-CFR-06-150
2025-07-21 | 6 | 11 | Framing Labor - Hardware | For Martin Aguilar | 3000 | 0 | 3000 |  |  |  | Framing Labor | Martin Aguilar | RI Waxahachie | 10680 | NA | Check | RIW-CFR-06-151
2025-05-27 | 6 | 11 | Framing Material | From Home Depot - Liquid Nails | 1047.9 | 0 | 1047.9 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10569 | NA | Credit Card | RIW-CFR-06-152
2025-07-21 | 6 | 11 | Framing Material | From Home Depot - LVL and Hold Downs | 2576.56 | 0 | 2576.56 |  |  |  | Framing Material | Home Depot | Jaimin AMEX | 10688 | NA | Credit Card | RIW-CFR-06-153
2025-07-25 | 6 | 11 | Framing Material | From Home Depot - LVL and Hold Downs (Refund) | -1389.44 | 0 | -1389.44 |  |  |  | Framing Material | Home Depot | Jaimin AMEX | 10688 | NA | Credit Card | RIW-CFR-06-154
2025-07-07 | 6 | 11 | Framing Labor | For Reytex Framing Corporation - Invoice 33 | 3508 | 350.98 | 3157.02 |  |  |  | Framing Labor | Reytex Framing Corporation | RI Waxahachie | 10666 | Yes | Check | RIW-CFR-06-155
2025-07-10 | 6 | 11 | Framing Material | From Home Depot - OSB Subfloor | 1360.11 | 0 | 1360.11 |  |  |  | Framing Material | Home Depot | Jaimin AMEX | 10713 | NA | Credit Card | RIW-CFR-06-156
2025-07-10 | 6 | 11 | Framing Material | From Home Depot - OSB Subfloor | -1360.11 | 0 | -1360.11 |  |  |  | Framing Material | Home Depot | Jaimin AMEX | 10713 | NA | Credit Card | RIW-CFR-06-157
2025-07-10 | 6 | 11 | Framing Material | From Home Depot - OSB Subfloor | 1360.11 | 0 | 1360.11 |  |  |  | Framing Material | Home Depot | Jaimin AMEX | 10713 | NA | Credit Card | RIW-CFR-06-158
2025-07-29 | 6 | 11 | Framing Material | From Home Depot - Dimensional Lumber/Flashing Tape/Wall & Roof Panel | 2379.3 | 0 | 2379.3 |  |  |  | Framing Material | Home Depot | Jaimin AMEX | 10725 | NA | Credit Card | RIW-CFR-06-159
2025-07-30 | 6 | 12 | Framing Labor - Hardware | For Martin Aguilar | 8550 | 0 | 8550 |  |  |  | Framing Labor | Martin Aguilar | RI Waxahachie | 10802 | NA | Check | RIW-CFR-06-160
2025-08-08 | 6 | 12 | Framing Labor - Misc. Punch List | For Martin Aguilar | 13436.9 | 0 | 13436.9 |  |  |  | Framing Labor | Martin Aguilar | RI Waxahachie | 10803 | NA | Check | RIW-CFR-06-161
2025-05-27 | 6 | 12 | Travel for Truss Engineer - Inspection | From Expedia | 417.97 | 0 | 417.97 |  |  |  | Trusses | Expedia | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-06-162
2025-05-27 | 6 | 12 | Travel for Truss Engineer - Inspection | From Expedia | 34.11 | 0 | 34.11 |  |  |  | Trusses | Expedia | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-06-163
2025-05-28 | 6 | 12 | Travel for Truss Engineer - Inspection | From Expedia | 201.4 | 0 | 201.4 |  |  |  | Trusses | Expedia | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-06-164
2025-08-18 | 6 | 12 | Framing Material | From Home Depot - OSB Subfloor & Dimensional Lumber | 738.52 | 0 | 738.52 |  |  |  | Framing Material | Home Depot | Jaimin AMEX | 10808 | NA | Credit Card | RIW-CFR-06-165
2025-08-20 | 6 | 12 | Framing Material | From Home Depot - Ratchet & Screws | 916.78 | 0 | 916.78 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10809 | NA | Credit Card | RIW-CFR-06-166
2025-08-20 | 6 | 12 | Framing Material | From Home Depot - Zinc & Galvanized Screws | 405.1 | 0 | 405.1 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10811 | NA | Credit Card | RIW-CFR-06-167
2025-03-05 | 6 | 12 | Framing Material | From Home Depot - Galvanized Washer | 85.19 | 0 | 85.19 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10830 | NA | Credit Card | RIW-CFR-06-168
2025-07-31 | 6 | 12 | Framing Material | From Home Depot - Galvanised Hex Nut, Carriage Bolt, Drill Bit, Washer | 271.51 | 0 | 271.51 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10782 | NA | Credit Card | RIW-CFR-06-169
2025-07-31 | 6 | 12 | Framing Material | From Home Depot - Sheathing Panel | 1653.28 | 0 | 1653.28 |  |  |  | Framing Material | Home Depot | Jaimin AMEX | 10783 | NA | Credit Card | RIW-CFR-06-170
2025-08-01 | 6 | 12 | Framing Material | From Home Depot - Southern Yellow Pine Dimensional Lumber | 321.77 | 0 | 321.77 |  |  |  | Framing Material | Home Depot | Jaimin AMEX | 10784 | NA | Credit Card | RIW-CFR-06-171
2025-08-04 | 6 | 12 | Framing Material | From Home Depot - Adhesive, Retrofit Bolt, Standoff Post and Post Cap | 749.21 | 0 | 749.21 |  |  |  | Framing Material | Home Depot | Jaimin AMEX | 10785 | NA | Credit Card | RIW-CFR-06-172
2025-08-06 | 6 | 12 | Framing Material | From Home Depot - Exterior Wall Sheathing | 135.31 | 0 | 135.31 |  |  |  | Framing Material | Home Depot | Jaimin AMEX | 10787 | NA | Credit Card | RIW-CFR-06-173
2025-08-06 | 6 | 12 | Framing Material | From Home Depot - Pressure Treated Timber Wood Post and Lumber | 622.81 | 0 | 622.81 |  |  |  | Framing Material | Home Depot | Jaimin AMEX | 10788 | NA | Credit Card | RIW-CFR-06-174
2025-07-28 | 6 | 12 | Framing Material | From Home Depot - Loose Lumber Refund | -1863.84 | 0 | -1863.84 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10687 | NA | Credit Card | RIW-CFR-06-175
[Confirm] | 6 | 12 | Millwork 50% Deposit | From Graniti Vicentia LLC | 52002.26 | 0 | 52002.26 |  |  |  | Public Area Millwork Material | Graniti Vicentia | [Confirm] | 10857 | NA | [Confirm] | RIW-CFR-06-176
2025-08-22 | 6 | 12 | Framing Labor - Misc. Punch List | For Martin Aguilar | 4450 | 0 | 4450 |  |  |  | Framing Labor | Martin Aguilar | RI Waxahachie | 10858 | NA | Check | RIW-CFR-06-177
2025-09-19 | 6 | 13 | Framing Labor - Hardware | For Martin Aguilar | 7145 | 0 | 7145 |  |  |  | Framing Labor | Martin Aguilar | Boulder | 10890 | NA | Check | RIW-CFR-06-178
2025-09-02 | 6 | 13 | Framing Labor - Hardware | For Martin Aguilar | 2000 | 0 | 2000 |  |  |  | Framing Labor | Martin Aguilar | Boulder | 10891 | NA | Check | RIW-CFR-06-179
2025-08-20 | 6 | 13 | Framing Material | From Harbor Freight - Ladders | 649.46 | 0 | 649.46 |  |  |  | Framing Material | Harbor Freight | Boulder AMEX | 10925 | NA | Credit Card | RIW-CFR-06-180
2025-08-20 | 6 | 13 | Framing Material | From Harbor Freight - Safety Stand, Wrench, Screws | 247.83 | 0 | 247.83 |  |  |  | Framing Material | Harbor Freight | Boulder AMEX | 10926 | NA | Credit Card | RIW-CFR-06-181
2025-08-25 | 6 | 13 | Framing Material | From Home Depot - OSB Subfloor and Pine Dimensional Lumber | 516.89 | 0 | 516.89 |  |  |  | Framing Material | Home Depot | Jaimin AMEX | 10867 | NA | Credit Card | RIW-CFR-06-182
2025-09-05 | 6 | 13 | Framing Material | From Home Depot - Framing Nails & Dimensional Lumber | 253.06 | 0 | 253.06 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10868 | NA | Credit Card | RIW-CFR-06-183
2025-09-11 | 6 | 13 | Framing Material | From Home Depot - Dimensional Lumber | 2273.94 | 0 | 2273.94 |  |  |  | Framing Material | Home Depot | Jaimin AMEX | 10869 | NA | Credit Card | RIW-CFR-06-184
2025-09-12 | 6 | 13 | Framing Material | From Home Depot - Galvanized Bolts, Standoff Post Base and Adhesive | 121.8 | 0 | 121.8 |  |  |  | Framing Material | Home Depot | Jaimin AMEX | 10874 | NA | Credit Card | RIW-CFR-06-185
2025-09-19 | 6 | 13 | Framing Material | From Home Depot - OSB Subfloor | 617.35 | 0 | 617.35 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10878 | NA | Credit Card | RIW-CFR-06-186
2025-09-15 | 6 | 13 | Framing Material | From Home Depot - Washer & Hex Nut | 161.54 | 0 | 161.54 |  |  |  | Framing Material | Home Depot | Jaimin AMEX | 10887 | NA | Credit Card | RIW-CFR-06-187
2025-08-20 | 6 | 13 | Framing Log + Verification | For Truss and Framing Corrections | 1500 | 0 | 1500 |  |  |  | Framing Labor | Krish Patel | [To Be Confirmed] | 10837 | No | ACH | RIW-CFR-06-188
2025-09-23 | 6 | 14 | Framing Material | From Home Depot - Shackle, Slide Lock & Zinc Thread | 127.97 | 0 | 127.97 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 10957 | NA | Credit Card | RIW-CFR-06-189
2025-10-02 | 6 | 14 | Framing Material | From Home Depot -Simpson Epoxy Adhesive & Retro-Fit Bolt | 3281.06 | 0 | 3281.06 |  |  |  | Framing Material | Home Depot | Jaimin AMEX | 10978 | NA | Credit Card | RIW-CFR-06-190
2025-10-03 | 6 | 14 | Framing Material | From Home Depot -Simpson Epoxy Adhesive & Retro-Fit Bolt Refund | -2137.94 | 0 | -2137.94 |  |  |  | Framing Material | Home Depot | Jaimin AMEX | 10978 | NA | Credit Card | RIW-CFR-06-191
2025-10-09 | 6 | 14 | Framing Material | From Home Depot - Dimensional Lumber | 203.85 | 0 | 203.85 |  |  |  | Framing Material | Home Depot | Jaimin AMEX | 10981 | NA | Credit Card | RIW-CFR-06-192
2025-10-15 | 6 | 14 | Framing Material | From Home Depot - Dimensional Lumber | 596.28 | 0 | 596.28 |  |  |  | Framing Material | Home Depot | Jaimin AMEX | 10984 | NA | Credit Card | RIW-CFR-06-193
2025-10-06 | 6 | 14 | Framing Labor - Hardware | For Martin Aguilar | 2150 | 0 | 2150 |  |  |  | Framing Labor | Martin Aguilar | RI Waxahachie | 11009 | NA | Check | RIW-CFR-06-194
2025-10-27 | 6 | 14 | Framing Labor - Misc. Punch List | For Martin Aguilar | 3695 | 0 | 3695 |  |  |  | Framing Labor | Martin Aguilar | RI Waxahachie | 11010 | NA | Check | RIW-CFR-06-195
2025-10-22 | 6 | 14 | Framing Material | From Home Depot - Exterior Wall Sheathing | 1053.27 | 0 | 1053.27 |  |  |  | Framing Material | Home Depot | Jaimin AMEX | 11030 | NA | Credit Card | RIW-CFR-06-196
2025-10-28 | 6 | 14 | Framing Material | From Home Depot - Dimensional Lumber | 586.5 | 0 | 586.5 |  |  |  | Framing Material | Home Depot | Jaimin AMEX | 11031 | NA | Credit Card | RIW-CFR-06-197
2025-10-25 | 6 | 14 | Framing Material | From Home Depot - Galvanized Screw | 124.3 | 0 | 124.3 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 11037 | NA | Credit Card | RIW-CFR-06-198
2025-11-24 | 6 | 15 | Framing Material | From Home Depot - Dimensional Lumber | 274.74 | 0 | 274.74 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 11100 | NA | Credit Card | RIW-CFR-06-199
2025-11-25 | 6 | 15 | Framing Material | From Home Depot - Prime KD Whitewood Stud & Sheathing Material | 325.56 | 0 | 325.56 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 11104 | NA | Credit Card | RIW-CFR-06-200
2025-11-25 | 6 | 15 | Framing Material | From Home Depot - Thread Coated Exterior Wood Screws & Cutting Tool-Kit | 128.37 | 0 | 128.37 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 11105 | NA | Credit Card | RIW-CFR-06-201
2025-12-01 | 6 | 15 | Framing Material | From Home Depot - Standard Grade Dimensional Lumber | 2084.98 | 0 | 2084.98 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 11109 | NA | Credit Card | RIW-CFR-06-202
2025-12-01 | 6 | 15 | Framing Material | From Home Depot - Southern Yellow Pine Lumber | 869.12 | 0 | 869.12 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 11110 | NA | Credit Card | RIW-CFR-06-203
2025-12-01 | 6 | 15 | Framing Material | From Home Depot - Glue Collated Straight Finish Nails | 100.46 | 0 | 100.46 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 11111 | NA | Credit Card | RIW-CFR-06-204
2025-12-05 | 6 | 15 | Framing Material | From Home Depot - Sheathing Material & Heavy Duty Glove | 211.09 | 0 | 211.09 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 11118 | NA | Credit Card | RIW-CFR-06-205
2025-11-10 | 6 | 15 | Framing Labor - Misc. Punch List | For Martin Aguilar | 7200 | 0 | 7200 |  |  |  | Framing Labor | Martin Aguilar | RI Waxahachie | 11137 | NA | Check | RIW-CFR-06-206
2025-12-03 | 6 | 15 | Framing Labor - Misc. Punch List | For Martin Aguilar | 7000 | 0 | 7000 |  |  |  | Framing Labor | Martin Aguilar | RI Waxahachie | 11138 | NA | Check | RIW-CFR-06-207
2025-12-19 | 6 | 15 | Framing Labor - Misc. Punch List | For Martin Aguilar | 800 | 0 | 800 |  |  |  | Framing Labor | Martin Aguilar | RI Waxahachie | 11157 | NA | Check | RIW-CFR-06-208
2025-12-30 | 6 | 15 | Framing Labor - Misc. Punch List | For Martin Aguilar | 600 | 0 | 600 |  |  |  | Framing Labor | Martin Aguilar | RI Waxahachie | 11221 | NA | Check | RIW-CFR-06-209
2026-01-26 | 6 | 16 | Millwork 50% Final Payment | From Graniti Vicentia | 43357.31 | 0 | 43357.31 |  |  |  | Public Area Millwork Material | Graniti Vicentia | Jaimin AMEX | 10857 | NA | Credit Card | RIW-CFR-06-210
2025-12-30 | 6 | 16 | Framing Material | From Home Depot - Galvanized Lag Screw | 98.11 | 0 | 98.11 |  |  |  | Framing Material | Home Depot | Boulder AMEX | 11264 | NA | Credit Card | RIW-CFR-06-211
2026-01-12 | 6 | 16 | Framing Labor - Misc. Punch List | For Martin Aguilar | 3425 | 0 | 3425 |  |  |  | Framing Labor | Martin Aguilar | RI Waxahachie | 12177 | NA | Check | RIW-CFR-06-212
7. Thermal and Moisture Protection
| 7 | 5 | Draw 5 Funds |  |  |  |  | 150000 | 15000 | 135000
| 7 | 6 | Draw 6 Funds - Reimbursements |  |  |  |  | 255 | 0 | 255
| 7 | 6 | Draw 6 Funds - To Be Paid |  |  |  |  | 25000 | 2500 | 22500
| 7 | 7 | Draw 7 Funds - Reimbursements |  |  |  |  | 14914.9 | 0 | 14914.9
| 7 | 7 | Draw 7 Funds - To Be Paid |  |  |  |  | 45452.21 | 4000 | 41452.21
| 7 | 8 | Draw 8 Funds - Reimbursements |  |  |  |  | 13195.92 | 0 | 13195.92
| 7 | 8 | Draw 8 Funds - To Be Paid |  |  |  |  | 95149.11 | 9000 | 86149.11
| 7 | 9 | Draw 9 Funds - Reimbursements |  |  |  |  | 20668.82 | 0 | 20668.82
| 7 | 9 | Draw 9 Funds - To Be Paid |  |  |  |  | 95715.18 | 10545.93 | 85169.25
| 7 | 10 | Draw 10 Funds - Reimbursements |  |  |  |  | 34345.57 | 0 | 34345.57
| 7 | 10 | Draw 10 Funds - To Be Paid |  |  |  |  | 72008.22 | 4900 | 67108.22
| 7 | 11 | Draw 11 Funds - Reimbursements |  |  |  |  | 4581.13 | 0 | 4581.13
| 7 | 11 | Draw 11 Funds - To Be Paid |  |  |  |  | 97040.55 | 9446.6 | 87593.95
| 7 | 12 | Draw 12 Funds - Reimbursements |  |  |  |  | 35169.8267 | 3333.3333 | 31836.4933
| 7 | 12 | Draw 12 Funds - To Be Paid |  |  |  |  | 35413.0267 | 3198.9177 | 32214.109
| 7 | 13 | Draw 13 Funds - Reimbursements |  |  |  |  | 342 | 0 | 342
| 7 | 13 | Draw 13 Funds - To Be Paid |  |  |  |  | 127574.55 | 12500 | 115074.55
| 7 | 14 | Draw 14 Funds - Reimbursements |  |  |  |  | 30000 | 500 | 29500
| 7 | 14 | Draw 14 Funds - To Be Paid |  |  |  |  | 15074.55 | 1249.999 | 13824.551
| 7 | 15 | Draw 15 Funds - Reimbursements |  |  |  |  | 22302.48 | 2000 | 20302.48
| 7 | 16 | Draw 16 Funds - Reimbursements |  |  |  |  | 9857.1222 | 985.7122 | 8871.41
| 7 | 16 | Draw 16 Funds - To Be Paid |  |  |  |  | 27483 | 600 | 26883
| 7 | 17 | Draw 17 Funds - Reimbursements |  |  |  |  | 6087.23 | 0 | 6087.23
| 7 | 17 | Draw 17 Funds - To Be Paid |  |  |  |  | 16800 | 1680 | 15120
2025-03-11 | 7 | 5 | Roofing Material and Labor | First Invoice - LED Roofing | 150000 | 15000 | 135000 |  |  |  | Roofing | LED Roofing | RI Waxahachie | 10347 | Yes | Check | RIW-CFR-07-001
2025-02-18 | 7 | 6 | Corridor Insulation Inspection | From Geoscience Engineers | 255 | 0 | 255 |  |  |  | Building Insulation | Geoscience Engineers | Owner (JP) AMEX | 10285 | NA | Credit Card | RIW-CFR-07-002
2025-03-24 | 7 | 6 | Prerock / Insulation for Top of Corridor | RFM Ventures - First Invoice | 25000 | 2500 | 22500 |  |  |  | Building Insulation | RFM Ventures | RI Waxahachie | 10341 | Yes | Check | RIW-CFR-07-003
2025-03-13 | 7 | 7 | Stucco Material | From Imperial Wallboard Supply - HFP, Basecoat, Washers | 14914.9 | 0 | 14914.9 |  |  |  | EFIS/Stone | Imperial Wallboard Supply | Owner (JP) AMEX | 10385 | NA | Credit Card | RIW-CFR-07-004
2025-04-15 | 7 | 7 | Stucco Labor Rough | From VG Stucco - First Invoice | 40000 | 4000 | 36000 |  |  |  | EFIS/Stone | VG Stucco | RI Waxahachie | 10433 | Yes | Check | RIW-CFR-07-005
2025-05-02 | 7 | 7 | EFIS/Stone - Equipment | EquipmentShare | 5452.21 | 0 | 5452.21 |  |  |  | EFIS/Stone | EquipmentShare | RI Waxahachie | 10442 | NA | [TBD] | RIW-CFR-07-006
2025-04-22 | 7 | 8 | Stucco Material | From Red River Brick | 10327.72 | 0 | 10327.72 |  |  |  | EFIS/Stone | General Shale | Owner (JP) AMEX | 10426 | NA | Credit Card | RIW-CFR-07-007
2025-04-25 | 7 | 8 | Stucco/Stone Material | From Red River Brick | 2868.2 | 0 | 2868.2 |  |  |  | EFIS/Stone | General Shale | Owner (JP) AMEX | 10490 | NA | Credit Card | RIW-CFR-07-008
2025-05-22 | 7 | 8 | Stucco Rough and Finish Labor | From VG Stucco - Pay App 02 (First Payment) | 78000 | 7800 | 70200 |  |  |  | EFIS/Stone | VG Stucco | RI Waxahachie | 10506 | Yes | Check | RIW-CFR-07-009
2025-06-03 | 7 | 8 | Stucco Rough and Finish Labor | From VG Stucco - Pay App 02 (Second Payment) | 12000 | 1200 | 10800 |  |  |  | EFIS/Stone | VG Stucco | RI Waxahachie | 10506 | Yes | ACH | RIW-CFR-07-010
2025-05-28 | 7 | 8 | EFIS/Stone - Equipment | EquipmentShare | 5149.11 | 0 | 5149.11 |  |  |  | EFIS/Stone | EquipmentShare | RI Waxahachie | 10516 | NA |  | RIW-CFR-07-011
2025-05-02 | 7 | 9 | Stucco/Stone Material | From Red River Brick | 2110.87 | 0 | 2110.87 |  |  |  | EFIS/Stone | General Shale | Owner (JP) AMEX | 10489 | NA | Credit Card | RIW-CFR-07-012
2025-05-08 | 7 | 9 | Stucco/Stone Material | From Red River Brick | 1112 | 0 | 1112 |  |  |  | EFIS/Stone | General Shale | Owner (JP) AMEX | 10482 | NA | Credit Card | RIW-CFR-07-013
2025-05-15 | 7 | 9 | Stucco/Stone Material | From Red River Brick | 10766.54 | 0 | 10766.54 |  |  |  | EFIS/Stone | General Shale | Owner (JP) AMEX | 10488 | NA | Credit Card | RIW-CFR-07-014
2025-05-15 | 7 | 9 | Stucco/Stone Material | From Silicone Specialities - EFIS Mesh/Adhesive | 4643.93 | 0 | 4643.93 |  |  |  | EFIS/Stone | Silicone Specialities | Owner (JP) AMEX | 10494 | NA | Credit Card | RIW-CFR-07-015
2025-05-22 | 7 | 9 | Stucco/Stone Material | From Red River Brick | 2035.48 | 0 | 2035.48 |  |  |  | EFIS/Stone | General Shale | Owner (JP) AMEX | 10513 | NA | Credit Card | RIW-CFR-07-016
2025-05-28 | 7 | 9 | Stucco/Stone Material | From Silicone Specialities - Dryvit Pastel & Sikaflex | 6976.73 | 0 | 6976.73 |  |  |  | EFIS/Stone | Silicone Specialities | Jaimin AMEX | 10520 | NA | Credit Card | RIW-CFR-07-017
2025-06-18 | 7 | 9 | EFIS/Stone - Equipment | From Triple A Stucco | 12384 | 1238.4 | 11145.6 |  |  |  | EFIS/Stone | Triple A Stucco | RI Waxahachie | 10523 | Yes | ACH | RIW-CFR-07-018
2025-06-19 | 7 | 9 | Stucco Rough and Finish Labor | From VG Stucco - Pay App 03 (First Payment) | 56941.0571 | 6941.0571 | 50000 |  |  |  | EFIS/Stone | VG Stucco | RI Waxahachie | 10578 | Yes | ACH | RIW-CFR-07-019
2025-07-07 | 7 | 9 | Stucco Rough and Finish Labor | From VG Stucco - Pay App 03 (Second Payment) | 19413.3929 | 2366.4729 | 17046.92 |  |  |  | EFIS/Stone | VG Stucco | RI Waxahachie | 10578 | No | ACH | RIW-CFR-07-020
2025-06-13 | 7 | 10 | Stucco/Stone Material | From Silicone Specialities - Lath Paper & Sikaflex Cartridge | 1261.11 | 0 | 1261.11 |  |  |  | EFIS/Stone | Silicone Specialities | Boulder AMEX | 10547 | NA | Credit Card | RIW-CFR-07-021
2025-06-02 | 7 | 10 | Stucco/Stone Material | From Red River Brick (Return) | -270.62 | 0 | -270.62 |  |  |  | EFIS/Stone | General Shale | Jaimin AMEX | [TBD] | NA | Credit Card | RIW-CFR-07-022
2025-06-03 | 7 | 10 | Stucco/Stone Material | From Red River Brick | 10495.92 | 0 | 10495.92 |  |  |  | EFIS/Stone | General Shale | Jaimin AMEX | 10541 | NA | Credit Card | RIW-CFR-07-023
2025-06-04 | 7 | 10 | Stucco/Stone Material | From Red River Brick | 2029.69 | 0 | 2029.69 |  |  |  | EFIS/Stone | General Shale | Jaimin AMEX | 10618 | NA | Credit Card | RIW-CFR-07-024
2025-06-04 | 7 | 10 | Stucco/Stone Material | From Red River Brick | 1635.66 | 0 | 1635.66 |  |  |  | EFIS/Stone | General Shale | Jaimin AMEX | 10619 | NA | Credit Card | RIW-CFR-07-025
2025-06-04 | 7 | 10 | Stucco/Stone Material | From Red River Brick | 1461.38 | 0 | 1461.38 |  |  |  | EFIS/Stone | General Shale | Jaimin AMEX | 10620 | NA | Credit Card | RIW-CFR-07-026
2025-06-12 | 7 | 10 | Stucco/Stone Material | From Red River Brick | 10495.92 | 0 | 10495.92 |  |  |  | EFIS/Stone | General Shale | Jaimin AMEX | 10621 | NA | Credit Card | RIW-CFR-07-027
2025-06-18 | 7 | 10 | Stucco/Stone Material | From Red River Brick | 7236.51 | 0 | 7236.51 |  |  |  | EFIS/Stone | General Shale | Jaimin AMEX | 10622 | NA | Credit Card | RIW-CFR-07-028
2025-06-30 | 7 | 10 | Stucco/Stone Material | From Red River Brick | 10495.92 | 0 | 10495.92 |  |  |  | EFIS/Stone | General Shale | Jaimin AMEX | 10640 | NA | Credit Card | RIW-CFR-07-029
2025-06-27 | 7 | 10 | Stucco/Stone Material | From Red River Brick | 1198.64 | 0 | 1198.64 |  |  |  | EFIS/Stone | General Shale | Jaimin AMEX | 10627 | NA | Credit Card | RIW-CFR-07-030
2025-06-30 | 7 | 10 | Stucco/Stone Material | From Silicone Specialities | 776.02 | 0 | 776.02 |  |  |  | EFIS/Stone | Silicone Specialities | Jaimin AMEX | 10616 | NA | Credit Card | RIW-CFR-07-031
2025-07-21 | 7 | 10 | Stucco/Stone Material | From VG Stucco - Pay App 04 (First Payment) | 22222.22 | 2222.222 | 19999.998 |  |  |  | EFIS/Stone | VG Stucco | RI Waxahachie | 10617 | Yes | ACH | RIW-CFR-07-032
2025-07-31 | 7 | 10 | Stucco/Stone Material | From VG Stucco - Pay App 04 (Second Payment) | 26777.78 | 2677.778 | 24100.002 |  |  |  | EFIS/Stone | VG Stucco | RI Waxahachie | 10617 | Yes | ACH | RIW-CFR-07-033
2025-07-18 | 7 | 10 | EFIS/Stone - Equipment | EquipmentShare | 10537.64 | 0 | 10537.64 |  |  |  | EFIS/Stone | EquipmentShare | RI Waxahachie | 10672 | NA | Wire | RIW-CFR-07-034
2025-06-25 | 7 | 11 | Stucco/Stone Material | From Silicone Specialities - Pay App 05 | -0.01 | 0 | -0.01 |  |  |  | EFIS/Stone | Silicone Specialities | Jaimin AMEX | 10717 | NA | Credit Card | RIW-CFR-07-035
2025-07-08 | 7 | 11 | Stucco/Stone Material | From Silicone Specialities - Pay App 05 | 1103.07 | 0 | 1103.07 |  |  |  | EFIS/Stone | Silicone Specialities | Jaimin AMEX | 10716 | NA | Credit Card | RIW-CFR-07-036
2025-07-29 | 7 | 11 | Stucco/Stone Material | From Red River Brick - VG Stucco - Pay App 05 | 3478.07 | 0 | 3478.07 |  |  |  | EFIS/Stone | General Shale | Jaimin AMEX | 10724 | NA | Credit Card | RIW-CFR-07-037
2025-08-18 | 7 | 11 | EFIS/Stone - Equipment | EquipmentShare | 2574.55 | 0 | 2574.55 |  |  |  | EFIS/Stone | EquipmentShare | RI Waxahachie | 10726 | NA | ACH | RIW-CFR-07-038
2025-08-21 | 7 | 11 | Second Invoice - Change Orders | From LED Roofing | 47100 | 4710 | 42390 |  |  |  | Roofing | LED Roofing | RI Waxahachie | 10729 | No | Check | RIW-CFR-07-039
2025-08-21 | 7 | 11 | Stucco/Stone Material | From VG Stucco - Pay App 05 (First Payment) | 35000 | 3500 | 31500 |  |  |  | EFIS/Stone | VG Stucco | RI Waxahachie | 10730 | No | ACH | RIW-CFR-07-040
2025-08-29 | 7 | 11 | Stucco/Stone Material | From VG Stucco - Pay App 05 (Second Payment) | 12366 | 1236.6 | 11129.4 |  |  |  | EFIS/Stone | VG Stucco | RI Waxahachie | 10730 | No | ACH | RIW-CFR-07-041
2025-08-04 | 7 | 12 | Stucco/Stone Material | From Silicone Specialities - VG Stucco - Pay App 06 | 753.42 | 0 | 753.42 |  |  |  | EFIS/Stone | Silicone Specialities | Jaimin AMEX | 10777 | NA | Credit Card | RIW-CFR-07-042
2025-09-18 | 7 | 12 | Stucco/Stone Material | From VG Stucco - Pay App 06 (First Payment) | 11046.65 | 1046.65 | 10000 |  |  |  | EFIS/Stone | VG Stucco | RI Waxahachie | 10848 | No | ACH | RIW-CFR-07-043
2025-10-14 | 7 | 12 | Stucco/Stone Material | From VG Stucco - Pay App 06 (Final Payment) | 5125.16 | 485.6 | 4639.56 |  |  |  | EFIS/Stone | VG Stucco | RI Waxahachie | 10848 | No | ACH | RIW-CFR-07-044
2025-08-29 | 7 | 12 | Insulation for Ceiling / Interior Wall / Corridor | RFM Ventures - Third Invoice (First Payment) | 33333.3333 | 3333.3333 | 30000 |  |  |  | Building Insulation | RFM Ventures | RI Waxahachie | 10847 | No | ACH | RIW-CFR-07-045
2025-09-15 | 7 | 12 | Insulation for Ceiling / Interior Wall / Corridor | RFM Ventures - Third Invoice (Final Payment) | 16666.6667 | 1666.6667 | 15000 |  |  |  | Building Insulation | RFM Ventures | RI Waxahachie | 10847 | No | ACH | RIW-CFR-07-046
2025-09-23 | 7 | 12 | EFIS/Stone - Equipment | EquipmentShare | 2574.55 | 0 | 2574.55 |  |  |  | EFIS/Stone | EquipmentShare | RI Waxahachie | 10849 | NA | ACH | RIW-CFR-07-047
2025-08-20 | 7 | 12 | Labor & Gas for Generators | From J&S7 Consulting | 1083.0733 | 0 | 1083.0733 |  |  |  | EFIS/Stone | J&S7 Consulting | Boulder | 10833 | NA | Check | RIW-CFR-07-048
2025-08-25 | 7 | 13 | Insulation Inspection | Geoscience Engineers | 342 | 0 | 342 |  |  |  | Building Insulation | Geoscience Engineers | Jaimin AMEX | 10829 | NA | Credit Card | RIW-CFR-07-049
2025-10-21 | 7 | 13 | Final Invoice | From LED Roofing | 100000 | 10000 | 90000 |  |  |  | Roofing | LED Roofing | RI Waxahachie | 10927 | No | Check | RIW-CFR-07-050
2025-10-17 | 7 | 13 | Insulation for Floor 4 | RFM Ventures - Fourth Invoice | 25000 | 2500 | 22500 |  |  |  | Building Insulation | RFM Ventures | RI Waxahachie | 10932 | No | ACH | RIW-CFR-07-051
2025-11-07 | 7 | 13 | EFIS/Stone - Equipment | EquipmentShare | 2574.55 | 0 | 2574.55 |  |  |  | EFIS/Stone | EquipmentShare | RI Waxahachie | 10935 | NA | Direct Pay | RIW-CFR-07-052
2025-11-05 | 7 | 14 | EFIS Payment - Change Order for Stone Columns | From VG Stucco - Pay App 07 (First Payment) | 5000 | 500 | 4500 |  |  |  | EFIS/Stone | VG Stucco | RI Waxahachie | 11061 | No | Check | RIW-CFR-07-053
2025-11-05 | 7 | 14 | EFIS Payment | From VG Stucco - Pay App 07 (Final Payment) | 25000 | 0 | 25000 |  |  |  | EFIS/Stone | VG Stucco | RI Waxahachie | 11061 | No | Check | RIW-CFR-07-054
2025-11-17 | 7 | 14 | Insulation for Floor 1 | From RFM Ventures - Pay App 06 | 12500 | 1250 | 11250 |  |  |  | Building Insulation | RFM Ventures | RI Waxahachie | 11050 | No | ACH | RIW-CFR-07-055
2025-12-09 | 7 | 14 | EFIS/Stone - Equipment | From EquipmentShare | 2574.55 | 0 | 2574.55 |  |  |  | EFIS/Stone | EquipmentShare | RI Waxahachie | 11055 | NA | Direct Pay | RIW-CFR-07-056
2025-12-03 | 7 | 15 | EFIS | From VG Stucco | 5000 | 500 | 4500 |  |  |  | EFIS/Stone | VG Stucco | RI Waxahachie | 11139 | No | ACH | RIW-CFR-07-057
2025-11-24 | 7 | 15 | EFIS | From VG Stucco | 5000 | 500 | 4500 |  |  |  | EFIS/Stone | VG Stucco | Boulder | 11145 | No | Check | RIW-CFR-07-058
2025-12-11 | 7 | 15 | EIFS Mesh, Dryvit Sandblast & Adhesive, Portland Cement | From Silicone Specialities Inc | 2302.48 | 0 | 2302.48 |  |  |  | EFIS/Stone | Silicone Specialities Inc | Boulder AMEX | 11150 | NA | Credit Card | RIW-CFR-07-059
2025-12-15 | 7 | 15 | EFIS | From VG Stucco | 5000 | 500 | 4500 |  |  |  | EFIS/Stone | VG Stucco | RI Waxahachie | 11158 | No | Check | RIW-CFR-07-060
2025-12-24 | 7 | 15 | EFIS | From VG Stucco | 5000 | 500 | 4500 |  |  |  | EFIS/Stone | VG Stucco | RI Waxahachie | 11211 | No | Check | RIW-CFR-07-061
2026-01-20 | 7 | 16 | EFIS | From VG Stucco - Pay App 09 | 9857.1222 | 985.7122 | 8871.41 |  |  |  | EFIS/Stone | VG Stucco | RI Waxahachie | 12178 | No | ACH | RIW-CFR-07-062
[To Be Paid] | 7 | 16 | EFIS | From VG Stucco - Pay App 10 | 27483 | 600 | 26883 |  |  |  | EFIS/Stone | VG Stucco | [To Be Paid] | 12188 | NA | [To Be Paid] | RIW-CFR-07-063
2026-02-11 | 7 | 17 | Stone Material | From Metro Brick & Stone | 909.82 | 0 | 909.82 |  |  |  | EFIS/Stone | Metro Brick & Stone | Jaimin AMEX | 12312 | NA | Credit Card
2026-02-10 | 7 | 17 | Window Cleaning & Back Fixes | From VG Stucco | 4000 | 0 | 4000 |  |  |  | EFIS/Stone | VG Stucco | RI Waxahachie | 12469 | Yes | Check
2026-01-20 | 7 | 17 | Stone Material | From Metro Brick & Stone | 722.5 | 0 | 722.5 |  |  |  | EFIS/Stone | Metro Brick & Stone | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-24 | 7 | 17 | Stone Material | From Metro Brick & Stone | 454.91 | 0 | 454.91 |  |  |  | EFIS/Stone | Metro Brick & Stone | Jaimin AMEX | [TBD] | NA | Credit Card
[To Be Paid] | 7 | 17 | EFIS Material | From VG Stucco - Pay App 11 | 16800 | 1680 | 15120 |  |  |  | EFIS/Stone | VG Stucco | [To Be Paid] | [TBD] | No | [To Be Paid]
8. Openings
| 8 | 1 | Draw 1 Funds |  |  |  |  | 50500 | 0 | 50500
| 8 | 3 | Draw 3 Funds |  |  |  |  | 34534.21 | 0 | 34534.21
| 8 | 4 | Draw 4 Funds |  |  |  |  | 30327 | 0 | 30327
| 8 | 5 | Draw 5 Funds |  |  |  |  | 93145.33 | 0 | 93145.33
| 8 | 6 | Draw 6 Funds - Reimbursement |  |  |  |  | 33120 | 0 | 33120
| 8 | 6 | Draw 6 Funds - To Be Paid |  |  |  |  | 81524.67 | 0 | 81524.67
| 8 | 9 | Draw 9 Funds - To Be Paid |  |  |  |  | 98376.6 | 0 | 98376.6
| 8 | 10 | Draw 10 Funds - To Be Paid |  |  |  |  | 12000 | 0 | 12000
| 8 | 12 | Draw 12 Funds - Reimbursement |  |  |  |  | 20200 | 0 | 20200
| 8 | 14 | Draw 14 Funds - Reimbursement |  |  |  |  | 11526.07 | 0 | 11526.07
| 8 | 15 | Draw 15 Funds - Reimbursement |  |  |  |  | 45647.1 | 0 | 45647.1
| 8 | 16 | Draw 16 Funds - Reimbursement |  |  |  |  | 6219.5 | 0 | 6219.5
| 8 | 16 | Draw 16 Funds - To Be Paid |  |  |  |  | 500 | 0 | 500
| 8 | 17 | Draw 17 Funds - Reimbursement |  |  |  |  | 151929.52 | 1887.5 | 150042.02
| 8 | 17 | Draw 17 Funds - To Be Paid |  |  |  |  | 15500 | 0 | 15500
2024-11-05 | 8 | 1/3 | Window Deposit | For Top Bright Windows and Door | 85034.21 | 0 | 85034.21 |  |  |  | Guest Room Windows | Top Bright Windows and Doors | Jaimin Uncle |  | NA |  | RIW-CFR-08-001
2025-01-27 | 8 | 4 | Onity Locks | 65% Deposit (For Discount) | 30327 | 0 | 30327 |  |  |  | Electronic Locksets | Onity | RI Waxahachie | 10218 | NA | Wire Transfer | RIW-CFR-08-002
2025-03-10 | 8 | 5 | Window Deposit - Second Payment | For Top Bright Windows and Door | 36604.21 | 0 | 36604.21 |  |  |  | Guest Room Windows | Top Bright Windows and Doors | Boulder | 10296 | NA | Wire Transfer | RIW-CFR-08-003
2025-02-25 | 8 | 5 | Window Deposit - Third Payment | For Top Bright Windows and Door | 56541.12 | 0 | 56541.12 |  |  |  | Guest Room Windows | Top Bright Windows and Doors | RI Waxahachie | 10297 | NA | Wire Transfer | RIW-CFR-08-004
2025-03-06 | 8 | 6 | Deposit for Doors | For Ongoing Windows & Doors | 8280 | 0 | 8280 |  |  |  | Doors and Hardware | Ongoing Windows & Doors | Owner (JP) AMEX | 10291 | NA | Credit Card | RIW-CFR-08-005
2025-03-06 | 8 | 6 | Deposit for Doors | For Ongoing Windows & Doors | 8280 | 0 | 8280 |  |  |  | Doors and Hardware | Ongoing Windows & Doors | Owner (JP) AMEX | 10292 | NA | Credit Card | RIW-CFR-08-006
2025-03-06 | 8 | 6 | Deposit for Doors | For Ongoing Windows & Doors | 8280 | 0 | 8280 |  |  |  | Doors and Hardware | Ongoing Windows & Doors | Owner (JP) AMEX | 10293 | NA | Credit Card | RIW-CFR-08-007
2025-03-06 | 8 | 6 | Deposit for Doors | For Ongoing Windows & Doors | 8280 | 0 | 8280 |  |  |  | Doors and Hardware | Ongoing Windows & Doors | Owner (JP) AMEX | 10294 | NA | Credit Card | RIW-CFR-08-008
2025-04-02 | 8 | 6 | Additional Deposit for Doors | For Ongoing Windows & Doors | 32935.4 | 0 | 32935.4 |  |  |  | Doors and Hardware | Ongoing Windows & Doors | RI Waxahachie | 10343 | NA | Wire Transfer | RIW-CFR-08-009
| 8 | 6 | Order Windows | For Top Bright Windows and Door - Additional Deposit | 48589.27 | 0 | 48589.27 |  |  |  | Guest Room Windows | Top Bright Windows and Doors | RI Waxahachie | 10342 | NA | Wire Transfer | RIW-CFR-08-010
2025-06-20 | 8 | 9 | Additional Deposit for Doors | For Ongoing Windows & Doors | 98376.6 | 0 | 98376.6 |  |  |  | Doors and Hardware | Ongoing Windows & Doors | RI Waxahachie | 10582 | Yes | Wire | RIW-CFR-08-011
2025-06-30 | 8 | 10 | Windows Installation | From GW Glass Construction | 12000 | 0 | 12000 |  |  |  | Guest Room Windows | GW Glass Construction | Jaimin AMEX | 10596 | NA | Credit Card | RIW-CFR-08-012
2025-08-29 | 8 | 12 | Windows Installation | From GW Glass Construction | 12000 | 0 | 12000 |  |  |  | Guest Room Windows | GW Glass Construction | Jaimin AMEX | 10855 | NA | [Confirm] | RIW-CFR-08-013
2025-08-29 | 8 | 12 | Windows Installation | From GW Glass Construction | 8200 | 0 | 8200 |  |  |  | Guest Room Windows | GW Glass Construction | Jaimin AMEX | 10856 | NA | [Confirm] | RIW-CFR-08-014
2025-10-09 | 8 | 14 | Windows Fixes | From Bryant Construction | 11474.5 | 0 | 11474.5 |  |  |  | Guest Room Windows | Bryant Construction | RI Waxahachie | 10997 | NA | ACH | RIW-CFR-08-015
2025-11-01 | 8 | 14 | Doors Material | From Home Depot - Commercial Grade with Ball Bearing & Butt Door Hinge | 51.57 | 0 | 51.57 |  |  |  | Doors and Hardware | Home Depot | Boulder AMEX | 11041 | NA | Credit Card | RIW-CFR-08-016
2025-12-04 | 8 | 15 | Windows Installation Labor | From GW Glass Construction | 7000 | 0 | 7000 |  |  |  | Guest Room Windows | GW Glass Construction | Jaimin AMEX | 11098 | NA | Credit Card | RIW-CFR-08-017
2025-12-19 | 8 | 15 | Doors and Hardware | From WB Doors | 3415.29 | 0 | 3415.29 |  |  |  | Doors and Hardware | William Brothers | Boulder AMEX | 11161 | NA | Credit Card | RIW-CFR-08-018
2025-12-15 | 8 | 15 | Doors and Hardware | From Home Depot - Flush Right Hand Inswing Steel Prehung Front Door | 231.81 | 0 | 231.81 |  |  |  | Doors and Hardware | Home Depot | Boulder AMEX | 11187 | NA | Credit Card | RIW-CFR-08-019
2026-01-15 | 8 | 15 | Door Install Labor | From TKG Construction | 35000 | 0 | 35000 |  |  |  | Doors and Hardware | TKG Construction | RI Waxahachie | 12175 | No | ACH | RIW-CFR-08-020
2025-12-29 | 8 | 16 | Doors Labor | From JR Construction | 2725 | 0 | 2725 |  |  |  | Doors and Hardware | JR Construction | RI Waxahachie | 12196 | NA | ACH | RIW-CFR-08-021
2026-01-20 | 8 | 16 | Door Material | From Home Depot - Ballbearing Door Hinge | 79.21 | 0 | 79.21 |  |  |  | Doors and Hardware | Home Depot | Boulder AMEX | 12200 | NA | Credit Card | RIW-CFR-08-022
2025-12-19 | 8 | 16 | Access Panels For Dog Houses | From WB Doors | 3415.29 | 0 | 3415.29 |  |  |  | Doors and Hardware | WB Doors | Boulder AMEX | 12310 | NA | Credit Card | RIW-CFR-08-023
2026-02-09 | 8 | 16 | Doors and Hardware Install | From TKG Construction | 500 | 0 | 500 |  |  |  | Doors and Hardware | TKG Construction | RI Waxahachie | 11285 | No | ACH | RIW-CFR-08-024
2026-02-25 | 8 | 17 | Door Material | From Home Depot - Door Lock Installation Saw Set | 57.26 | 0 | 57.26 |  |  |  | Doors and Hardware | Home Depot | Boulder AMEX | 12455 | NA | Credit Card
2026-03-02 | 8 | 17 | Electronic Locksets | From Onity | 28640.68 | 0 | 28640.68 |  |  |  | Electronic Locksets | Onity | RI Waxahachie | 12468 | NA | ACH
2026-02-26 | 8 | 17 | Door Material | From Home Depot - Aluminium Channel | 59.06 | 0 | 59.06 |  |  |  | Doors and Hardware | Home Depot | Boulder AMEX | 12500 | NA | Credit Card
2026-03-03 | 8 | 17 | Windows Installation Labor | From GW Glass Construction | 5450 | 0 | 5450 |  |  |  | Guest Room Windows | GW Glass Construction | Jaimin AMEX | 12524 | NA | Credit Card
2026-02-05 | 8 | 17 | Closers | From Amazon | 3195.74 | 0 | 3195.74 |  |  |  | Doors and Hardware | Amazon | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-06 | 8 | 17 | Locks | From Amazon | 1106.67 | 0 | 1106.67 |  |  |  | Doors and Hardware | Amazon | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-08 | 8 | 17 | Window Stops | From Amazon | 582.2 | 0 | 582.2 |  |  |  | Guest Room Windows | Amazon | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-10 | 8 | 17 | Passage Locks | From Amazon | 416.5 | 0 | 416.5 |  |  |  | Doors and Hardware | Amazon | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-17 | 8 | 17 | Door Hardware | From Amazon | 1375.68 | 0 | 1375.68 |  |  |  | Doors and Hardware | Amazon | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-17 | 8 | 17 | Door Hinge Pins | From Amazon | 136.35 | 0 | 136.35 |  |  |  | Doors and Hardware | Amazon | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-19 | 8 | 17 | Passage Locks | From Amazon | 1332.8 | 0 | 1332.8 |  |  |  | Doors and Hardware | Amazon | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-19 | 8 | 17 | Hinges | From Amazon | 272.76 | 0 | 272.76 |  |  |  | Doors and Hardware | Amazon | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-19 | 8 | 17 | Hinges | From Amazon | 248.96 | 0 | 248.96 |  |  |  | Doors and Hardware | Amazon | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-19 | 8 | 17 | Push / Pull | From Amazon | 84.36 | 0 | 84.36 |  |  |  | Doors and Hardware | Amazon | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-19 | 8 | 17 | Push / Pull | From Amazon | 28.12 | 0 | 28.12 |  |  |  | Doors and Hardware | Amazon | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-21 | 8 | 17 | Hinges | From Amazon | 470.67 | 0 | 470.67 |  |  |  | Doors and Hardware | Amazon | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-21 | 8 | 17 | Window Stops | From Amazon | 291.1 | 0 | 291.1 |  |  |  | Guest Room Windows | Amazon | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-24 | 8 | 17 | Dummy Locks | From Amazon | 108.14 | 0 | 108.14 |  |  |  | Doors and Hardware | Amazon | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-24 | 8 | 17 | Passage Locks | From Amazon | 91.91 | 0 | 91.91 |  |  |  | Doors and Hardware | Amazon | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-25 | 8 | 17 | Panic Bars | From Amazon | 1704.42 | 0 | 1704.42 |  |  |  | Doors and Hardware | Amazon | Boulder AMEX | [TBD] | NA | Credit Card
2026-03-01 | 8 | 17 | Automatic Door Bottom | From Amazon | 151.52 | 0 | 151.52 |  |  |  | Doors and Hardware | Amazon | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-23 | 8 | 17 | Doors Hardware | From DK Hardware | 388.5 | 0 | 388.5 |  |  |  | Doors and Hardware | DK Hardware | Boulder AMEX | [TBD] | NA | Credit Card
[To Be Paid] | 8 | 17 | Guest Room Doors | From TKG Construction - Pay App 11 | 1500 | 0 | 1500 |  |  |  | Guest Room Windows | TKG Construction | [To Be Paid] | [TBD] | No | [To Be Paid]
[To Be Paid] | 8 | 17 | Public Area Doors & Other Doors & Caulking | From TKG Construction - Pay App 11 | 14000 | 0 | 14000 |  |  |  | Doors and Hardware | TKG Construction | [To Be Paid] | [TBD] | No | [To Be Paid]
2026-02-20 | 8 | 17 | Labor And Diesel | From J&S7 Consulting | 2589 | 0 | 2589 |  |  |  | Metal Flashing | J&S7 Consulting | RI Waxahachie | 12314 | NA
2026-02-10 | 8 | 17 | Framing Material | From Lowes - Rough Cedar Lumber (2x4x12) | 3089.8 | 0 | 3089.8 |  |  |  | Metal Flashing | Lowes | Boulder AMEX | 12341 | NA | Credit Card
2026-02-10 | 8 | 17 | Framing Material | From Lowes - Framing Lumber And Fasteners | 5931.69 | 0 | 5931.69 |  |  |  | Metal Flashing | Lowes | Boulder AMEX | 12342 | NA | Credit Card
2026-02-20 | 8 | 17 | Parking Lot Striping And ADA Markings | From H&W Extreme Cleaning Solutions - Parking Lot Striping And ADA Markings | 8451.79 | 0 | 8451.79 |  |  |  | Metal Flashing | H&W Extreme Cleaning Solutions | Jaimin AMEX | 12343 | NA | Credit Card
2026-02-18 | 8 | 17 | Landscaping | From 4 Nature Landscape | 13500 | 0 | 13500 |  |  |  | Metal Flashing | 4 Nature Landscape | Jaimin AMEX | 12309 | NA
2026-02-19 | 8 | 17 | Elevator Engineering, Materials And Installation Labor | From KONE - Elevator Engineering, Materials And Installation Labor | 18875 | 1887.5 | 16987.5 |  |  |  | Metal Flashing | Kone | Boulder | 12313 | NA
2026-02-20 | 8 | 17 | Jobsite Labor | From J&S7 Consulting | 7735 | 0 | 7735 |  |  |  | Metal Flashing | J&S7 Consulting | RI Waxahachie | 12314 | NA
2026-02-18 | 8 | 17 | Final Cleaning | From Americo Concrete | 9620 | 0 | 9620 |  |  |  | Metal Flashing | Americo Concrete | RI Waxahachie | 12476 | Yes | Check
2026-03-03 | 8 | 17 | Landscaping | From 4 Nature Landscape | 10237.31 | 0 | 10237.31 |  |  |  | Metal Flashing | 4 Nature Landscape | Jaimin AMEX | 12521 | NA
2026-03-02 | 8 | 17 | Final Cleaning | From Americo Concrete | 9435 | 0 | 9435 |  |  |  | Metal Flashing | Americo Concrete | RI Waxahachie | 12483 | Yes | Check
2026-01-28 | 8 | 17 | Equipment Costs | From EquipmentShare | 16271.53 | 0 | 16271.53 |  |  |  | Metal Flashing | EquipmentShare | Boulder AMEX | [TBD] | NA | Credit Card
9. Finishes
| 9 | 7 | Draw 7 Funds - Reimbursements |  |  |  |  | 522.2 | 0 | 522.2
| 9 | 8 | Draw 8 Funds - To Be Paid |  |  |  |  | 13150 | 1315 | 11835
| 9 | 12 | Draw 12 Funds - Reimbursements |  |  |  |  | 5183.14 | 0 | 5183.14
| 9 | 12 | Draw 12 Funds - To Be Paid |  |  |  |  | 118000 | 11800 | 106200
| 9 | 13 | Draw 13 Funds - To Be Paid |  |  |  |  | 101000 | 10100 | 90900
| 9 | 14 | Draw 14 Funds - Reimbursements |  |  |  |  | 91094.45 | 3000 | 88094.45
| 9 | 14 | Draw 14 Funds - To Be Paid |  |  |  |  | 259000 | 25900 | 233100
| 9 | 15 | Draw 15 Funds - Reimbursements |  |  |  |  | 122124.5 | 7919.444 | 114205.056
| 9 | 15 | Draw 15 Funds - To Be Paid |  |  |  |  | 65805.56 | 6580.556 | 59225.004
| 9 | 16 | Draw 16 Funds - Reimbursements |  |  |  |  | 81400.41 | 0 | 81400.41
| 9 | 16 | Draw 16 Funds - To Be Paid |  |  |  |  | 41820 | 0 | 41820
| 9 | 17 | Draw 17 Funds - Reimbursements |  |  |  |  | 39800.31 | 0 | 39800.31
| 9 | 17 | Draw 17 Funds - To Be Paid |  |  |  |  | 28000 | 0 | 28000
2025-03-19 | 9 | 7 | Misc. Jobsite Materials | From Home Depot - Paint for Model Room | 197.45 | 0 | 197.45 |  |  |  | Painting | Home Depot | Boulder AMEX | 10364 | NA | Credit Card | RIW-CFR-09-001
2025-03-20 | 9 | 7 | Misc. Jobsite Materials | From Home Depot - Paint for Model Room | 90.06 | 0 | 90.06 |  |  |  | Painting | Home Depot | Boulder AMEX | 10365 | NA | Credit Card | RIW-CFR-09-002
2025-03-20 | 9 | 7 | Misc. Jobsite Materials | From Home Depot - Paint for Model Room | 234.69 | 0 | 234.69 |  |  |  | Painting | Home Depot | Boulder AMEX | 10366 | NA | Credit Card | RIW-CFR-09-003
2025-05-22 | 9 | 8 | Model Room Labor and Material | Change Order - RFM Ventures | 13150 | 1315 | 11835 |  |  |  | Model Room | RFM Ventures | RI Waxahachie | 10505 | Yes | Check | RIW-CFR-09-004
2025-08-20 | 9 | 12 | Drywall Material | From Home Depot - Drywall Screws & Tape | 161.75 | 0 | 161.75 |  |  |  | Drywall Material | Home Depot | Boulder AMEX | 10812 | NA | Credit Card | RIW-CFR-09-005
2025-08-21 | 9 | 12 | Drywall Material | From Home Depot - Knife, Tape, Pan, etc. | 198.23 | 0 | 198.23 |  |  |  | Drywall Material | Home Depot | Boulder AMEX | 10813 | NA | Credit Card | RIW-CFR-09-006
2025-08-21 | 9 | 12 | Drywall Material | From Home Depot - Drywall Joint Tape | 85.36 | 0 | 85.36 |  |  |  | Drywall Material | Home Depot | Boulder AMEX | 10814 | NA | Credit Card | RIW-CFR-09-007
2025-08-22 | 9 | 12 | Drywall Material | From Home Depot - Tarp, Knife, Shear & Tin Snip | 537.8 | 0 | 537.8 |  |  |  | Drywall Material | Home Depot | Boulder AMEX | 10815 | NA | Credit Card | RIW-CFR-09-008
2025-08-22 | 9 | 12 | Labor for Sheetrocking Elevator | From JG AU Drywall | 4200 | 0 | 4200 |  |  |  | Drywall Labor | JG AU Drywall | RI Waxahachie | 10841 | NA | Check | RIW-CFR-09-009
2025-09-15 | 9 | 12 | RC Channel & Sheetrocking for Walls, Celing, Corridor | RFM Ventures - Third Invoice (Final Payment) | 118000 | 11800 | 106200 |  |  |  | Drywall Material | RFM Ventures | RI Waxahachie | 10847 | No | ACH | RIW-CFR-09-010
2025-10-17 | 9 | 13 | RC Channel & Sheetrock for Floor 4 | RFM Ventures - Fourth Invoice | 59000 | 5900 | 53100 |  |  |  | Drywall Material | RFM Ventures | RI Waxahachie | 10932 | No | ACH | RIW-CFR-09-011
2025-10-17 | 9 | 13 | Texture & Tape/Bed/Sand for Floors 2/3 | RFM Ventures - Fourth Invoice | 42000 | 4200 | 37800 |  |  |  | Drywall Labor | RFM Ventures | RI Waxahachie | 10932 | No | ACH | RIW-CFR-09-012
2025-09-26 | 9 | 14 | Painting Material | From Home Depot - Interior Primer | 6321.8 | 0 | 6321.8 |  |  |  | Painting | Home Depot | Boulder AMEX | 10958 | NA | Credit Card | RIW-CFR-09-013
2025-10-02 | 9 | 14 | Paint Brush, Extension Cord, Waterproofer & Floor Fan | From Home Depot | 176.08 | 0 | 176.08 |  |  |  | Painting | Home Depot | Boulder AMEX | 10962 | NA | Credit Card | RIW-CFR-09-014
2025-10-02 | 9 | 14 | Interior Primer | From Home Depot | 6321.8 | 0 | 6321.8 |  |  |  | Painting | Home Depot | Boulder AMEX | 10963 | NA | Credit Card | RIW-CFR-09-015
2025-10-03 | 9 | 14 | Paint Brush & Waterproofer | From Home Depot | 39.45 | 0 | 39.45 |  |  |  | Painting | Home Depot | Boulder AMEX | 10964 | NA | Credit Card | RIW-CFR-09-016
2025-10-13 | 9 | 14 | Tile Leveling Clip and Cutters, Diamond Blade & Adhesive | From Home Depot | 616.65 | 0 | 616.65 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 10965 | NA | Credit Card | RIW-CFR-09-017
2025-10-13 | 9 | 14 | Tile Leveling Clip, Rim Blade with Mesh & Thinset Mortar | From Home Depot | 549.13 | 0 | 549.13 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 10966 | NA | Credit Card | RIW-CFR-09-018
2025-10-13 | 9 | 14 | Tile Leveling Clip & Contractor Bags | From Home Depot | 304.89 | 0 | 304.89 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 10967 | NA | Credit Card | RIW-CFR-09-019
2025-10-13 | 9 | 14 | Thinset Mortar | From Home Depot | 256.62 | 0 | 256.62 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 10968 | NA | Credit Card | RIW-CFR-09-020
2025-10-14 | 9 | 14 | Tile Leveling Clip, Lubricant Spray & Thinset Mortar | From Home Depot | 531.43 | 0 | 531.43 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 10969 | NA | Credit Card | RIW-CFR-09-021
2025-10-14 | 9 | 14 | Thinset Mortar | From Home Depot | 498.98 | 0 | 498.98 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 10970 | NA | Credit Card | RIW-CFR-09-022
2025-10-14 | 9 | 14 | Aluminium Reducer Tile Edging Trim | From Home Depot | 98.78 | 0 | 98.78 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 10971 | NA | Credit Card | RIW-CFR-09-023
2025-10-14 | 9 | 14 | Aluminium Reducer Tile Edging Trim Refund | From Home Depot | -98.78 | 0 | -98.78 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 10971 | NA | Credit Card | RIW-CFR-09-024
2025-10-14 | 9 | 14 | Flooring Material | From Home Depot - All Surface Construction Adhesive | 636.92 | 0 | 636.92 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 10972 | NA | Credit Card | RIW-CFR-09-025
2025-10-15 | 9 | 14 | Thinset Mortar & Contractor Bags | From Home Depot | 232.03 | 0 | 232.03 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 10973 | NA | Credit Card | RIW-CFR-09-026
2025-10-16 | 9 | 14 | Flooring Material | From Home Depot - Silicone Caulk & Gun, Diamond Blade, Painter's Towels | 612.85 | 0 | 612.85 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 10974 | NA | Credit Card | RIW-CFR-09-027
2025-10-16 | 9 | 14 | Drywall Material | From Home Depot - Drywall Screw | 22.98 | 0 | 22.98 |  |  |  | Drywall Material | Home Depot | Boulder AMEX | 10975 | NA | Credit Card | RIW-CFR-09-028
2025-10-17 | 9 | 14 | Flooring Material | From Home Depot - Premium Tile Diamond Blade | 68.55 | 0 | 68.55 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 10976 | NA | Credit Card | RIW-CFR-09-029
2025-10-20 | 9 | 14 | Thinset Mortar | From Home Depot | 498.98 | 0 | 498.98 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 10977 | NA | Credit Card | RIW-CFR-09-030
2025-10-14 | 9 | 14 | Flooring Material | From Home Depot - All Surface Construction Adhesive | 454.93 | 0 | 454.93 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 10980 | NA | Credit Card | RIW-CFR-09-031
2025-10-14 | 9 | 14 | Liquid Nails, Thinset Mortar, Tile Leveling Stems & Caps | From Home Depot | 1868.5 | 0 | 1868.5 |  |  |  | Flooring Material | Home Depot | Jaimin AMEX | 10982 | NA | Credit Card | RIW-CFR-09-032
2025-10-27 | 9 | 14 | Flooring Labor | From TKG Construction | 27180 | 0 | 27180 |  |  |  | Flooring Install | TKG Construction | RI Waxahachie | 11004 | NA | ACH | RIW-CFR-09-033
2025-10-24 | 9 | 14 | Flooring Material | From Home Depot - Heavy Duty Temporary Floor Protection | 913.68 | 0 | 913.68 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 11029 | NA | Credit Card | RIW-CFR-09-034
2025-10-28 | 9 | 14 | Thinset Mortar | From Home Depot | 498.98 | 0 | 498.98 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 11038 | NA | Credit Card | RIW-CFR-09-035
2025-10-30 | 9 | 14 | Painting Material | From Home Depot - Bi-Metal Hole Saw and Multi-Use Painter's Tape | 264.56 | 0 | 264.56 |  |  |  | Painting | Home Depot | Boulder AMEX | 11040 | NA | Credit Card | RIW-CFR-09-036
2025-11-01 | 9 | 14 | Self-Leveling Underlayment & Thinset Mortar | From Home Depot | 379.47 | 0 | 379.47 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 11042 | NA | Credit Card | RIW-CFR-09-037
2025-11-02 | 9 | 14 | Self-Leveling Underlayment & Spray Foam Sealant | From Home Depot | 502.97 | 0 | 502.97 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 11043 | NA | Credit Card | RIW-CFR-09-038
2025-10-20 | 9 | 14 | Flooring Material | From Floor & Décor | 1297.7 | 0 | 1297.7 |  |  |  | Flooring Material | Floor & Décor | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-09-039
2025-10-21 | 9 | 14 | Flooring Material | From Floor & Décor | 91.23 | 0 | 91.23 |  |  |  | Flooring Material | Floor & Décor | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-09-040
2025-10-27 | 9 | 14 | Flooring Material | From Floor & Décor | -64.89 | 0 | -64.89 |  |  |  | Flooring Material | Floor & Décor | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-09-041
2025-10-27 | 9 | 14 | Flooring Material | From Floor & Décor | 345.23 | 0 | 345.23 |  |  |  | Flooring Material | Floor & Décor | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-09-042
2025-10-06 | 9 | 14 | Paint Material | From PPG Paints | 9672.95 | 0 | 9672.95 |  |  |  | Painting | PPG Paints | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-09-043
2025-11-05 | 9 | 14 | Flooring Labor | From TKG Construction | 30000 | 3000 | 27000 |  |  |  | Flooring Install | TKG Construction | RI Waxahachie | 11004 | NA | ACH | RIW-CFR-09-044
2025-11-17 | 9 | 14 | RC Channel & Sheetrock for Floor 1 | From RFM Ventures - Pay App 05 | 59000 | 5900 | 53100 |  |  |  | Drywall Material | RFM Ventures | RI Waxahachie | 11050 | No | ACH | RIW-CFR-09-045
2025-11-17 | 9 | 14 | Texture & Tape/Bed/Sand for Floors 1 to 4 | From RFM Ventures - Pay App 05 | 66000 | 6600 | 59400 |  |  |  | Drywall Labor | RFM Ventures | RI Waxahachie | 11050 | No | ACH | RIW-CFR-09-046
2025-11-17 | 9 | 14 | Coat Heavy Primer 2 Coat Paint Floors 1 to 4 | From RFM Ventures - Pay App 05 | 90000 | 9000 | 81000 |  |  |  | Painting | RFM Ventures | RI Waxahachie | 11050 | No | ACH | RIW-CFR-09-047
2025-11-17 | 9 | 14 | ACT 2 Draws Floors 1 to 4 | From RFM Ventures - Pay App 05 | 44000 | 4400 | 39600 |  |  |  | Lay-in Ceiling's Materials | RFM Ventures | RI Waxahachie | 11050 | No | ACH | RIW-CFR-09-048
2025-11-04 | 9 | 15 | Flooring Material | From Home Depot - Polymer-Modified Thinset Mortar | 427.7 | 0 | 427.7 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 11048 | NA | Credit Card | RIW-CFR-09-049
2025-11-05 | 9 | 15 | Flooring Material | From Home Depot - Original Multi-Use Painter's Tape | 37.61 | 0 | 37.61 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 11064 | NA | Credit Card | RIW-CFR-09-050
2025-11-06 | 9 | 15 | Flooring Material | From Home Depot - High Density Painters Plastic Sheeting & Multi-Use Painter Tape | 384.42 | 0 | 384.42 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 11065 | NA | Credit Card | RIW-CFR-09-051
2025-11-07 | 9 | 15 | Flooring Material | From Home Depot - Cement Backerboard & Polymer-Modified Thinset Mortar | 292.09 | 0 | 292.09 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 11067 | NA | Credit Card | RIW-CFR-09-052
2025-11-10 | 9 | 15 | Drywall Material | From Home Depot - Drywall Screws & Exterior Wood Screws | 75.18 | 0 | 75.18 |  |  |  | Drywall Material | Home Depot | Boulder AMEX | 11069 | NA | Credit Card | RIW-CFR-09-053
2025-11-14 | 9 | 15 | Flooring Material | From Home Depot - Board Surface Protector Paper & Heavy Duty Tape | 236.89 | 0 | 236.89 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 11075 | NA | Credit Card | RIW-CFR-09-054
2025-11-15 | 9 | 15 | Flooring Material | From Home Depot - Polymer-Modified Thinset Mortar | 213.85 | 0 | 213.85 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 11092 | NA | Credit Card | RIW-CFR-09-055
2025-11-18 | 9 | 15 | Flooring Material | From Home Depot - Diamond Grit Grout Removal Multi-Tool Blade | 57.74 | 0 | 57.74 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 11094 | NA | Credit Card | RIW-CFR-09-056
2025-11-24 | 9 | 15 | Carpet Installation | From Home Depot - Self-Adhesive Film & Carpet Protection Self Adhesive Film | 926.64 | 0 | 926.64 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 11099 | NA | Credit Card | RIW-CFR-09-057
2025-11-24 | 9 | 15 | Carpet Installation | From Home Depot - Self-Adhesive Film | 1338.19 | 0 | 1338.19 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 11102 | NA | Credit Card | RIW-CFR-09-058
2025-11-24 | 9 | 15 | Carpet Installation | From Home Depot - Self-Adhesive Film | 1147.02 | 0 | 1147.02 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 11103 | NA | Credit Card | RIW-CFR-09-059
2025-12-04 | 9 | 15 | Drywall Material | From Home Depot - Black Forced Air Kerosene/Diesel Outdoor Space Heater with Thermostat | 1181.83 | 0 | 1181.83 |  |  |  | Drywall Material | Home Depot | Boulder AMEX | 11114 | NA | Credit Card | RIW-CFR-09-060
2025-11-24 | 9 | 15 | Carpet Installation | From Home Depot - Self-Adhesive Film | 955.85 | 0 | 955.85 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 11120 | NA | Credit Card | RIW-CFR-09-061
2025-11-19 | 9 | 15 | Flooring Labor | From TKG Construction | 35000 | 0 | 35000 |  |  |  | Flooring Install | TKG Construction | RI Waxahachie | 11140 | NA | ACH | RIW-CFR-09-062
2025-12-11 | 9 | 15 | Drywall Material | From Home Depot - Drywall Anchors, Drywall Screws, Steel Screwdriving Bit | 173.71 | 0 | 173.71 |  |  |  | Drywall Material | Home Depot | Boulder AMEX | 11168 | NA | Credit Card | RIW-CFR-09-063
2025-12-12 | 9 | 15 | Carpet Installation | From Home Depot - Construction Adhesive, Bi-Metal Hole Saw & Tape | 260.79 | 0 | 260.79 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 11174 | NA | Credit Card | RIW-CFR-09-064
2025-12-15 | 9 | 15 | Drywall Material | From Home Depot - Drywall Anchors & Microfiber Spin Mop | 220.55 | 0 | 220.55 |  |  |  | Drywall Material | Home Depot | Boulder AMEX | 11188 | NA | Credit Card | RIW-CFR-09-065
2025-12-17 | 9 | 15 | RC Channel & Sheetrock for Floor 1 | From RFM Ventures - Pay App 06 (First Payment) | 19000 | 1900 | 17100 |  |  |  | Drywall Material | RFM Ventures | RI Waxahachie | 11155 | No | ACH | RIW-CFR-09-066
2025-12-17 | 9 | 15 | Texture & Tape/Bed/Sand for Floor 1 | From RFM Ventures - Pay App 06 (First Payment) | 12000 | 1200 | 10800 |  |  |  | Drywall Labor | RFM Ventures | RI Waxahachie | 11155 | No | ACH | RIW-CFR-09-067
2025-12-17 | 9 | 15 | Paint for Floor 1 | From RFM Ventures - Pay App 06 (First Payment) | 13000 | 1300 | 11700 |  |  |  | Painting | RFM Ventures | RI Waxahachie | 11155 | No | ACH | RIW-CFR-09-068
2025-12-17 | 9 | 15 | Vinyl for Floors 1 to 4 | From RFM Ventures - Pay App 06 (First Payment) | 35194.44 | 3519.44 | 31675 |  |  |  | VMC Install | RFM Ventures | RI Waxahachie | 11155 | No | ACH | RIW-CFR-09-069
2026-01-14 | 9 | 15 | Vinyl for Floors 1 to 4 | From RFM Ventures - Pay App 06 (Final Payment) | 39805.56 | 3980.56 | 35825 |  |  |  | VMC Install | RFM Ventures | RI Waxahachie | 11155 | No | ACH | RIW-CFR-09-070
2026-01-14 | 9 | 15 | ACT Floor 1 | From RFM Ventures - Pay App 06 (Final Payment) | 26000 | 2600 | 23400 |  |  |  | Lay-in Ceiling's Materials | RFM Ventures | RI Waxahachie | 11155 | No | ACH | RIW-CFR-09-071
2025-10-23 | 9 | 16 | Flooring Material | From Home Depot - T-Hinge | 40.67 | 0 | 40.67 |  |  |  | Flooring Material | Home Depot | [To Be Confirmed] | 11049 | NA | Credit Card | RIW-CFR-09-072
2025-12-03 | 9 | 16 | Flooring Material | From Home Depot - Tan Star Drive Flat-Head Wood Deck Screws | 34.19 | 0 | 34.19 |  |  |  | Flooring Material | Home Depot | [To Be Confirmed] | 11132 | NA | Credit Card | RIW-CFR-09-073
2025-12-29 | 9 | 16 | Flooring Material | From Home Depot - Liquid nails, Circular Saw Blade & Head Screw | 142.21 | 0 | 142.21 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 11231 | NA | Credit Card | RIW-CFR-09-074
2026-01-16 | 9 | 16 | Flooring Material | From Home Depot - Microfiber Refills & Multi-Purpose Microfiber Cloth | 31.34 | 0 | 31.34 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 11232 | NA | Credit Card | RIW-CFR-09-075
2026-01-16 | 9 | 16 | Flooring Material | From Home Depot - 90-Degree Pull Elbow, Compression Coupling & One-Hole Strap | 38.4 | 0 | 38.4 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 11233 | NA | Credit Card | RIW-CFR-09-076
2026-01-16 | 9 | 16 | Flooring Material | From Home Depot - Universal Patch and Skimcoat, Floor Adhesive & Self-Leveling Underlayment | 375.27 | 0 | 375.27 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 11235 | NA | Credit Card | RIW-CFR-09-077
2026-01-02 | 9 | 16 | Flooring Material | From Home Depot - Adhesive & Head Toggle Bolt Anchors | 99.18 | 0 | 99.18 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 11237 | NA | Credit Card | RIW-CFR-09-078
2026-01-05 | 9 | 16 | Flooring Material | From Home Depot - Trash Bags, Contractor Bags & Towels | 144.85 | 0 | 144.85 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 11238 | NA | Credit Card | RIW-CFR-09-079
2026-01-06 | 9 | 16 | Flooring Material | From Home Depot - Cement Board, Grade, Outdoor Lock & Multi-Purpose Cleaner Concentrate | 862.58 | 0 | 862.58 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 11239 | NA | Credit Card | RIW-CFR-09-080
2026-01-07 | 9 | 16 | Flooring Material | From Home Depot - Aggregate Grout & Cabinet Screw | 92.63 | 0 | 92.63 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 11240 | NA | Credit Card | RIW-CFR-09-081
2026-01-08 | 9 | 16 | Drywall Material | From Home Depot - Drywall Anchors, Drilling Screws | 53.37 | 0 | 53.37 |  |  |  | Drywall Material | Home Depot | Boulder AMEX | 11242 | NA | Credit Card | RIW-CFR-09-082
2026-01-08 | 9 | 16 | Flooring Material | From Home Depot - Toggle Bolt Anchors & Steel Screwdriving | 71.46 | 0 | 71.46 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 11243 | NA | Credit Card | RIW-CFR-09-083
2026-01-08 | 9 | 16 | Flooring Material | From Home Depot - Super Hold Glue, Socket Wrench & Twist Drill | 243.94 | 0 | 243.94 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 11245 | NA | Credit Card | RIW-CFR-09-084
2026-01-10 | 9 | 16 | Flooring Material | From Home Depot - Contractor Grade Tan Masking Tape | 19.01 | 0 | 19.01 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 11250 | NA | Credit Card | RIW-CFR-09-085
2026-01-10 | 9 | 16 | Flooring Material | From Home Depot - Thermoplastic Rubber Wall Coil & Floor Adhesive | 465.22 | 0 | 465.22 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 11251 | NA | Credit Card | RIW-CFR-09-086
2026-01-22 | 9 | 16 | Paint Material | From PPG Paints | 15784.59 | 0 | 15784.59 |  |  |  | Painting | PPG Paints | Jaimin AMEX | 11254 | NA | Credit Card | RIW-CFR-09-087
2025-12-24 | 9 | 16 | Flooring Material | From Home Depot - String Mop, Dust Flat Mop, Contractor Bags & Scrub Brush | 160.51 | 0 | 160.51 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 11255 | NA | Credit Card | RIW-CFR-09-088
2025-12-24 | 9 | 16 | Flooring Material | From Home Depot - Thinset Mortar | 498.98 | 0 | 498.98 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 11256 | NA | Credit Card | RIW-CFR-09-089
2025-12-24 | 9 | 16 | Flooring Material | From Home Depot - Thinset Mortar | 498.98 | 0 | 498.98 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 11257 | NA | Credit Card | RIW-CFR-09-090
2025-12-26 | 9 | 16 | Flooring Material | From Home Depot - Wood Subfloors | 137.08 | 0 | 137.08 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 11259 | NA | Credit Card | RIW-CFR-09-091
2025-12-26 | 9 | 16 | Flooring Material | From Home Depot - Wood Subfloors | 228.46 | 0 | 228.46 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 11260 | NA | Credit Card | RIW-CFR-09-092
2025-12-29 | 9 | 16 | Flooring Material | From Home Depot - Canister Vacuum, Floor Protection & Painter's Tape | 899.95 | 0 | 899.95 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 11261 | NA | Credit Card | RIW-CFR-09-093
2025-12-31 | 9 | 16 | Flooring Material | From Home Depot - Glazed Ceramic Floor and Wall Tile | 2112.56 | 0 | 2112.56 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 11265 | NA | Credit Card | RIW-CFR-09-094
2025-12-30 | 9 | 16 | Paint Material | From Lowe's - Ultracolor Plus | 562.47 | 0 | 562.47 |  |  |  | Painting | Lowe's | Boulder AMEX | 11266 | NA | Credit Card | RIW-CFR-09-095
2026-01-06 | 9 | 16 | Paint Material | From Lowe's - Ultracolor Plus & Horseshoe Spacer | 381.6 | 0 | 381.6 |  |  |  | Painting | Lowe's | Boulder AMEX | 11267 | NA | Credit Card | RIW-CFR-09-096
2026-01-06 | 9 | 16 | COs | From TKG Construction | 28500 | 0 | 28500 |  |  |  | Flooring Install | TKG Construction | RI Waxahachie | 11285 | No | ACH | RIW-CFR-09-097
2026-01-06 | 9 | 16 | Flooring Labor | From TKG Construction | 1500 | 0 | 1500 |  |  |  | Flooring Install | TKG Construction | RI Waxahachie | 11285 | No | ACH | RIW-CFR-09-098
2026-01-07 | 9 | 16 | Flooring Labor | From TKG Construction | 15000 | 0 | 15000 |  |  |  | Flooring Install | TKG Construction | RI Waxahachie | 11285 | No | ACH | RIW-CFR-09-099
2026-01-10 | 9 | 16 | Drywall Material | From Home Depot - Drywall Material | 70.72 | 0 | 70.72 |  |  |  | Drywall Material | Home Depot | [To Be Confirmed] | 11287 | NA | Credit Card | RIW-CFR-09-100
2026-01-02 | 9 | 16 | Paint Material | From Lowe's - Ultracolor Plus & Flex | 269.37 | 0 | 269.37 |  |  |  | Painting | Lowe's | Boulder AMEX | 12169 | NA | Credit Card | RIW-CFR-09-101
2026-02-03 | 9 | 16 | Corner Guards | From Inpro Corporation | 2960.47 | 0 | 2960.47 |  |  |  | Drywall Material | Inpro Corporation | Jaimin AMEX | 12194 | NA | Credit Card | RIW-CFR-09-102
2026-01-15 | 9 | 16 | Paint Material | From Sherwin Williams | 707.53 | 0 | 707.53 |  |  |  | Painting | Sherwin Williams | Jaimin AMEX | 12195 | NA | Credit Card | RIW-CFR-09-103
2026-01-23 | 9 | 16 | Painting Material | From Home Depot - Multi Surface Painter's Tape | 92.64 | 0 | 92.64 |  |  |  | Painting | Home Depot | Boulder AMEX | 12197 | NA | Credit Card | RIW-CFR-09-104
2026-01-21 | 9 | 16 | Flooring Material | From Home Depot - Waterproof & Crack Prevention Membrance | 383.19 | 0 | 383.19 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 12199 | NA | Credit Card | RIW-CFR-09-105
2026-01-20 | 9 | 16 | Carpet Installation | From Home Depot - Self Adhesive Film & Stretch Wrap | 198.39 | 0 | 198.39 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 12201 | NA | Credit Card | RIW-CFR-09-106
2026-01-20 | 9 | 16 | Flooring Material | From Home Depot - Thinset Mortar & Thermoplastic Rubber Base Coil | 622.5 | 0 | 622.5 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 12202 | NA | Credit Card | RIW-CFR-09-107
2026-01-19 | 9 | 16 | Paint Material | From Lowe's - Masking Tape | 115.89 | 0 | 115.89 |  |  |  | Painting | Lowe's | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-09-108
2025-11-12 | 9 | 16 | Flooring Material | From C&C Wholesale | 356.36 | 0 | 356.36 |  |  |  | Flooring Material | C&C Wholesale | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-09-109
2025-10-28 | 9 | 16 | Flooring Material | From Surface Material | 775.69 | 0 | 775.69 |  |  |  | Flooring Material | Surface Material | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-09-110
2025-10-31 | 9 | 16 | Flooring Material | From C&C Wholesale | 1241.94 | 0 | 1241.94 |  |  |  | Flooring Material | C&C Wholesale | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-09-111
2025-11-01 | 9 | 16 | Flooring Material | From C&C Wholesale | 1628.06 | 0 | 1628.06 |  |  |  | Flooring Material | C&C Wholesale | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-09-112
2025-11-01 | 9 | 16 | Flooring Material | From C&C Wholesale | -1241.94 | 0 | -1241.94 |  |  |  | Flooring Material | C&C Wholesale | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-09-113
2025-11-07 | 9 | 16 | Flooring Material | From Surface Material | 530.96 | 0 | 530.96 |  |  |  | Flooring Material | Surface Material | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-09-114
2025-12-19 | 9 | 16 | Flooring Material | From C&C Wholesale | 332.54 | 0 | 332.54 |  |  |  | Flooring Material | C&C Wholesale | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-09-115
2025-12-19 | 9 | 16 | Flooring Material | From C&C Wholesale | 332.54 | 0 | 332.54 |  |  |  | Flooring Material | C&C Wholesale | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-09-116
2025-12-20 | 9 | 16 | Flooring Material | From C&C Wholesale | 2704.41 | 0 | 2704.41 |  |  |  | Flooring Material | C&C Wholesale | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-09-117
2026-01-16 | 9 | 16 | Flooring Material | From Floor & Décor | 339.65 | 0 | 339.65 |  |  |  | Flooring Material | Floor & Décor | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-09-118
2026-02-12 | 9 | 16 | Flooring Labor | From TKG Construction | 18070 | 0 | 18070 |  |  |  | Flooring Install | TKG Construction | RI Waxahachie | 11285 | No | ACH | RIW-CFR-09-119
2026-02-26 | 9 | 16 | Flooring Labor | From TKG Construction | 250 | 0 | 250 |  |  |  | Flooring Install | TKG Construction | RI Waxahachie | 11285 | No | ACH | RIW-CFR-09-119
2026-02-26 | 9 | 16 | Deliveries & Repairs | From TKG Construction | 23500 | 0 | 23500 |  |  |  | Flooring Install | TKG Construction | RI Waxahachie | 11285 | No | ACH | RIW-CFR-09-120
2026-02-04 | 9 | 17 | Drywall Material | From Home Depot - Gypsum Board, Joint Compound and Drywall Screws and Tape | 109.85 | 0 | 109.85 |  |  |  | Drywall Material | Home Depot | Boulder AMEX | 12207 | NA | Credit Card
2026-02-11 | 9 | 17 | Drywall Material | From Home Depot - Joint Compound For Drywall Finishing | 55.53 | 0 | 55.53 |  |  |  | Drywall Material | Home Depot | Boulder AMEX | 12210 | NA | Credit Card
2026-02-11 | 9 | 17 | Drywall Material | From Home Depot - Gypsum Board, Drywall Screws and Zip Bit | 79.74 | 0 | 79.74 |  |  |  | Drywall Material | Home Depot | Boulder AMEX | 12211 | NA | Credit Card
2026-02-13 | 9 | 17 | Drywall Material | From Home Depot - Drywall Sheets (1/2 In Ultralight) | 96.32 | 0 | 96.32 |  |  |  | Drywall Material | Home Depot | Boulder AMEX | 12219 | NA | Credit Card
2026-02-16 | 9 | 17 | Flooring Material | From Home Depot - Tile Mortar and Sponge | 297.62 | 0 | 297.62 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 12220 | NA | Credit Card
2026-02-18 | 9 | 17 | Flooring Material | From Home Depot - Whitewood Stud, Saw, Drill Bit | 126.43 | 0 | 126.43 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 12222 | NA | Credit Card
2026-02-18 | 9 | 17 | Painting Material | From Home Depot - Painting ToolsPaint Roller Frame | 10.95 | 0 | 10.95 |  |  |  | Painting | Home Depot | Boulder AMEX | 12224 | NA | Credit Card
2026-01-23 | 9 | 17 | Flooring Material | From Home Depot - Temporary Heat Supplies (Kerosene And Heaters) | 551.88 | 0 | 551.88 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 12225 | NA | Credit Card
2026-02-18 | 9 | 17 | Painting Material Refund | From Home Depot - Refund | -26.63 | 0 | -26.63 |  |  |  | Painting | Home Depot | Boulder AMEX | 12226 | NA | Credit Card
2026-02-18 | 9 | 17 | Painting Material | From Home Depot - Painting Supplies (Roller Covers, Trays) | 54.62 | 0 | 54.62 |  |  |  | Painting | Home Depot | Boulder AMEX | 12226 | NA | Credit Card
2026-02-18 | 9 | 17 | Drywall Material | From Home Depot - Drywall Screws box And Carpenter Pencils | 20.58 | 0 | 20.58 |  |  |  | Drywall Material | Home Depot | Boulder AMEX | 12228 | NA | Credit Card
2026-02-18 | 9 | 17 | Painting Material | From Home Depot - Wood Moving Dolly, Water Primer and Sealerand Roller | 413.53 | 0 | 413.53 |  |  |  | Painting | Home Depot | Boulder AMEX | 12231 | NA | Credit Card
2026-02-18 | 9 | 17 | Painting Material Refund | From Home Depot - Refund | -47.62 | 0 | -47.62 |  |  |  | Painting | Home Depot | Boulder AMEX | 12231 | NA | Credit Card
2026-02-17 | 9 | 17 | Flooring Material | From Home Depot - Machine Washable Mop, Contractor Bags, Joint Compound | 257.96 | 0 | 257.96 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 12236 | NA | Credit Card
2026-02-17 | 9 | 17 | Drywall Material | From Home Depot - Joint Coumpound, Drywall Tape and Sanding Sponge | 47.08 | 0 | 47.08 |  |  |  | Drywall Material | Home Depot | Boulder AMEX | 12238 | NA | Credit Card
2026-02-17 | 9 | 17 | Flooring Material | From Home Depot - Drill Bits, Anchors and Snacks | 97.87 | 0 | 97.87 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 12241 | NA | Credit Card
2026-02-13 | 9 | 17 | Flooring Material | From Home Depot - Joint Compound | 30.96 | 0 | 30.96 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 12257 | NA | Credit Card
2026-02-13 | 9 | 17 | Flooring Material | From Home Depot - Misc. And SuppliesSelf Adhesive Film | 140.68 | 0 | 140.68 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 12259 | NA | Credit Card
2026-02-12 | 9 | 17 | Painting Material | From Home Depot - Jobsite SuppliesSpray Paint | 7.03 | 0 | 7.03 |  |  |  | Painting | Home Depot | Boulder AMEX | 12265 | NA | Credit Card
2026-02-12 | 9 | 17 | Drywall Material | From Home Depot - Drywall Corner Bead Materials | 182.51 | 0 | 182.51 |  |  |  | Drywall Material | Home Depot | Boulder AMEX | 12266 | NA | Credit Card
2026-02-11 | 9 | 17 | Flooring Material | From Home Depot - Carpet Adhesive And Hinge and Latch Set | 285.27 | 0 | 285.27 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 12276 | NA | Credit Card
2026-02-10 | 9 | 17 | Flooring Material | From Home Depot - Carpet Flooring Adhesive | 285.08 | 0 | 285.08 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 12277 | NA | Credit Card
2026-02-10 | 9 | 17 | Painting Material | From Home Depot - Painting SuppliesFlat Paint Brush and Plastic Sheeting | 50.77 | 0 | 50.77 |  |  |  | Painting | Home Depot | Boulder AMEX | 12278 | NA | Credit Card
2026-02-10 | 9 | 17 | Flooring Material | From Home Depot - Polyblend Grout and Tile Trim | 132.69 | 0 | 132.69 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 12289 | NA | Credit Card
2026-02-09 | 9 | 17 | Painting Material | From Home Depot - Spray Foam Sealant | 35.85 | 0 | 35.85 |  |  |  | Painting | Home Depot | Boulder AMEX | 12291 | NA | Credit Card
2026-02-09 | 9 | 17 | Drywall Material | From Home Depot - Wall Shelf Bracket and Drywall Anchor | 250.69 | 0 | 250.69 |  |  |  | Drywall Material | Home Depot | Boulder AMEX | 12292 | NA | Credit Card
2026-02-08 | 9 | 17 | Flooring Material | From Home Depot - Tile Grout And Grout Float | 246.73 | 0 | 246.73 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 12294 | NA | Credit Card
2026-02-07 | 9 | 17 | Painting Material | From Home Depot - Primer Spray And Metal Cut | 71.94 | 0 | 71.94 |  |  |  | Painting | Home Depot | Boulder AMEX | 12295 | NA | Credit Card
2026-02-06 | 9 | 17 | Painting Material | From Home Depot - Cedar Stain and Sealer, Framing Nails and Roller | 81.49 | 0 | 81.49 |  |  |  | Painting | Home Depot | Boulder AMEX | 12296 | NA | Credit Card
2026-02-06 | 9 | 17 | Painting Material | From Home Depot - Paint Brush, Gloves, Blades and Cleaners | 75.47 | 0 | 75.47 |  |  |  | Painting | Home Depot | Boulder AMEX | 12297 | NA | Credit Card
2026-02-06 | 9 | 17 | Flooring Material | From Home Depot - Motar Mix, Tile Spacer and Vinyl sealer | 118.04 | 0 | 118.04 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 12298 | NA | Credit Card
2026-02-04 | 9 | 17 | Flooring Material | From Home Depot - Self Adhesive and Microfibre Cloth | 209.18 | 0 | 209.18 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 12300 | NA | Credit Card
2026-02-03 | 9 | 17 | Flooring Material | From Home Depot - Wall Base Floor Adhesive | 103.83 | 0 | 103.83 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 12301 | NA | Credit Card
2026-02-03 | 9 | 17 | Flooring Material | From Home Depot - Vinly Adhesive, Vinly Roller, Tape Roller and Flooring Trowel | 394.94 | 0 | 394.94 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 12302 | NA | Credit Card
2026-02-03 | 9 | 17 | Flooring Material | From Home Depot - Tile Setting Materials Thinset Mortar | 171.08 | 0 | 171.08 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 12303 | NA | Credit Card
2026-02-02 | 9 | 17 | Painting Material | From Home Depot - PaintingPaint, Brush Sprays | 316.92 | 0 | 316.92 |  |  |  | Painting | Home Depot | Boulder AMEX | 12306 | NA | Credit Card
2026-02-19 | 9 | 17 | Painting Materials | From Home Depot - Soap, Painter's Tape, Cleaner and Polish | 215.41 | 0 | 215.41 |  |  |  | Painting | Home Depot | Boulder AMEX | 12315 | NA | Credit Card
2026-02-20 | 9 | 17 | Drywall Material | From Home Depot - Roller Catch, Tooth Rachet, Drywall Screws | 208.26 | 0 | 208.26 |  |  |  | Drywall Material | Home Depot | Boulder AMEX | 12321 | NA | Credit Card
2026-02-20 | 9 | 17 | Drywall Material | From Home Depot - Extension Cord, Drywall Screws. | 231.82 | 0 | 231.82 |  |  |  | Drywall Material | Home Depot | Boulder AMEX | 12322 | NA | Credit Card
2026-02-20 | 9 | 17 | Painting Material | From Home Depot - Roll and Paint Bucket | 17.26 | 0 | 17.26 |  |  |  | Painting | Home Depot | Boulder AMEX | 12324 | NA | Credit Card
2026-02-20 | 9 | 17 | Drywall Material | From Home Depot - Drywall Anchors, Magnetic Holder, Wood Screw | 30.44 | 0 | 30.44 |  |  |  | Drywall Material | Home Depot | Boulder AMEX | 12325 | NA | Credit Card
2026-02-21 | 9 | 17 | Flooring Material | From Home Depot - Grout | 57.09 | 0 | 57.09 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 12328 | NA | Credit Card
2026-02-23 | 9 | 17 | Flooring Material | From Home Depot - Rubber Wall Cove Base | 134.34 | 0 | 134.34 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 12329 | NA | Credit Card
2026-02-04 | 9 | 17 | Flooring Material | From Lowes - Flooring Transitions And Vinyl Divider | 399.33 | 0 | 399.33 |  |  |  | Flooring Material | Lowes | Boulder AMEX | 12335 | NA | Credit Card
2026-02-13 | 9 | 17 | Flooring Material | From Lowes - Tile Setting Materials (Grout | 267.19 | 0 | 267.19 |  |  |  | Flooring Material | Lowes | Boulder AMEX | 12336 | NA | Credit Card
2026-02-11 | 9 | 17 | Flooring Material | From Lowes - Transition Reducers And Flooring Trim Materials | 149.26 | 0 | 149.26 |  |  |  | Flooring Material | Lowes | Boulder AMEX | 12339 | NA | Credit Card
2026-02-06 | 9 | 17 | Painting Material | From Home Depot - Painting SuppliesPaint Pail and Gloves and Brushes | 94.37 | 0 | 94.37 |  |  |  | Painting | Home Depot | Boulder AMEX | 12346 | NA | Credit Card
2026-02-12 | 9 | 17 | Drywall Material | From Lowe's - Drywall | 527.09 | 0 | 527.09 |  |  |  | Drywall Material | Lowes | Boulder AMEX | 12401 | NA | Credit Card
2026-02-02 | 9 | 17 | Flooring Material | From Lowes - Tile Setting Materials | 440.76 | 0 | 440.76 |  |  |  | Flooring Material | Lowes | Boulder AMEX | 12402 | NA | Credit Card
2026-02-25 | 9 | 17 | Painting Material | From Home Depot - Metal Interior/Exterior Paint | 162.72 | 0 | 162.72 |  |  |  | Painting | Home Depot | Boulder AMEX | 12457 | NA | Credit Card
2026-02-18 | 9 | 17 | Painting Material | From Lowes - Ultracolor Plus, and Sctch Blue Painter | 150.9 | 0 | 150.9 |  |  |  | Painting | Lowes | Boulder AMEX | 12460 | NA | Credit Card
2026-02-28 | 9 | 17 | Flooring Material | From Home Depot - Joint Compound & Sheetrock | 65.76 | 0 | 65.76 |  |  |  | Flooring Material | Home Depot | Boulder AMEX | 12465 | NA | Credit Card
2026-02-24 | 9 | 17 | Public Area Tile Carpet | From J&JR Construction | 19111 | 0 | 19111 |  |  |  | Flooring Install | J&JR Construction | RI Waxahachie | 12471 | Yes | Check
2026-01-20 | 9 | 17 | Flooring Material | From Lowes - Type 1Mastic Gal And Ultracolor Plus | 141.74 | 0 | 141.74 |  |  |  | Flooring Material | Lowes | Jaimin AMEX | [TBD] | NA | Credit Card
2026-01-28 | 9 | 17 | Flooring Material | From Lowes - Ultracolor Plus, and Ultra Flex White | 687.08 | 0 | 687.08 |  |  |  | Flooring Material | Lowes | Jaimin AMEX | [TBD] | NA | Credit Card
2026-02-20 | 9 | 17 | Flooring Material | From Floor & Décor | 200.04 | 0 | 200.04 |  |  |  | Flooring Material | Floor & Décor | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-21 | 9 | 17 | Painting Material | From Sherwin Williams | 822.67 | 0 | 822.67 |  |  |  | Painting | Sherwin Williams | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-05 | 9 | 17 | Rubber Edge Trim | From Amazon | 29.18 | 0 | 29.18 |  |  |  | Flooring Material | Amazon | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-06 | 9 | 17 | Rubber Trims | From Amazon | 38.72 | 0 | 38.72 |  |  |  | Flooring Material | Amazon | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-08 | 9 | 17 | Stair Edging Strip | From Amazon | 25.97 | 0 | 25.97 |  |  |  | Flooring Material | Amazon | Boulder AMEX | [TBD] | NA | Credit Card
2026-01-31 | 9 | 17 | Flooring Material | From Floor & Décor | 1920.44 | 0 | 1920.44 |  |  |  | Flooring Material | Floor & Décor | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-01 | 9 | 17 | Flooring Material | From Floor & Décor | 2940.94 | 0 | 2940.94 |  |  |  | Flooring Material | Floor & Décor | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-03 | 9 | 17 | Flooring Material | From Floor & Décor | 554.74 | 0 | 554.74 |  |  |  | Flooring Material | Floor & Décor | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-09 | 9 | 17 | Flooring Material | From Cazares Carpet | 310.02 | 0 | 310.02 |  |  |  | Flooring Material | Cazares Carpet | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-12 | 9 | 17 | Flooring Material | From Cazares Carpet | 116.26 | 0 | 116.26 |  |  |  | Flooring Material | Cazares Carpet | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-15 | 9 | 17 | Flooring Material | From Floor & Décor | 2446.26 | 0 | 2446.26 |  |  |  | Flooring Material | Floor & Décor | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-20 | 9 | 17 | Flooring Material | From Cazares Carpet | 1317.4 | 0 | 1317.4 |  |  |  | Flooring Material | Cazares Carpet | Boulder AMEX | [TBD] | NA | Credit Card
2026-01-20 | 9 | 17 | Carpet | From C&C Wholesale | 494.49 | 0 | 494.49 |  |  |  | Flooring Material | C&C Wholesale | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-28 | 9 | 17 | ACT | From Gilbert | 154.5 | 0 | 154.5 |  |  |  | Lay-in Ceiling's Materials | Gilbert | Boulder AMEX | [TBD] | NA | Credit Card
[To Be Paid] | 9 | 17 | Flooring Labor | From TKG Construction - Pay App 11 | 28000 | 0 | 28000 |  |  |  | Flooring Install | TKG Construction | [To Be Paid] | [TBD] | No | [To Be Paid]
10. Specialties and Equipment
| 10 | 4 | Draw 4 Funds |  |  |  |  | 26378.81 | 0 | 26378.81
| 10 | 5 | Draw 5 Funds |  |  |  |  | 36164.11 | 0 | 36164.11
| 10 | 6 | Draw 6 Funds - Reimbursement |  |  |  |  | 190 | 0 | 190
| 10 | 11 | Draw 11 Funds - Reimbursement |  |  |  |  | 20433.68 | 0 | 20433.68
| 10 | 14 | Draw 14 Funds - Reimbursements |  |  |  |  | 20986.93 | 0 | 20986.93
| 10 | 14 | Draw 14 Funds - To Be Paid |  |  |  |  | 250000 | 0 | 250000
| 10 | 15 | Draw 15 Funds - Reimbursements |  |  |  |  | 5520.87 | 0 | 5520.87
| 10 | 16 | Draw 16 Funds - Reimbursements |  |  |  |  | 11243.33 | 0 | 11243.33
| 10 | 16 | Draw 16 Funds - To Be Paid |  |  |  |  | 21769.6 | 0 | 21769.6
| 10 | 17 | Draw 17 Funds - Reimbursements |  |  |  |  | 10462.44 | 0 | 10462.44
| 10 | 17 | Draw 17 Funds - To Be Paid |  |  |  |  | 2450 | 0 | 2450
2024-12-23 | 10 | 4 | Tub and Shower Surrounds | 50% Deposit (Pre-Tax & Shipping) | 20323.92 | 0 | 20323.92 |  |  |  | Glass Shower/Surround Install | JMHS | RI Waxahachie | 10220 | NA | Wire Transfer | RIW-CFR-10-001
2024-12-23 | 10 | 4 | Toilet Accessories (Dish, Foot Rest, Ledge, Trim) | 50% Deposit (Pre-Tax & Shipping) | 6054.89 | 0 | 6054.89 |  |  |  | Toilet Material | JMHS | RI Waxahachie | 10220 | NA | Wire Transfer | RIW-CFR-10-002
2025-03-07 | 10 | 5 | Tub and Shower Surrounds | Remaining Deposit (Pre-Tax) | 20323.92 | 0 | 20323.92 |  |  |  | Glass Shower/Surround Install | JMHS | RI Waxahachie | 10308 | NA | Wire Transfer | RIW-CFR-10-003
2025-03-07 | 10 | 5 | Toilet Accessories (Dish, Foot Rest, Ledge, Trim) | Remaining Deposit (Pre-Tax) | 6054.89 | 0 | 6054.89 |  |  |  | Toilet Material | JMHS | RI Waxahachie | 10308 | NA | Wire Transfer | RIW-CFR-10-004
2025-03-07 | 10 | 5 | Tub and Shower Surrounds | Allocated Shipping Costs | 7539.2201 | 0 | 7539.2201 |  |  |  | Glass Shower/Surround Install | JMHS | RI Waxahachie | 10308 | NA | Wire Transfer | RIW-CFR-10-005
2025-03-07 | 10 | 5 | Toilet Accessories (Dish, Foot Rest, Ledge, Trim) | Allocated Shipping Costs | 2246.0799 | 0 | 2246.0799 |  |  |  | Toilet Material | JMHS | RI Waxahachie | 10308 | NA | Wire Transfer | RIW-CFR-10-006
2025-03-07 | 10 | 6 | Tub and Shower Surrounds | Additional Invoice Amount | 190 | 0 | 190 |  |  |  | Glass Shower/Surround Install | JMHS | RI Waxahachie | 10308 | NA | Wire Transfer | RIW-CFR-10-007
2025-07-25 | 10 | 11 | Hook, Bars, Rods, Seats, Glass Shelf, Toilet Holder | From JMHS - Bathroom Scope 50% Deposit - RIWTX-102 | 18423.79 | 0 | 18423.79 |  |  |  | Toilet Material | JMHS | RI Waxahachie | 10679 | NA | ACH | RIW-CFR-10-008
2025-07-25 | 10 | 11 | Shower Surrounds | From JMHS - Bathroom Scope 50% Deposit - RIWTX-102 | 2009.89 | 0 | 2009.89 |  |  |  | Glass Shower/Surround Install | JMHS | RI Waxahachie | 10679 | NA | ACH | RIW-CFR-10-009
2025-11-03 | 10 | 14 | Shower Surrounds | From JMHS - Bathroom Scope Remaining 50% Payment - RIWTX-102 | 2009.89 | 0 | 2009.89 |  |  |  | Glass Shower/Surround Install | JMHS | RI Waxahachie | 10679 | NA | ACH | RIW-CFR-10-010
2025-11-03 | 10 | 14 | Hook, Bars, Rods, Seats, Glass Shelf, Toilet Holder | From JMHS - Bathroom Scope Remaining 50% Payment - RIWTX-102 | 18423.79 | 0 | 18423.79 |  |  |  | Toilet Material | JMHS | RI Waxahachie | 10679 | NA | ACH | RIW-CFR-10-011
2025-10-24 | 10 | 14 | Fire Extinguisher Cabinets | From Texas Fire Extinguishers | 553.25 | 0 | 553.25 |  |  |  | Fire Extinguisher Material | Texas Fire Extinguisher | Boulder AMEX | 11022 | NA | Credit Card | RIW-CFR-10-012
[To Be Paid] | 10 | 14 | Kitchen Equipment |  | 150000 | 0 | 150000 |  |  |  | Kitchen Equipment |  | [To Be Paid] | [To Be Paid] | NA | [To Be Paid] | RIW-CFR-10-013
[To Be Paid] | 10 | 14 | Laundry Equipment |  | 100000 | 0 | 100000 |  |  |  | Laundry Equipment |  | [To Be Paid] | [To Be Paid] | NA | [To Be Paid] | RIW-CFR-10-014
2025-11-10 | 10 | 15 | Misc. Shower/Surround Install Material | From Home Depot - Kitchen & Bath Sealant Clear & Furring Strip Board | 400.31 | 0 | 400.31 |  |  |  | Glass Shower/Surround Install | Home Depot | Boulder AMEX | 11068 | NA | Credit Card | RIW-CFR-10-015
2025-11-15 | 10 | 15 | Misc. Shower/Surround Install Material | From Home Depot - Window, Door, Kitchen & Bath Sealant White, Acetone | 1154.25 | 0 | 1154.25 |  |  |  | Glass Shower/Surround Install | Home Depot | Boulder AMEX | 11090 | NA | Credit Card | RIW-CFR-10-016
2025-11-15 | 10 | 15 | Misc. Shower/Surround Install Material | From Home Depot - Window, Door, Kitchen & Bath Sealant White & Liquid Nails | 877.11 | 0 | 877.11 |  |  |  | Glass Shower/Surround Install | Home Depot | Boulder AMEX | 11091 | NA | Credit Card | RIW-CFR-10-017
2025-11-17 | 10 | 15 | Misc. Shower/Surround Install Material | From Home Depot - Acetone, Furring Strip Board & Heavy Duty Nitrile | 68.75 | 0 | 68.75 |  |  |  | Glass Shower/Surround Install | Home Depot | Boulder AMEX | 11093 | NA | Credit Card | RIW-CFR-10-018
2025-11-18 | 10 | 15 | Misc. Shower/Surround Install Material | From Home Depot - Kitchen and Bath Sealant White & Finish Nails | 232.28 | 0 | 232.28 |  |  |  | Glass Shower/Surround Install | Home Depot | Boulder AMEX | 11095 | NA | Credit Card | RIW-CFR-10-019
2025-11-24 | 10 | 15 | Misc. Shower/Surround Install Material | From Home Depot - Window & Door Sealant White and Hardwood Blade | 145.32 | 0 | 145.32 |  |  |  | Glass Shower/Surround Install | Home Depot | Boulder AMEX | 11101 | NA | Credit Card | RIW-CFR-10-020
2025-11-29 | 10 | 15 | Misc. Shower/Surround Install Material | From Home Depot - Window, Door, Kitchen & Bath Sealant White, Acetone | 378.49 | 0 | 378.49 |  |  |  | Glass Shower/Surround Install | Home Depot | Boulder AMEX | 11107 | NA | Credit Card | RIW-CFR-10-021
2025-12-01 | 10 | 15 | Misc. Shower/Surround Install Material | From Home Depot - Kitchen and Bath Sealant White | 772.91 | 0 | 772.91 |  |  |  | Glass Shower/Surround Install | Home Depot | Boulder AMEX | 11108 | NA | Credit Card | RIW-CFR-10-022
2025-12-03 | 10 | 15 | Misc. Shower/Surround Install Material | From Home Depot - Furring Strip Board & Multi-Purpose Terry Towel | 36.58 | 0 | 36.58 |  |  |  | Glass Shower/Surround Install | Home Depot | Boulder AMEX | 11112 | NA | Credit Card | RIW-CFR-10-023
2025-12-06 | 10 | 15 | Misc. Shower/Surround Install Material | From Home Depot - Urine Remover Spray, Sealer and Stain-Blocker Aerosol, etc. | 162.04 | 0 | 162.04 |  |  |  | Glass Shower/Surround Install | Home Depot | Boulder AMEX | 11134 | NA | Credit Card | RIW-CFR-10-024
2025-12-06 | 10 | 15 | Misc. Shower/Surround Install Material | From Home Depot - All Surface Construction Adhesive, Furring Strip Board, etc. | 190.53 | 0 | 190.53 |  |  |  | Glass Shower/Surround Install | Home Depot | Boulder AMEX | 11135 | NA | Credit Card | RIW-CFR-10-025
2025-12-10 | 10 | 15 | Misc. Shower/Surround Install Material | From Home Depot - Kitchen and Bath Sealant White | 449.24 | 0 | 449.24 |  |  |  | Glass Shower/Surround Install | Home Depot | Boulder AMEX | 11149 | NA | Credit Card | RIW-CFR-10-026
2025-12-10 | 10 | 15 | Misc. Shower/Surround Install Material | From Home Depot - Kitchen and Bath Sealant White | 449.24 | 0 | 449.24 |  |  |  | Glass Shower/Surround Install | Home Depot | Boulder AMEX | 11167 | NA | Credit Card | RIW-CFR-10-027
2025-12-11 | 10 | 15 | Misc. Shower/Surround Install Material | From Home Depot - Window and Door Sealant White | 132.19 | 0 | 132.19 |  |  |  | Glass Shower/Surround Install | Home Depot | Boulder AMEX | 11169 | NA | Credit Card | RIW-CFR-10-028
2025-12-17 | 10 | 15 | Misc. Shower/Surround Install Material | From Home Depot - Painter's Tape, Epoxy and Adhesives & Fiberglass Resins | 71.63 | 0 | 71.63 |  |  |  | Glass Shower/Surround Install | Home Depot | Boulder AMEX | 11192 | NA | Credit Card | RIW-CFR-10-029
2026-01-14 | 10 | 16 | Misc. Shower/Surround Install Material | From Home Depot - Tub and Tile Silicone Caulk & Window, Door and Trim Sealant | 82.67 | 0 | 82.67 |  |  |  | Glass Shower/Surround Install | Home Depot | Boulder AMEX | 11228 | NA | Credit Card | RIW-CFR-10-030
2026-01-09 | 10 | 16 | BBQ Grill | From BBQ | 4847.47 | 0 | 4847.47 |  |  |  | BBQ Grill | BBQ Guys | Boulder AMEX | 11246 | NA | Credit Card | RIW-CFR-10-031
2026-01-09 | 10 | 16 | Misc. Shower/Surround Install Material | From Home Depot - Steel Enhancing Polish, Window and Door Sealant | 194.96 | 0 | 194.96 |  |  |  | Glass Shower/Surround Install | Home Depot | Boulder AMEX | 11247 | NA | Credit Card | RIW-CFR-10-032
2025-12-30 | 10 | 16 | Fire Extinguisher Cabinets | From Texas Fire Extinguisher | 5306.72 | 0 | 5306.72 |  |  |  | Fire Extinguisher Material | Texas Fire Extinguisher | Jaimin AMEX | 11271 | NA | Credit Card | RIW-CFR-10-033
2026-01-22 | 10 | 16 | Misc. Shower/Surround Install Material | From Home Depot - Kitchen & Bath Sealant White | 278.51 | 0 | 278.51 |  |  |  | Glass Shower/Surround Install | Home Depot | Boulder AMEX | 12198 | NA | Credit Card | RIW-CFR-10-034
2025-10-28 | 10 | 16 | Caulking Material | From Jordan Toplano | 533 | 0 | 533 |  |  |  | Glass Shower/Surround Install | Jordan Toplano | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-10-035
2025-12-08 | 10 | 16 | Caulking Material | From ESSA Group of America | 519.6 | 0 | 519.6 |  |  |  | Glass Shower/Surround Install | ESSA Group of America | Boulder AMEX | 11216 | NA | Credit Card | RIW-CFR-10-036
2026-02-26 | 10 | 16 | Shower Door Install | From TKG Construction | 13750 | 0 | 13750 |  |  |  | Glass Shower/Surround Install | TKG Construction | RI Waxahachie | 11285 | No | RI Waxahachie | RIW-CFR-10-037
2026-02-26 | 10 | 16 | Bathroom Hardware Install | From TKG Construction | 7500 | 0 | 7500 |  |  |  | Toilet Material | TKG Construction | RI Waxahachie | 11285 | No | RI Waxahachie | RIW-CFR-10-038
2026-02-13 | 10 | 17 | Bathroom Partitions | From Normex Construction | 8505 | 0 | 8505 |  |  |  | Toilet Material | Normex Construction | Jaimin AMEX | 12234 | NA | Credit Card
2026-02-10 | 10 | 17 | Misc. Shower/Surround Install Material | From Lowes - Low Profile Sidewall Vent Materials | 345.97 | 0 | 345.97 |  |  |  | Glass Shower/Surround Install | Lowes | Boulder AMEX | 12340 | NA | Credit Card
2026-02-25 | 10 | 17 | Misc. Shower/Surround Install Material | From Home Depot - Lavatory Protector | 236.2 | 0 | 236.2 |  |  |  | Glass Shower/Surround Install | Home Depot | Boulder AMEX | 12453 | NA | Credit Card
2026-02-25 | 10 | 17 | Toilet Material | From Home Depot - Grab Bar | 152.85 | 0 | 152.85 |  |  |  | Toilet Material | Home Depot | Boulder AMEX | 12458 | NA | Credit Card
2026-03-02 | 10 | 17 | Misc. Shower/Surround Install Material | From Home Depot - Kitchen & Bath Sealant, Empoxy & Resins | 80.82 | 0 | 80.82 |  |  |  | Glass Shower/Surround Install | Home Depot | Boulder AMEX | 12485 | NA | Credit Card
2026-03-02 | 10 | 17 | Misc. Shower/Surround Install Material | From Home Depot - Silicone Caulk & Thinset Mortar | 139 | 0 | 139 |  |  |  | Glass Shower/Surround Install | Home Depot | Boulder AMEX | 12486 | NA | Credit Card
2026-03-02 | 10 | 17 | Misc. Shower/Surround Install Material | From Home Depot - Silicone Caulk & Gun | 129.75 | 0 | 129.75 |  |  |  | Glass Shower/Surround Install | Home Depot | Boulder AMEX | 12488 | NA | Credit Card
2026-02-26 | 10 | 17 | Misc. Shower/Surround Install Material | From Home Depot - Flush Right Hand Wing & Drywall Material | 263.91 | 0 | 263.91 |  |  |  | Glass Shower/Surround Install | Home Depot | Boulder AMEX | 12501 | NA | Credit Card
2026-02-24 | 10 | 17 | Toilet Material | From Home Depot - Grab Bar | 297.23 | 0 | 297.23 |  |  |  | Toilet Material | Home Depot | Boulder AMEX | 12512 | NA | Credit Card
2026-02-24 | 10 | 17 | ADA Shower Seat | From Amazon | 184.01 | 0 | 184.01 |  |  |  | Glass Shower/Surround Install | Amazon | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-24 | 10 | 17 | Soap Trap Showers | From Amazon | 51.94 | 0 | 51.94 |  |  |  | Glass Shower/Surround Install | Amazon | Boulder AMEX | [TBD] | NA | Credit Card
2026-03-01 | 10 | 17 | Soap Dish Showers | From Amazon | 75.76 | 0 | 75.76 |  |  |  | Glass Shower/Surround Install | Amazon | Boulder AMEX | [TBD] | NA | Credit Card
[To Be Paid] | 10 | 17 | Shower Glass Doors | From TKG Construction - Pay App 11 | 2450 | 0 | 2450 |  |  |  | Glass Shower/Surround Install | TKG Construction | [To Be Paid] | [TBD] | No | [To Be Paid]
11. Furnishings
| 11 | 11 | Draw 11 Funds - Reimbursement |  |  |  |  | 10288.08 | 0 | 10288.08
| 11 | 14 | Draw 14 Funds - Reimbursement |  |  |  |  | 22615.56 | 0 | 22615.56
| 11 | 15 | Draw 15 Funds - Reimbursement |  |  |  |  | 78812.13 | 0 | 78812.13
| 11 | 15 | Draw 15 Funds - To Be Paid |  |  |  |  | 35000 | 0 | 35000
| 11 | 16 | Draw 16 Funds - Reimbursement |  |  |  |  | 2410.15 | 0 | 2410.15
| 11 | 16 | Draw 16 Funds - To Be Paid |  |  |  |  | 33500 | 0 | 33500
| 11 | 17 | Draw 17 Funds - Reimbursement |  |  |  |  | 13539.63 | 0 | 13539.63
| 11 | 17 | Draw 17 Funds - To Be Paid |  |  |  |  | 28000 | 0 | 28000
2025-07-25 | 11 | 11 | Undermount Vanity Sink | From JMHS - Bathroom Scope 50% Deposit - RIWTX-102 | 2428.92 | 0 | 2428.92 |  |  |  | Quartz Materials & Public Install | JMHS | RI Waxahachie | 10679 | NA | ACH | RIW-CFR-11-001
2025-07-25 | 11 | 11 | Fixed Glass Shower Panel and Hinge Shower Door | From JMHS - Bathroom Scope 50% Deposit - RIWTX-102 | 7859.16 | 0 | 7859.16 |  |  |  | Tub/Shower Surrounds and Pan | JMHS | RI Waxahachie | 10679 | NA | ACH | RIW-CFR-11-002
2025-11-03 | 11 | 14 | Undermount Vanity Sink | From JMHS - Bathroom Scope Remaining 50% Payment - RIWTX-102 | 2428.92 | 0 | 2428.92 |  |  |  | Quartz Materials & Public Install | JMHS | RI Waxahachie | 10679 | NA | ACH | RIW-CFR-11-003
2025-11-03 | 11 | 14 | Fixed Glass Shower Panel and Hinge Shower Door | From JMHS - Bathroom Scope Remaining 50% Payment - RIWTX-102 | 8029.14 | 0 | 8029.14 |  |  |  | Tub/Shower Surrounds and Pan | JMHS | RI Waxahachie | 10679 | NA | ACH | RIW-CFR-11-004
2025-09-19 | 11 | 14 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 405 | 0 | 405 |  |  |  | FF&E Installation | David Salinas | RI Waxahachie | 10883 | NA | ACH | RIW-CFR-11-005
2025-09-12 | 11 | 14 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 615 | 0 | 615 |  |  |  | FF&E Installation | David Salinas | RI Waxahachie | 10884 | NA | ACH | RIW-CFR-11-006
2025-09-26 | 11 | 14 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 630 | 0 | 630 |  |  |  | FF&E Installation | David Salinas | RI Waxahachie | 10938 | NA | ACH | RIW-CFR-11-007
2025-10-03 | 11 | 14 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 585 | 0 | 585 |  |  |  | FF&E Installation | David Salinas | RI Waxahachie | 10985 | NA | ACH | RIW-CFR-11-008
2025-10-10 | 11 | 14 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 375 | 0 | 375 |  |  |  | FF&E Installation | David Salinas | RI Waxahachie | 10986 | NA | ACH | RIW-CFR-11-009
2025-10-17 | 11 | 14 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 510 | 0 | 510 |  |  |  | FF&E Installation | David Salinas | RI Waxahachie | 10987 | NA | ACH | RIW-CFR-11-010
2025-10-24 | 11 | 14 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 615 | 0 | 615 |  |  |  | FF&E Installation | David Salinas | RI Waxahachie | 10988 | NA | ACH | RIW-CFR-11-011
2025-09-05 | 11 | 14 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 660 | 0 | 660 |  |  |  | FF&E Installation | David Salinas | RI Waxahachie | 10989 | NA | ACH | RIW-CFR-11-012
2025-09-05 | 11 | 14 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 1045 | 0 | 1045 |  |  |  | FF&E Installation | Rodolfo Rios | RI Waxahachie | 10990 | NA | ACH | RIW-CFR-11-013
2025-10-03 | 11 | 14 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 1068.75 | 0 | 1068.75 |  |  |  | FF&E Installation | Rodolfo Rios | RI Waxahachie | 10991 | NA | ACH | RIW-CFR-11-014
2025-10-10 | 11 | 14 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 760 | 0 | 760 |  |  |  | FF&E Installation | Rodolfo Rios | RI Waxahachie | 10992 | NA | ACH | RIW-CFR-11-015
2025-10-17 | 11 | 14 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 1068.75 | 0 | 1068.75 |  |  |  | FF&E Installation | Rodolfo Rios | RI Waxahachie | 10993 | NA | ACH | RIW-CFR-11-016
2025-10-24 | 11 | 14 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 1068.75 | 0 | 1068.75 |  |  |  | FF&E Installation | Rodolfo Rios | RI Waxahachie | 10994 | NA | ACH | RIW-CFR-11-017
2025-10-31 | 11 | 14 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 1065 | 0 | 1065 |  |  |  | FF&E Installation | David Salinas | RI Waxahachie | 11011 | NA | ACH | RIW-CFR-11-018
2025-10-31 | 11 | 14 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 1686.25 | 0 | 1686.25 |  |  |  | FF&E Installation | Rodolfo Rios | RI Waxahachie | 11012 | NA | ACH | RIW-CFR-11-019
2025-11-03 | 11 | 15 | FF&E Installation | From Home Depot - Blue Medium Duty Tarp | 104.35 | 0 | 104.35 |  |  |  | FF&E Installation | Home Depot | Boulder AMEX | 11044 | NA | Credit Card | RIW-CFR-11-020
2025-11-04 | 11 | 15 | FF&E Installation | From Home Depot - Wood Moving Dolly | 66.64 | 0 | 66.64 |  |  |  | FF&E Installation | Home Depot | Boulder AMEX | 11046 | NA | Credit Card | RIW-CFR-11-021
2025-11-04 | 11 | 15 | FF&E Installation | From Home Depot - Blue Medium Duty Tarp | 269.52 | 0 | 269.52 |  |  |  | FF&E Installation | Home Depot | Boulder AMEX | 11047 | NA | Credit Card | RIW-CFR-11-022
2025-12-04 | 11 | 15 | FF&E Installation | From Home Depot - Bidirectional Break Shim & Painters Multi-Tool | 31.2 | 0 | 31.2 |  |  |  | FF&E Installation | Home Depot | Boulder AMEX | 11116 | NA | Credit Card | RIW-CFR-11-023
2025-12-05 | 11 | 15 | FF&E Installation | From Home Depot - Reversible Drill & Multi-Tool Oscillating Blade, etc. | 328.12 | 0 | 328.12 |  |  |  | FF&E Installation | Home Depot | Boulder AMEX | 11117 | NA | Credit Card | RIW-CFR-11-024
2025-11-07 | 11 | 15 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 1187.5 | 0 | 1187.5 |  |  |  | FF&E Installation | Rodolfo Rios | RI Waxahachie | 11121 | NA | ACH | RIW-CFR-11-025
2025-11-14 | 11 | 15 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 1068.75 | 0 | 1068.75 |  |  |  | FF&E Installation | Rodolfo Rios | RI Waxahachie | 11122 | NA | ACH | RIW-CFR-11-026
2025-11-21 | 11 | 15 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 1235 | 0 | 1235 |  |  |  | FF&E Installation | Rodolfo Rios | RI Waxahachie | 11123 | NA | ACH | RIW-CFR-11-027
2025-11-28 | 11 | 15 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 1068.75 | 0 | 1068.75 |  |  |  | FF&E Installation | Rodolfo Rios | RI Waxahachie | 11124 | NA | ACH | RIW-CFR-11-028
2025-12-05 | 11 | 15 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 1187.5 | 0 | 1187.5 |  |  |  | FF&E Installation | Rodolfo Rios | RI Waxahachie | 11125 | NA | ACH | RIW-CFR-11-029
2025-11-07 | 11 | 15 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 690 | 0 | 690 |  |  |  | FF&E Installation | David Salinas | RI Waxahachie | 11126 | NA | ACH | RIW-CFR-11-030
2025-11-14 | 11 | 15 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 780 | 0 | 780 |  |  |  | FF&E Installation | David Salinas | RI Waxahachie | 11127 | NA | ACH | RIW-CFR-11-031
2025-11-21 | 11 | 15 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 690 | 0 | 690 |  |  |  | FF&E Installation | David Salinas | RI Waxahachie | 11128 | NA | ACH | RIW-CFR-11-032
2025-11-28 | 11 | 15 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 1280 | 0 | 1280 |  |  |  | FF&E Installation | David Salinas | RI Waxahachie | 11129 | NA | ACH | RIW-CFR-11-033
2025-12-05 | 11 | 15 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 735 | 0 | 735 |  |  |  | FF&E Installation | David Salinas | RI Waxahachie | 11130 | NA | ACH | RIW-CFR-11-034
2025-11-25 | 11 | 15 | FF&E Installation | From Home Depot - Stretch Wrap | 324.62 | 0 | 324.62 |  |  |  | FF&E Installation | Home Depot | Boulder AMEX | 11131 | NA | Credit Card | RIW-CFR-11-035
2025-12-06 | 11 | 15 | FF&E Installation | From Home Depot - Oscillating Blade, Thread Coated Exterior Wood Screws, etc. | 132.81 | 0 | 132.81 |  |  |  | FF&E Installation | Home Depot | Boulder AMEX | 11133 | NA | Credit Card | RIW-CFR-11-036
2025-12-12 | 11 | 15 | FF&E Installation | From TKG Construction | 25000 | 0 | 25000 |  |  |  | FF&E Installation | TKG Construction | RI Waxahachie | 11146 | NA | ACH | RIW-CFR-11-037
2025-12-12 | 11 | 15 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 495 | 0 | 495 |  |  |  | FF&E Installation | David Salinas | RI Waxahachie | 11147 | NA | ACH | RIW-CFR-11-038
2025-12-12 | 11 | 15 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 1725 | 0 | 1725 |  |  |  | FF&E Installation | Rodolfo Rios | RI Waxahachie | 11148 | NA | ACH | RIW-CFR-11-039
2025-12-19 | 11 | 15 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 1725 | 0 | 1725 |  |  |  | FF&E Installation | David Salinas | RI Waxahachie | 11152 | NA | ACH | RIW-CFR-11-040
2025-12-19 | 11 | 15 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 1520 | 0 | 1520 |  |  |  | FF&E Installation | Rodolfo Rios | RI Waxahachie | 11153 | NA | ACH | RIW-CFR-11-041
2025-12-16 | 11 | 15 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 2500 | 0 | 2500 |  |  |  | FF&E Installation | Rodolfo Rios | RI Waxahachie | 11156 | NA | ACH | RIW-CFR-11-042
2025-12-09 | 11 | 15 | FF&E Installation | From Home Depot - Markers & Wax Crayons | 13.43 | 0 | 13.43 |  |  |  | FF&E Installation | Home Depot | Boulder AMEX | 11166 | NA | Credit Card | RIW-CFR-11-043
2025-12-17 | 11 | 15 | Granite Installation | From Home Depot - All-Purpose Acrylic Latex Caulk | 264.02 | 0 | 264.02 |  |  |  | Quartz Materials & Public Install | Home Depot | Boulder AMEX | 11191 | NA | Credit Card | RIW-CFR-11-044
2025-12-18 | 11 | 15 | Granite Installation | From Home Depot - Construction Adhesive, Japanese Hardwood Blade | 99.56 | 0 | 99.56 |  |  |  | Quartz Materials & Public Install | Home Depot | Boulder AMEX | 11196 | NA | Credit Card | RIW-CFR-11-045
2025-12-20 | 11 | 15 | FF&E Installation | From Home Depot - Hex Drive Stainless Steel Lag Screw | 102.86 | 0 | 102.86 |  |  |  | FF&E Installation | Home Depot | Boulder AMEX | 11206 | NA | Credit Card | RIW-CFR-11-046
2025-12-26 | 11 | 15 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 1117.5 | 0 | 1117.5 |  |  |  | FF&E Installation | David Salinas | RI Waxahachie | 11212 | NA | ACH | RIW-CFR-11-047
2025-12-26 | 11 | 15 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 1237.5 | 0 | 1237.5 |  |  |  | FF&E Installation | Rodolfo Rios | RI Waxahachie | 11213 | NA | ACH | RIW-CFR-11-048
2025-12-26 | 11 | 15 | Granite Material & Labor | From TKG Construction | 30000 | 0 | 30000 |  |  |  | Quartz Materials & Public Install | TKG Construction | RI Waxahachie | 11214 | NA | ACH | RIW-CFR-11-049
2026-01-02 | 11 | 15 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 630 | 0 | 630 |  |  |  | FF&E Installation | David Salinas | RI Waxahachie | 11219 | NA | ACH | RIW-CFR-11-050
2026-01-02 | 11 | 15 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 1202.5 | 0 | 1202.5 |  |  |  | FF&E Installation | Rodolfo Rios | RI Waxahachie | 11220 | NA | ACH | RIW-CFR-11-051
2026-01-30 | 11 | 15 | Change Order - FF&E Installation | From TKG Construction | 18000 | 0 | 18000 |  |  |  | FF&E Installation | TKG Construction | RI Waxahachie | 12175 | No | ACH | RIW-CFR-11-052
2026-01-30 | 11 | 15 | Tub/Shower Surround Installation | From TKG Construction | 12000 | 0 | 12000 |  |  |  | Tub/Shower Surrounds and Pan | TKG Construction | RI Waxahachie | 12175 | No | ACH | RIW-CFR-11-053
2026-01-15 | 11 | 15 | Tub/Shower Surround Installation | From TKG Construction | 5000 | 0 | 5000 |  |  |  | Tub/Shower Surrounds and Pan | TKG Construction | RI Waxahachie | 12175 | No | ACH | RIW-CFR-11-053
2026-01-14 | 11 | 16 | Granite Installation | From Home Depot - Sanded Ceramic Tile Caulk | 11.4 | 0 | 11.4 |  |  |  | Quartz Materials & Public Install | Home Depot | Boulder AMEX | 11227 | NA | Credit Card | RIW-CFR-11-054
2026-01-07 | 11 | 16 | Granite Installation | From Home Depot - Acrylic Latex Plus Silicone Caulk | 684.43 | 0 | 684.43 |  |  |  | Quartz Materials & Public Install | Home Depot | Boulder AMEX | 11241 | NA | Credit Card | RIW-CFR-11-055
2026-01-08 | 11 | 16 | Granite Installation | From Home Depot - Steel Round Tube, Head Screw, Spray Paint & Primer | 122.8 | 0 | 122.8 |  |  |  | Quartz Materials & Public Install | Home Depot | Boulder AMEX | 11244 | NA | Credit Card | RIW-CFR-11-056
2025-12-31 | 11 | 16 | Granite Installation | From Home Depot - Adhesive & Circular Saw Blade | 106.49 | 0 | 106.49 |  |  |  | Quartz Materials & Public Install | Home Depot | Boulder AMEX | 11268 | NA | Credit Card | RIW-CFR-11-057
2025-12-12 | 11 | 16 | Granite Glue and Caulking | From Gran Quartz | 1485.03 | 0 | 1485.03 |  |  |  | Quartz Materials & Public Install | Gran Quartz | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-11-058
[To Be Paid] | 11 | 16 | Guestroom Granite Install | From TKG Construction | 22070 | 0 | 22070 |  |  |  | Quartz Materials & Public Install | TKG Construction | [To Be Paid] | 11285 | No | [To Be Paid] | RIW-CFR-11-059
2026-02-12 | 11 | 16 | Guestroom Granite Install | From TKG Construction | 1930 | 0 | 1930 |  |  |  | Quartz Materials & Public Install | TKG Construction | RI Waxahachie | 11285 | No | ACH | RIW-CFR-11-059
2026-02-09 | 11 | 16 | Tub/Shower Surrounds and Pan Install | From TKG Construction | 9500 | 0 | 9500 |  |  |  | Tub/Shower Surrounds and Pan | TKG Construction | RI Waxahachie | 11285 | No | ACH | RIW-CFR-11-060
2026-02-18 | 11 | 17 | Granite Installation | From Home Depot - Sealant, Adhesive And Silicone Caulk | 218.62 | 0 | 218.62 |  |  |  | Quartz Materials & Public Install | Home Depot | Boulder AMEX | 12229 | NA | Credit Card
2026-02-13 | 11 | 17 | Granite Installation | From Home Depot - Silicone Caulk, Caulk Guns and Sealant Cleaner | 580.22 | 0 | 580.22 |  |  |  | Quartz Materials & Public Install | Home Depot | Boulder AMEX | 12262 | NA | Credit Card
2026-02-02 | 11 | 17 | Granite Installation | From Home Depot - Silicone Caulk and Sealant | 136.78 | 0 | 136.78 |  |  |  | Quartz Materials & Public Install | Home Depot | Boulder AMEX | 12304 | NA | Credit Card
2026-02-20 | 11 | 17 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 1401.25 | 0 | 1401.25 |  |  |  | FF&E Installation | Rodolfo Rios | RI Waxahachie | 12332 | NA | ACH
2026-02-24 | 11 | 17 | Granite Installation | From Home Depot - Granite, Slate, Ceramic & Glass Tiles Drill Bit | 78.85 | 0 | 78.85 |  |  |  | Quartz Materials & Public Install | Home Depot | Boulder AMEX | 12355 | NA | Credit Card
2026-02-24 | 11 | 17 | Granite Installation | From Home Depot - Caulk, Cleaner, And Contractor Trash Bags | 218.11 | 0 | 218.11 |  |  |  | Quartz Materials & Public Install | Home Depot | Boulder AMEX | 12357 | NA | Credit Card
2026-02-27 | 11 | 17 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 1686.25 | 0 | 1686.25 |  |  |  | FF&E Installation | Rodolfo Rios | RI Waxahachie | 12496 | NA | ACH
2026-02-13 | 11 | 17 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 373.75 | 0 | 373.75 |  |  |  | FF&E Installation | David Salinas | RI Waxahachie | 12497 | NA | ACH
2026-02-13 | 11 | 17 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 1812.5 | 0 | 1812.5 |  |  |  | FF&E Installation | Rodolfo Rios | RI Waxahachie | 12498 | NA | ACH
2026-02-06 | 11 | 17 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 1812.5 | 0 | 1812.5 |  |  |  | FF&E Installation | Rodolfo Rios | RI Waxahachie | [TBD] | NA | ACH
2026-02-06 | 11 | 17 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 371.25 | 0 | 371.25 |  |  |  | FF&E Installation | David Salinas | RI Waxahachie | [TBD] | NA | ACH
2026-02-13 | 11 | 17 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 2600 | 0 | 2600 |  |  |  | FF&E Installation | David Salinas | Boulder | [TBD] | NA | ACH
2025-11-30 | 11 | 17 | Closet Shelves | From Amazon | 503.35 | 0 | 503.35 |  |  |  | FF&E Installation | Amazon | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-06 | 11 | 17 | Closet Shelves | From Amazon | 573.2 | 0 | 573.2 |  |  |  | FF&E Installation | Amazon | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-08 | 11 | 17 | Closet Shelves | From Amazon | 515.88 | 0 | 515.88 |  |  |  | FF&E Installation | Amazon | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-09 | 11 | 17 | Closet Shelves | From Amazon | 630.52 | 0 | 630.52 |  |  |  | FF&E Installation | Amazon | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-22 | 11 | 17 | Closet Magnet | From Amazon | 16.23 | 0 | 16.23 |  |  |  | FF&E Installation | Amazon | Boulder AMEX | [TBD] | NA | Credit Card
2026-03-03 | 11 | 17 | Closet Magnet | From Amazon | 10.37 | 0 | 10.37 |  |  |  | FF&E Installation | Amazon | Boulder AMEX | [TBD] | NA | Credit Card
[To Be Paid] | 11 | 17 | Guestroom Granite Install | From TKG Construction - Pay App 11 | 1000 | 0 | 1000 |  |  |  | Quartz Materials & Public Install | TKG Construction | [To Be Paid] | [TBD] | No | [To Be Paid]
[To Be Paid] | 11 | 17 | FF&E/Delivery/Others | From TKG Construction - Pay App 11 | 27000 | 0 | 27000 |  |  |  | Quartz Materials & Public Install | TKG Construction | [To Be Paid] | [TBD] | No | [To Be Paid]
12. Swimming Pool
| 12 | 10 | Draw 10 Funds - To Be Paid |  |  |  |  | 76560 | 7656 | 68904
| 12 | 13 | Draw 13 Funds - To Be Paid |  |  |  |  | 1294.7 | 129.47 | 1165.23
| 12 | 14 | Draw 14 Funds - To Be Paid |  |  |  |  | 6496.1 | 0 | 6496.1
| 12 | 16 | Draw 16 Funds - Reimbursement |  |  |  |  | 41121.8189 | 2565.1289 | 38556.69
| 12 | 16 | Draw 16 Funds - To Be Paid |  |  |  |  | 5000 | 0 | 5000
| 12 | 17 | Draw 17 Funds - Reimbursement |  |  |  |  | 53234.93 | 3944 | 49290.93
| 12 | 17 | Draw 17 Funds - To Be Paid |  |  |  |  | 23156.15 | 0 | 23156.15
2025-07-18 | 12 | 10 | Swimming Pool Labor and Material | From San Diego Pool's and Shotcrete - Pay App 01 | 76560 | 7656 | 68904 |  |  |  | Swimming Pool | San Diego Pools and Shotcrete | RI Waxahachie | 10675 | No | ACH | RIW-CFR-12-001
2026-01-30 | 12 | 13 | Elevator Material & Installation Labor | From Kone - Allocated Payment (Pay App 03) | 1294.7 | 129.47 | 1165.23 |  |  |  | Swimming Pool | Kone | RI Waxahachie | 10929 | No | [To Be Paid] | RIW-CFR-12-002
[To Be Paid] | 12 | 14 | Elevator - Equipment | From EquipmentShare | 6496.1 | 0 | 6496.1 |  |  |  | Swimming Pool | EquipmentShare | RI Waxahachie | 11056 | NA | [To Be Paid] | RIW-CFR-12-003
2026-01-26 | 12 | 16 | Millwork 50% Final Payment | From Graniti Vicentia | 11769.86 | 0 | 11769.86 |  |  |  | Swimming Pool | Graniti Vicentia | Jaimin AMEX | 10857 | NA | Credit Card | RIW-CFR-12-004
2026-01-30 | 12 | 16 | Elevator Material & Installation Labor | From Kone - Allocated Payment Pay App 04 | 25651.2889 | 2565.1289 | 23086.16 |  |  |  | Swimming Pool | Kone | RI Waxahachie | 12176 | NA | Wire | RIW-CFR-12-005
2026-01-28 | 12 | 16 | Jobsite Equipment | From EquipmentShare | 3495.72 | 0 | 3495.72 |  |  |  | Swimming Pool | EquipmentShare | Jaimin AMEX | 12203 | NA | Credit Card | RIW-CFR-12-006
2025-08-18 | 12 | 16 | Safety Net for Elevator | From Amazon | 204.95 | 0 | 204.95 |  |  |  | Swimming Pool | Amazon | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-12-007
2026-02-09 | 12 | 16 | FF&E Installation | From TKG Construction | 5000 | 0 | 5000 |  |  |  | Swimming Pool | TKG Construction | RI Waxahachie | 11285 | No | ACH | RIW-CFR-12-008
2026-02-11 | 12 | 17 | Framing Material | From Home Depot - Lumber, Screws, Sheathing, Panel | 1394.07 | 0 | 1394.07 |  |  |  | Swimming Pool | Home Depot | Boulder AMEX | 12209 | NA | Credit Card
2026-02-12 | 12 | 17 | Framing Material | From Home Depot - Tape Measure, Aviation Snips and Gypsum Board | 165.16 | 0 | 165.16 |  |  |  | Swimming Pool | Home Depot | Boulder AMEX | 12213 | NA | Credit Card
2026-02-09 | 12 | 17 | Framing Material | From Home Depot - Sanded Pine Plywood Sheets | 653.64 | 0 | 653.64 |  |  |  | Swimming Pool | Home Depot | Boulder AMEX | 12215 | NA | Credit Card
2026-02-15 | 12 | 17 | Framing Material | From Home Depot - Parawedge Wedge Anchors Pcket | 31.44 | 0 | 31.44 |  |  |  | Swimming Pool | Home Depot | Boulder AMEX | 12249 | NA | Credit Card
2026-02-13 | 12 | 17 | Framing Material | From Home Depot - Pine Plywood, Lumber and Screws | 302.03 | 0 | 302.03 |  |  |  | Swimming Pool | Home Depot | Boulder AMEX | 12263 | NA | Credit Card
2026-02-13 | 12 | 17 | Framing Material | From Home Depot - Flathead Screws and Insert Bit | 35.76 | 0 | 35.76 |  |  |  | Swimming Pool | Home Depot | Boulder AMEX | 12264 | NA | Credit Card
2026-02-12 | 12 | 17 | Framing Material | From Home Depot - 5/8 In Firecode Gypsum Board Sheets | 25.59 | 0 | 25.59 |  |  |  | Swimming Pool | Home Depot | Boulder AMEX | 12268 | NA | Credit Card
2026-02-10 | 12 | 17 | CMU Block Material | From Home Depot - CMU Blocks-Concrete Block and Brick Tie | 663.73 | 0 | 663.73 |  |  |  | Swimming Pool | Home Depot | Boulder AMEX | 12288 | NA | Credit Card
2026-02-10 | 12 | 17 | CMU Block Material | From Home Depot - Refund | -602.96 | 0 | -602.96 |  |  |  | Swimming Pool | Home Depot | Boulder AMEX | 12288 | NA | Credit Card
2026-02-09 | 12 | 17 | Framing Material | From Home Depot - Lumber, machine wash Mop and Cleaning Products | 621.97 | 0 | 621.97 |  |  |  | Swimming Pool | Home Depot | Boulder AMEX | 12293 | NA | Credit Card
2026-02-05 | 12 | 17 | Framing Material | From Home Depot - Pine Plywood and Lumber | 526.12 | 0 | 526.12 |  |  |  | Swimming Pool | Home Depot | Boulder AMEX | 12299 | NA | Credit Card
2026-02-02 | 12 | 17 | Framing Material | From Home Depot - Dimensional Lumber (2x6x10) | 188.23 | 0 | 188.23 |  |  |  | Swimming Pool | Home Depot | Boulder AMEX | 12305 | NA | Credit Card
2026-02-11 | 12 | 17 | Framing Material | From Lowes - Framing Lumber And Hardware Kit | 241.9 | 0 | 241.9 |  |  |  | Swimming Pool | Lowes | Boulder AMEX | 12338 | NA | Credit Card
2026-02-21 | 12 | 17 | Framing Material | From Home Depot - Screws | 36.53 | 0 | 36.53 |  |  |  | Swimming Pool | Home Depot | Boulder AMEX | 12347 | NA | Credit Card
2026-02-25 | 12 | 17 | Trench Safety Box Rental For Utility Work | From National Trench Safety - Trench Safety Box Rental For Utility Work | 1159.58 | 0 | 1159.58 |  |  |  | Swimming Pool | National Trench Safety | Jaimin AMEX | 12403 | NA | Credit Card
2026-02-28 | 12 | 17 | Framing Material | From Home Depot - Scissors & Elastic Straps | 73.46 | 0 | 73.46 |  |  |  | Swimming Pool | Home Depot | Boulder AMEX | 12464 | NA | Credit Card
2026-02-27 | 12 | 17 | Framing Material | From Home Depot - Washer, Bolt & Drill Bits | 68.11 | 0 | 68.11 |  |  |  | Swimming Pool | Home Depot | Boulder AMEX | 12466 | NA | Credit Card
2026-02-17 | 12 | 17 | Swimming Pool Labor and Material | From San Diego Pools and Shotcrete | 39440 | 3944 | 35496 |  |  |  | Swimming Pool | San Diego Pools and Shotcrete | RI Waxahachie | 12477 | No | ACH
2026-02-09 | 12 | 17 | Framing Labor - Misc. Punch List | From Martin Aguilar | 2000 | 0 | 2000 |  |  |  | Swimming Pool | Martin Aguilar | RI Waxahachie | 12481 | NA | Check
2026-02-26 | 12 | 17 | Framing Material | From Home Depot - Zinc Flat Washer, Nut & Alloy Bit | 156.17 | 0 | 156.17 |  |  |  | Swimming Pool | Home Depot | Boulder AMEX | 12499 | NA | Credit Card
2026-02-13 | 12 | 17 | Jobsite Material Expense | From Home Depot | 552.95 | 0 | 552.95 |  |  |  | Swimming Pool | Home Depot | Boulder AMEX | 12510 | NA | Credit Card
2026-02-20 | 12 | 17 | Framing Material | From Martin Aguilar | 1900 | 0 | 1900 |  |  |  | Swimming Pool | Martin Aguilar | RI Waxahachie | [TBD] | NA | Check
2026-02-06 | 12 | 17 | Framing Material | From Harbor Freight | 376.38 | 0 | 376.38 |  |  |  | Swimming Pool | Harbor Freight | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-17 | 12 | 17 | Equipment Insurance | From Liberty Mutual | 170.23 | 0 | 170.23 |  |  |  | Swimming Pool | Liberty Mutual | Boulder AMEX | [TBD] | NA | Credit Card
2026-01-13 | 12 | 17 | Jobsite Expense | From Home Depot | 290.39 | 0 | 290.39 |  |  |  | Swimming Pool | Home Depot | Boulder AMEX | 12526 | NA | Credit Card
2026-01-22 | 12 | 17 | Jobsite Expense | From Home Depot | 187.58 | 0 | 187.58 |  |  |  | Swimming Pool | Home Depot | Boulder AMEX | [TBD] | NA | Credit Card
2026-01-22 | 12 | 17 | Jobsite Expense | From Home Depot | 144.71 | 0 | 144.71 |  |  |  | Swimming Pool | Home Depot | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-10 | 12 | 17 | Framing Material | From Lowes - Framing Lumber And Fasteners Refund | -3332.89 | 0 | -3332.89 |  |  |  | Swimming Pool | Lowes | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-20 | 12 | 17 | Jobsite Expense | From Home Depot | 421.2 | 0 | 421.2 |  |  |  | Swimming Pool | Home Depot | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-20 | 12 | 17 | Jobsite Expense | From Home Depot | 16.79 | 0 | 16.79 |  |  |  | Swimming Pool | Home Depot | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-19 | 12 | 17 | Pool Sconces | From Amazon | 235.76 | 0 | 235.76 |  |  |  | Swimming Pool | Amazon | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-19 | 12 | 17 | Sconces | From Amazon | 71.94 | 0 | 71.94 |  |  |  | Swimming Pool | Amazon | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-22 | 12 | 17 | Linen Chute | From Amazon | 67.64 | 0 | 67.64 |  |  |  | Swimming Pool | Amazon | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-22 | 12 | 17 | Linen Chute | From Amazon | 18.39 | 0 | 18.39 |  |  |  | Swimming Pool | Amazon | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-25 | 12 | 17 | Sconces | From Amazon | 497 | 0 | 497 |  |  |  | Swimming Pool | Amazon | Boulder AMEX | [TBD] | NA | Credit Card
2025-11-17 | 12 | 17 | Equipment Rental/Repair |  | 1488.12 | 0 | 1488.12 |  |  |  | Swimming Pool | Auto-Tech | Boulder AMEX | [TBD] | NA | Credit Card
2025-07-08 | 12 | 17 | Jobsite Office Equipment | From Best Buy | 1110.82 | 0 | 1110.82 |  |  |  | Swimming Pool | Best Buy | Boulder AMEX | [TBD] | NA | Credit Card
2025-07-08 | 12 | 17 | Jobsite Office Equipment | From Best Buy | 714.43 | 0 | 714.43 |  |  |  | Swimming Pool | Best Buy | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-07 | 12 | 17 | Liquid Rubber Elevator | From Amazon | 865.75 | 0 | 865.75 |  |  |  | Swimming Pool | Amazon | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-15 | 12 | 17 | Glasses |  | 257.21 | 0 | 257.21 |  |  |  | Swimming Pool | Oakley | Boulder AMEX | [TBD] | NA | Credit Card
[To Be Paid] | 12 | 17 | Marriott Requirement - 360 Capture Subscription | From Openspace | 6156.15 | 0 | 6156.15 |  |  |  | Swimming Pool | Openspace | [To Be Paid] | 11288 | NA | [To Be Paid]
[To Be Paid] | 12 | 17 | Extra Labor Per Discussion - Sai & Aniket | From Boulder Construction | 6000 | 0 | 6000 |  |  |  | Swimming Pool | Boulder Construction | [To Be Paid] | NA | NA | [To Be Paid]
[To Be Paid] | 12 | 17 | Extra Labor Per Discussion - Sai & Aniket | From Boulder Construction | 6000 | 0 | 6000 |  |  |  | Swimming Pool | Boulder Construction | [To Be Paid] | NA | NA | [To Be Paid]
[To Be Paid] | 12 | 17 | Exterior Fence | From TKG Construction - Pay App 11 | 5000 | 0 | 5000 |  |  |  | Swimming Pool | TKG Construction | [To Be Paid] | [TBD] | No | [To Be Paid]
13. Conveying Equipment
| 13 | 1 | Draw 1 Funds |  |  |  |  | 77100 | 0 | 77100
| 13 | 3 | Draw 3 Funds |  |  |  |  | 3748 | 3748 | 0
| 13 | 8 | Draw 8 Funds - Reimbursements |  |  |  |  | 11800 | 0 | 11800
| 13 | 12 | Draw 12 Funds - To Be Paid |  |  |  |  | 134936.07 | 17830.407 | 117105.663
| 13 | 13 | Draw 13 Funds - To Be Paid |  |  |  |  | 42415.93 | 4241.593 | 38174.337
| 13 | 14 | Draw 14 Funds - To Be Paid |  |  |  |  | 0 | 0 | 0
2024-11-05 | 13 | 1 | Elevator Deposit | From Kone | 80848 | 8084.8 | 72763.2 |  |  |  | Elevators | Kone | RI Waxahachie | 10059 | No |  | RIW-CFR-13-001
2025-04-21 | 13 | 8 | Linen Chute | From Kasl Enterprises | 11800 | 0 | 11800 |  |  |  | Linen Chute | KASL Enterprises | Owner (JP) AMEX | 10427 | NA | Credit Card | RIW-CFR-13-002
2025-10-08 | 13 | 12 | Elevator Material & Installation Labor | From Kone | 134936.07 | 13493.61 | 121442.46 |  |  |  | Elevators | Kone | RI Waxahachie | 10846 | No | ACH | RIW-CFR-13-003
2026-01-30 | 13 | 13 | Elevator Material & Installation Labor | From Kone - Allocated Payment (Pay App 03) | 42415.93 | 4241.59 | 38174.34 |  |  |  | Elevators | Kone | RI Waxahachie | 10929 | No | [To Be Paid] | RIW-CFR-13-004
[To Be Paid] | 13 | 14 | Elevator - Equipment | From EquipmentShare | 6496.1 | 0 | 6496.1 |  |  |  | Elevators | EquipmentShare | RI Waxahachie | 11056 | NA | [To Be Paid] | RIW-CFR-13-005
[To Be Paid] | 13 | 14 | Elevator - Equipment | From EquipmentShare | -6496.1 | 0 | -6496.1 |  |  |  | Elevators | EquipmentShare | RI Waxahachie | 11056 | NA | [To Be Paid] | RIW-CFR-13-006
14. Fire Suppression
| 14 | 4 | Draw 4 Funds |  |  |  |  | 30000 | 3000 | 27000
| 14 | 6 | Draw 6 Funds - To Be Paid |  |  |  |  | 15000 | 1500 | 13500
| 14 | 11 | Draw 11 Funds - To Be Paid |  |  |  |  | 142000 | 14200 | 127800
| 14 | 15 | Draw 15 Funds - To Be Paid |  |  |  |  | 10000 | 1000 | 9000
2025-02-24 | 14 | 4 | Fire Alarm/Sprinkler Designs | From Safe Life FP (Invoice 01) | 30000 | 3000 | 27000 |  |  |  | Fire Suppression | Safe Life Fire Protection | RI Waxahachie | 10219 | No | Wire Transfer | RIW-CFR-14-001
2025-04-08 | 14 | 6 | Fire Standpipe | From Safe Life FP (Invoice 02) | 15000 | 1500 | 13500 |  |  |  | Fire Suppression | Safe Life Fire Protection | RI Waxahachie | 10344 | Yes | Wire Transfer | RIW-CFR-14-002
2025-09-18 | 14 | 11 | Fire Sprinkler Rough and Stand Pipe | From Safe Life FP (Invoice 03) - Split (First Payment) | 107000 | 10700 | 96300 |  |  |  | Fire Suppression | Safe Life Fire Protection | RI Waxahachie | 10731 | No | ACH | RIW-CFR-14-003
2025-09-18 | 14 | 11 | Fire Sprinkler - Change Order | From Safe Life FP (Invoice 03) - Split (First Payment) | 35000 | 3500 | 31500 |  |  |  | Fire Suppression | Safe Life Fire Protection | RI Waxahachie | 10731 | No | ACH | RIW-CFR-14-004
2026-01-28 | 14 | 15 | Fire Sprinkler Trim | From Safe Life FP (Invoice 04) | 10000 | 1000 | 9000 |  |  |  | Fire Suppression | Safe Life Fire Protection | RI Waxahachie | 11225 | No | [To Be Paid] | RIW-CFR-14-005
15. Plumbing/HVAC
| 15 | 2 | Draw 2 Funds - Plumbing |  |  |  |  | 160000 | 16000 | 144000
| 15 | 3 | Draw 3 Funds - Plumbing |  |  |  |  | 485.3 | 0 | 485.3
| 15 | 4 | Draw 4 Funds - Plumbing |  |  |  |  | 66666.66 | 6666.66 | 60000
| 15 | 5 | Draw 5 Funds - Plumbing Material |  |  |  |  | 121688.63 | 0 | 121688.63
| 15 | 5 | Draw 5 Funds - Plumbing Labor |  |  |  |  | 44444.44 | 4444.44 | 40000
| 15 | 5 | Draw 5 Funds - Mechanical |  |  |  |  | 150000 | 15000 | 135000
| 15 | 6 | Draw 6 Funds - Reimbursement |  |  |  |  | 2177.84 | 0 | 2177.84
| 15 | 6 | Draw 6 Funds - To Be Paid |  |  |  |  | 129966.02 | 0 | 129966.02
| 15 | 7 | Draw 7 Funds - To Be Paid (Plumbing) |  |  |  |  | 123950.27 | 24563.9 | 99386.37
| 15 | 7 | Draw 7 Funds - To Be Paid (Mechanical) | True Up Funds From Draw 5 |  |  |  | 61000 | 6100 | 54900
| 15 | 8 | Draw 8 Funds - To Be Paid (Mechanical) |  |  |  |  | 52000 | 5200 | 46800
| 15 | 9 | Draw 9 Funds - To Be Paid (Mechanical) |  |  |  |  | 71598.73 | 0 | 71598.73
| 15 | 10 | Draw 10 Funds - To Be Paid (Mechanical) |  |  |  |  | 118932.93 | 10000 | 108932.93
| 15 | 12 | Draw 12 Funds - Reimbursement (Mechanical) |  |  |  |  | 78939.0456 | 6961.2222 | 71977.8233
| 15 | 13 | Draw 13 Funds - To Be Paid (Mechanical) |  |  |  |  | 23000 | 2300 | 20700
| 15 | 14 | Draw 14 Funds - Reimbursement |  |  |  |  | 507.64 | 0 | 507.64
| 15 | 14 | Draw 14 Funds - To Be Paid |  |  |  |  | 8000 | 800 | 7200
| 15 | 15 | Draw 15 Funds - Reimbursement |  |  |  |  | 6861.88 | 0 | 6861.88
| 15 | 15 | Draw 15 Funds - To Be Paid |  |  |  |  | 137369.98 | 13737 | 123632.98
| 15 | 16 | Draw 16 Funds - Reimbursement |  |  |  |  | 649.48 | 0 | 649.48
| 15 | 16 | Draw 16 Funds - To Be Paid |  |  |  |  | 347166.03 | 34716.603 | 312449.427
| 15 | 17 | Draw 17 Funds - To Be Paid |  |  |  |  | 183001.41 | 11353.2 | 171648.21
2024-10-04 | 15 | 2 | Plumbing - Rough | MA Williams Plumbing Invoice | 55555.56 | 5555.556 | 50000.004 |  |  |  | Plumbing | MA Williams Plumbing | Boulder | 10053 | Yes | Check | RIW-CFR-15-001
2024-10-15 | 15 | 2 | Plumbing - Rough | MA Williams Plumbing Invoice | 104444.44 | 10444.444 | 93999.996 |  |  |  | Plumbing | MA Williams Plumbing | Boulder | 10056 | Yes | Check | RIW-CFR-15-002
2024-10-02 | 15 | 3 | Plumbing - Misc. Material | From Home Depot | 70.63 | 0 | 70.63 |  |  |  | Plumbing | Home Depot | Rush | 10125 | NA |  | RIW-CFR-15-003
2024-10-01 | 15 | 3 | Plumbing - Misc. Material | From Home Depot | 90.95 | 0 | 90.95 |  |  |  | Plumbing | Home Depot | Rush | 10126 | NA |  | RIW-CFR-15-004
2024-07-01 | 15 | 3 | Plumbing - Misc. Material | From Home Depot | 12.89 | 0 | 12.89 |  |  |  | Plumbing | Home Depot | Rush |  | NA |  | RIW-CFR-15-005
2024-11-11 | 15 | 3 | Plumbing - Misc. Material | From Home Depot | 204.02 | 0 | 204.02 |  |  |  | Plumbing | Home Depot | Rush | 10085 | NA |  | RIW-CFR-15-006
2024-11-14 | 15 | 3 | Plumbing - Misc. Material | From Home Depot | 106.81 | 0 | 106.81 |  |  |  | Plumbing | Home Depot | Boulder AMEX | 10086 | NA |  | RIW-CFR-15-007
2025-01-03 | 15 | 4 | Plumbing - Top Out Labor | MA Williams Plumbing Invoice - Allocated Across Multiple Payments | 22222.22 | 2222.22 | 20000 |  |  |  | Plumbing | MA Williams Plumbing | RI Waxahachie | 10310 | No | Check | RIW-CFR-15-008
2025-01-27 | 15 | 4 | Plumbing - Top Out Labor | MA Williams Plumbing Invoice - Allocated Across Multiple Payments | 22222.22 | 2222.22 | 20000 |  |  |  | Plumbing | MA Williams Plumbing | RI Waxahachie | 10310 | No | Check | RIW-CFR-15-009
2025-02-08 | 15 | 4 | Plumbing - Top Out Labor | MA Williams Plumbing Invoice - Allocated Across Multiple Payments | 22222.22 | 2222.22 | 20000 |  |  |  | Plumbing | MA Williams Plumbing | RI Waxahachie | 10310 | No | Check | RIW-CFR-15-010
2025-02-24 | 15 | 5 | Plumbing - Top Out Labor | MA Williams Plumbing Invoice | 22222.22 | 2222.22 | 20000 |  |  |  | Plumbing | MA Williams Plumbing | RI Waxahachie | 10333 | Yes | Check | RIW-CFR-15-011
2025-03-11 | 15 | 5 | Plumbing - Top Out Labor | MA Williams Plumbing Invoice | 22222.22 | 2222.22 | 20000 |  |  |  | Plumbing | MA Williams Plumbing | RI Waxahachie | 10392 | Yes | Check | RIW-CFR-15-012
2025-02-20 | 15 | 5 | Plumbing - Top Out & Other Material Payment | From Moore Supply - Allocated Payment (Excl. Utilities Allocation) | 121688.63 | 0 | 121688.63 |  |  |  | Plumbing | Moore Supply | Owner (JP) AMEX | 10288 | NA | Credit Card | RIW-CFR-15-013
2025-03-19 | 15 | 5 | HVAC/Mechanical Material | From Iceberg Heating & AC - Pay App 01 | 10059.1444 | 1005.9144 | 9053.23 |  |  |  | Mechanical | Z&R Vargas | RI Waxahachie | 10348 | Yes | Check | RIW-CFR-15-014
2025-03-24 | 15 | 5 | HVAC/Mechanical Material | From Iceberg Heating & AC - Pay App 01 | 15910.3333 | 1591.0333 | 14319.3 |  |  |  | Mechanical | Winsupply | RI Waxahachie | 10348 | No | Check | RIW-CFR-15-015
2025-03-25 | 15 | 5 | HVAC/Mechanical Material | From Iceberg Heating & AC - Pay App 01 | 71324.7222 | 7132.4722 | 64192.25 |  |  |  | Mechanical | Captiveaire Systems | RI Waxahachie | 10348 | Yes | Check | RIW-CFR-15-016
2025-03-17 | 15 | 5 | HVAC/Mechanical Labor | From Iceberg Heating & AC - Pay App 01 - Remaining Check to Contractor (True Up Retainage) | 27705.8 | 2770.58 | 24935.22 |  |  |  | Mechanical | Iceberg Heating and Air | RI Waxahachie | 10348 | Yes | Check | RIW-CFR-15-017
2025-02-12 | 15 | 6 | Sample VTAC | From Greens Electric - For Mock Up Room | 2177.84 | 0 | 2177.84 |  |  |  | VTACs | Greens Electric | Owner (JP) AMEX | 10283 | NA | Credit Card | RIW-CFR-15-018
| 15 | 6 | VTAC Sleeves | From Greens Electric | 22490.02 | 0 | 22490.02 |  |  |  | VTACs | Greens Electric | RI Waxahachie | 10345 | NA | Wire Transfer | RIW-CFR-15-019
| 15 | 6 | VTAC Costs - 50% Deposit | From Greens Electric | 107476 | 0 | 107476 |  |  |  | VTACs | Greens Electric | RI Waxahachie | 10346 | NA | Wire Transfer | RIW-CFR-15-020
2025-04-30 | 15 | 5/7 | HVAC/Mechanical Labor | From Iceberg Heating & AC - Pay App 02 (First Payment) | 34050.7556 | 3405.0756 | 30645.68 |  |  |  | Mechanical | Iceberg Heating and Air | RI Waxahachie | 10440 | Yes | Check | RIW-CFR-15-021
2025-05-13 | 15 | 7 | HVAC/Mechanical Material | From Iceberg Heating & AC - Pay App 02 | 44009.6444 | 4400.9644 | 39608.68 |  |  |  | Mechanical | Bartos | RI Waxahachie | 10440 | Yes | Check | RIW-CFR-15-022
2025-05-01 | 15 | 7 | HVAC/Mechanical Material | From Iceberg Heating & AC - Pay App 02 | 7939.6 | 793.96 | 7145.64 |  |  |  | Mechanical | Winsupply | RI Waxahachie | 10440 | Yes | Check | RIW-CFR-15-023
2025-05-02 | 15 | 7 | Plumbing - Remaining Top Out Invoice | From MA Williams Plumbing - Adjusted Against Material Balance | 58600.9 | 24563.9 | 34037 |  |  |  | Plumbing | MA Williams Plumbing | RI Waxahachie | 10446 | No | Check | RIW-CFR-15-024
2025-04-29 | 15 | 7 | Plumbing - Top Out & Other Material Payment | From Moore Supply - Allocated Payment | 65349.37 | 0 | 65349.37 |  |  |  | Plumbing | Moore Supply | Owner (JP) AMEX | 10446 | NA | Credit Card | RIW-CFR-15-025
2025-05-28 | 15 | 8 | HVAC/Mechanical Material and Labor | From Iceberg Heating & AC - Pay App 03 (Final Payment) | 21930.5556 | 2193.0556 | 19737.5 |  |  |  | Mechanical | Iceberg Heating and Air | RI Waxahachie | 10514 | Yes | Check | RIW-CFR-15-026
2025-06-06 | 15 | 8 | HVAC/Mechanical Material and Labor | From Iceberg Heating & AC - Pay App 03 | 30069.4444 | 3006.9444 | 27062.5 |  |  |  | Mechanical | Bartos | RI Waxahachie | 10514 | Yes | Check | RIW-CFR-15-027
2025-06-20 | 15 | 9 | VTAC Costs - Heat Pump, Power Supply Kit | Greens Distribution - Additional Payment | 71598.73 | 0 | 71598.73 |  |  |  | VTACs | Greens Electric | RI Waxahachie | 10581 | Yes | Wire | RIW-CFR-15-028
2025-08-01 | 15 | 10 | HVAC/Mechanical Material and Labor | From Iceberg Heating & AC - Pay App 04 (First Payment) | 55111.2778 | 5511.1278 | 49600.15 |  |  |  | Mechanical | Iceberg Heating and Air | RI Waxahachie | 10676 | No | Check | RIW-CFR-15-029
2025-08-01 | 15 | 10 | HVAC/Mechanical Material and Labor | From Iceberg Heating & AC - Pay App 04 (Second Payment) | 35000 | 3500 | 31500 |  |  |  | Mechanical | Iceberg Heating and Air | RI Waxahachie | 10676 | No | Check | RIW-CFR-15-030
2025-10-31 | 15 | 10 | HVAC/Mechanical Material and Labor | From Iceberg Heating & AC - Pay App 04 (Third Payment) | 4444.4444 | 444.4444 | 4000 |  |  |  | Mechanical | Iceberg Heating and Air | RI Waxahachie | 10676 | No | Check | RIW-CFR-15-031
[To Be Paid] | 15 | 10 | HVAC/Mechanical Material and Labor | From Iceberg Heating & AC - Pay App 04 (Final Payment) | 5444.2778 | 544.4278 | 4899.85 |  |  |  | Mechanical | Iceberg Heating and Air | [To Be Paid] | 10676 | No | [To Be Paid] | RIW-CFR-15-032
2025-07-30 | 15 | 10 | VTAC Grilles | From Greens Electric | 18932.93 | 0 | 18932.93 |  |  |  | VTACs | Greens Electric | RI Waxahachie | 10719 | No | ACH | RIW-CFR-15-033
[Confirm] | 15 | 12 | Mechanical Equipment | From Trane - Iceberg Heating & Ac | 69612.2222 | 6961.2222 | 62651 |  |  |  | Mechanical | Trane US | [Confirm] | 10854 | No | [Confirm] | RIW-CFR-15-034
2025-07-31 | 15 | 12 | Jobsite Labor | Clean Up & Other Misc. Tasks | 855 | 0 | 855 |  |  |  | Plumbing | Rodolfo Rios | RI Waxahachie | 10794 | NA | ACH | RIW-CFR-15-035
2025-08-04 | 15 | 12 | Jobsite Labor | Clean Up & Other Misc. Tasks | 150 | 0 | 150 |  |  |  | Plumbing | Rodolfo Rios | RI Waxahachie | 10795 | NA | ACH | RIW-CFR-15-036
2025-08-08 | 15 | 12 | Jobsite Labor | Clean Up & Other Misc. Tasks | 1068.75 | 0 | 1068.75 |  |  |  | Plumbing | Rodolfo Rios | RI Waxahachie | 10796 | NA | ACH | RIW-CFR-15-037
2025-08-15 | 15 | 12 | Jobsite Labor | Clean Up & Other Misc. Tasks | 681.25 | 0 | 681.25 |  |  |  | Plumbing | Rodolfo Rios | RI Waxahachie | 10797 | NA | ACH | RIW-CFR-15-038
2025-08-01 | 15 | 12 | Jobsite Labor | Clean Up & Other Misc. Tasks | 465 | 0 | 465 |  |  |  | Plumbing | David Salinas | RI Waxahachie | 10798 | NA | ACH | RIW-CFR-15-039
2025-08-15 | 15 | 12 | Jobsite Labor | Clean Up & Other Misc. Tasks | 405 | 0 | 405 |  |  |  | Plumbing | David Salinas | RI Waxahachie | 10799 | NA | ACH | RIW-CFR-15-040
2025-08-08 | 15 | 12 | Jobsite Labor | Clean Up & Other Misc. Tasks | 405 | 0 | 405 |  |  |  | Plumbing | David Salinas | RI Waxahachie | 10800 | NA | ACH | RIW-CFR-15-041
2025-08-22 | 15 | 12 | Jobsite Labor | Clean Up & Other Misc. Tasks | 1045 | 0 | 1045 |  |  |  | Plumbing | Rodolfo Rios | RI Waxahachie | 10834 | NA | ACH | RIW-CFR-15-042
2025-08-22 | 15 | 12 | Jobsite Labor | Clean Up & Other Misc. Tasks | 712.5 | 0 | 712.5 |  |  |  | Plumbing | David Salinas | RI Waxahachie | 10835 | NA | ACH | RIW-CFR-15-043
2025-08-25 | 15 | 12 | Jobsite Labor | Clean Up & Other Misc. Tasks | 1500 | 0 | 1500 |  |  |  | Plumbing | David Salinas | RI Waxahachie | 10839 | NA | ACH | RIW-CFR-15-044
2025-08-29 | 15 | 12 | Jobsite Labor | Clean Up & Other Misc. Tasks | 315 | 0 | 315 |  |  |  | Plumbing | David Salinas | RI Waxahachie | 10852 | NA | ACH | RIW-CFR-15-045
2025-08-29 | 15 | 12 | Jobsite Labor | Clean Up & Other Misc. Tasks | 641.25 | 0 | 641.25 |  |  |  | Plumbing | Rodolfo Rios | RI Waxahachie | 10853 | NA | ACH | RIW-CFR-15-046
2025-08-20 | 15 | 12 | Labor & Gas for Generators | From J&S7 Consulting | 1083.0733 | 0 | 1083.0733 |  |  |  | Mechanical | J&S7 Consulting | Boulder | 10833 | NA | Check | RIW-CFR-15-047
2025-11-03 | 15 | 13 | HVAC/Mechanical Material and Labor | From Iceberg Heating & AC - Pay App 05 - Overpaid 2Inv | 15337.9 | 0 | 15337.9 |  |  |  | Mechanical | Winsupply | RI Waxahachie | 10931 | No | [To Be Paid] | RIW-CFR-15-048
[To Be Paid] | 15 | 13 | HVAC/Mechanical Material and Labor | From Iceberg Heating & AC - Pay App 05 (Z&R Vargas from Pay App 05 Adj) | 7662.1 | 2300 | 5362.1 |  |  |  | Mechanical | Iceberg Heating and Air | [To Be Paid] | 10931 | No | [To Be Paid] | RIW-CFR-15-049
2025-10-27 | 15 | 14 | Plumbing Material | From Home Depot - Utility Pump & Tethered Switch | 400.47 | 0 | 400.47 |  |  |  | Plumbing | Home Depot | Boulder AMEX | 11032 | NA | Credit Card | RIW-CFR-15-050
2025-10-27 | 15 | 14 | Plumbing Material | From Home Depot - HP Plastic Utlity Pump | 107.17 | 0 | 107.17 |  |  |  | Plumbing | Home Depot | Boulder AMEX | 11035 | NA | Credit Card | RIW-CFR-15-051
[To Be Paid] | 15 | 14 | HVAC/Mechanical Material and Labor | From Iceberg Heating & AC - Pay App 06 | 551.36 | 0 | 551.36 |  |  |  | Mechanical | Z&R Vargas | [To Be Paid] | 11058 | NA | [To Be Paid] | RIW-CFR-15-052
[To Be Paid] | 15 | 14 | HVAC/Mechanical Material and Labor | From Iceberg Heating & AC - Pay App 06 | 344.3 | 0 | 344.3 |  |  |  | Mechanical | Winsupply | [To Be Paid] | 11058 | NA | [To Be Paid] | RIW-CFR-15-053
[To Be Paid] | 15 | 14 | HVAC/Mechanical Material and Labor | From Iceberg Heating & AC - Pay App 06 | 2252.18 | 0 | 2252.18 |  |  |  | Mechanical | Winsupply | [To Be Paid] | 11058 | NA | [To Be Paid] | RIW-CFR-15-054
[To Be Paid] | 15 | 14 | HVAC/Mechanical Material and Labor | From Iceberg Heating & AC - Pay App 06 | 58.4 | 0 | 58.4 |  |  |  | Mechanical | Winsupply | [To Be Paid] | 11058 | NA | [To Be Paid] | RIW-CFR-15-055
[To Be Paid] | 15 | 14 | HVAC/Mechanical Material and Labor | From Iceberg Heating & AC - Pay App 06 | 151.72 | 0 | 151.72 |  |  |  | Mechanical | Winsupply | [To Be Paid] | 11058 | NA | [To Be Paid] | RIW-CFR-15-056
[To Be Paid] | 15 | 14 | HVAC/Mechanical Material and Labor | From Iceberg Heating & AC - Pay App 06 | 2001.8 | 0 | 2001.8 |  |  |  | Mechanical | Winsupply | [To Be Paid] | 11058 | NA | [To Be Paid] | RIW-CFR-15-057
[To Be Paid] | 15 | 14 | HVAC/Mechanical Material and Labor | From Iceberg Heating & AC - Pay App 06 | 1251.46 | 0 | 1251.46 |  |  |  | Mechanical | Winsupply | [To Be Paid] | 11058 | NA | [To Be Paid] | RIW-CFR-15-058
[To Be Paid] | 15 | 14 | HVAC/Mechanical Material and Labor | From Iceberg Heating & AC - Pay App 06 | 1388.78 | 800 | 588.78 |  |  |  | Mechanical | Iceberg Heating and Air | [To Be Paid] | 11058 | No | [To Be Paid] | RIW-CFR-15-059
2025-12-03 | 15 | 15 | Mechanical | From Home Depot - Indoor/Outdoor Wireless Thermometer & Acurite Monitor | 136.91 | 0 | 136.91 |  |  |  | Mechanical | Home Depot | Boulder AMEX | 11113 | NA | Credit Card | RIW-CFR-15-060
2025-12-01 | 15 | 15 | Guest Room Thermostats | From Supply House | 6724.97 | 0 | 6724.97 |  |  |  | Mechanical | Supply House | Boulder AMEX | 11224 | NA | Credit Card | RIW-CFR-15-061
2025-11-30 | 15 | 15 | Thermostats | From Jackson B2C | 5169.67 | 0 | 5169.67 |  |  |  | Mechanical | Jackson B2C | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-15-062
2025-12-02 | 15 | 15 | Thermostats - Refund | From Jackson B2C | -5169.67 | 0 | -5169.67 |  |  |  | Mechanical | Jackson B2C | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-15-063
[To Be Paid] | 15 | 15 | HVAC/Mechanical Material and Labor | From Iceberg Heating & AC - Pay App 07 | 14341.29 | 2136.998 | 12204.292 |  |  |  | Mechanical | Iceberg Heating and Air | [To Be Paid] | 11217 | No | [To Be Paid] | RIW-CFR-15-064
[To Be Paid] | 15 | 15 | HVAC/Mechanical Material and Labor | From Iceberg Heating & AC - Pay App 07 | 7028.69 | 0 | 7028.69 |  |  |  | Mechanical | Z & R Vargas | [To Be Paid] | 11217 | No | [To Be Paid] | RIW-CFR-15-065
[To Be Paid] | 15 | 15 | HVAC/Mechanical Material and Labor | From Iceberg Heating & AC - Pay App 08 | 5650.88 | 0 | 5650.88 |  |  |  | Mechanical | Winsupply | [To Be Paid] | 11218 | No | [To Be Paid] | RIW-CFR-15-066
[To Be Paid] | 15 | 15 | HVAC/Mechanical Material and Labor | From Iceberg Heating & AC - Pay App 08 | 2446.45 | 0 | 2446.45 |  |  |  | Mechanical | Bartos | [To Be Paid] | 11218 | No | [To Be Paid] | RIW-CFR-15-067
[To Be Paid] | 15 | 15 | HVAC/Mechanical Material and Labor | From Iceberg Heating & AC - Pay App 08 | 1407.87 | 0 | 1407.87 |  |  |  | Mechanical | RDZ Sheet Metal | [To Be Paid] | 11218 | No | [To Be Paid] | RIW-CFR-15-068
[To Be Paid] | 15 | 15 | HVAC/Mechanical Material and Labor | From Iceberg Heating & AC - Pay App 08 | 12831.99 | 0 | 12831.99 |  |  |  | Mechanical | Trane US | [To Be Paid] | 11218 | No | [To Be Paid] | RIW-CFR-15-069
[To Be Paid] | 15 | 15 | HVAC/Mechanical Material and Labor | From Iceberg Heating & AC - Pay App 08 | 93662.81 | 11600.002 | 82062.808 |  |  |  | Mechanical | Iceberg Heating and Air | [To Be Paid] | 11218 | No | [To Be Paid] | RIW-CFR-15-070
2026-01-09 | 15 | 16 | Wall Mounted Fire Place Heater w/Thermostat | From Amazon | 649.48 | 0 | 649.48 |  |  |  | Mechanical | Amazon | Boulder AMEX | 12175 | NA | Credit Card | RIW-CFR-15-071
2026-02-18 | 15 | 16 | Plumbing | From MA Williams Plumbing - Pay App 05 | 200000 | 20000 | 180000 |  |  |  | Plumbing | MA Williams Plumbing | RI Waxahachie | 12182 | NA | [To Be Paid] | RIW-CFR-15-072
[To Be Paid] | 15 | 16 | HVAC/Mechanical Material and Labor | From Iceberg Heating and Ac - Pay App 10 | 147166.03 | 14716.603 | 132449.427 |  |  |  | Mechanical | Iceberg Heating and Ac | [To Be Paid] | 12184 | NA | [To Be Paid] | RIW-CFR-15-073
[To Be Paid] | 15 | 17 | Plumbing Material & Labor | From MA William Plumbing - Pay App 06 (Second Payment) | 78120.8889 | 7812.0889 | 70308.8 |  |  |  | Plumbing | MA Williams Plumbing | [To Be Paid] | [TBD] | No | [To Be Paid]
2026-03-16 | 15 | 17 | Plumbing Material & Labor | From MA William Plumbing - Pay App 06 (First Payment) | 11111.1111 | 1111.1111 | 10000 |  |  |  | Plumbing | MA Williams Plumbing | RI Waxahachie | [TBD] | No | Check
2026-03-04 | 15 | 17 | Electrical Material | From Elliott Electrical | 69469.41 | 0 | 69469.41 |  |  |  | Plumbing | Elliott Electric | Jaimin AMEX | 12528 | NA | Credit Card
[To Be Paid] | 15 | 17 | Electrical Labor | From GMC Electrical - Pay App 10 (Split) | 24300 | 2430 | 21870 |  |  |  | Plumbing | GMC Electrical | [To Be Paid] | [TBD] | NA | [To Be Paid]
16. Electrical
| 16 | 1 | Order Switch Gear | Greens Distributions - Initial Deposit |  |  |  | 23382 | 0 | 23382
| 16 | 2 | Electrical - Forecast | Rough-In Completed + Future Work |  |  |  | 35000 | 3000 | 32000
| 16 | 3 | Draw 3 Funds |  |  |  |  | 2970.73 | 0 | 2970.73
| 16 | 4 | Draw 4 Funds |  |  |  |  | 18310.59 | 0 | 18310.59
| 16 | 5 | Draw 5 Funds |  |  |  |  | 82160.36 | 0 | 82160.36
| 16 | 6 | Draw 6 Funds - Reimbursements |  |  |  |  | 15759.89 | 0 | 15759.89
| 16 | 6 | Draw 6 Funds - To Be Paid |  |  |  |  | 46500 | 4650 | 41850
| 16 | 7 | Draw 6 Funds - Reimbursements |  |  |  |  | 16743.62 | 0 | 16743.62
| 16 | 7 | Draw 6 Funds - To Be Paid |  |  |  |  | 69121.18 | 0 | 69121.18
| 16 | 8 | Draw 8 Funds - Reimbursements (Electrical) |  |  |  |  | 7.13 | 0 | 7.13
| 16 | 8 | Draw 8 Funds - Reimbursements (Structured Cabling) |  |  |  |  | 18750 | 1875 | 16875
| 16 | 8 | Draw 8 Funds - To Be Paid (Electrical) | True Up Funds From Draw 2 |  |  |  | 16400 | 1640 | 14760
| 16 | 9 | Draw 9 Funds - Reimbursements (Electrical) |  |  |  |  | 141664.31 | 0 | 141664.31
| 16 | 9 | Draw 9 Funds - To Be Paid (Electrical) |  |  |  |  | 52264.89 | 2750 | 49514.89
| 16 | 10 | Draw 10 Funds - Reimbursements (Electrical) |  |  |  |  | 40070.96 | 0 | 40070.96
| 16 | 10 | Draw 10 Funds - To Be Paid (Electrical) |  |  |  |  | 34000 | 3400 | 30600
| 16 | 11 | Draw 11 Funds - Reimbursements (Electrical) |  |  |  |  | 48220.11 | 0 | 48220.11
| 16 | 11 | Draw 11 Funds - To Be Paid (Electrical) |  |  |  |  | 54982.35 | 5300 | 49682.35
| 16 | 12 | Draw 12 Funds - Reimbursements (Electrical) |  |  |  |  | 68799.4633 | 550 | 68249.4633
| 16 | 12 | Draw 12 Funds - To Be Paid (Electrical) |  |  |  |  | 2028.98 | 0 | 2028.98
| 16 | 13 | Draw 13 Funds - Reimbursements (Electrical) |  |  |  |  | 89246.35 | 1100 | 88146.35
| 16 | 14 | Draw 14 Funds - Reimbursements (Electrical) |  |  |  |  | 104800.01 | 1180 | 103620.01
| 16 | 14 | Draw 14 Funds - To Be Paid (Electrical) |  |  |  |  | 35492.58 | 3075 | 32417.58
| 16 | 15 | Draw 15 Funds - Reimbursements (Electrical) |  |  |  |  | 26779.39 | 0 | 26779.39
| 16 | 16 | Draw 16 Funds - Reimbursements (Electrical) |  |  |  |  | 6085.22 | 0 | 6085.22
| 16 | 16 | Draw 16 Funds - To Be Paid (Electrical) |  |  |  |  | 57500 | 5750 | 51750
| 16 | 17 | Draw 17 Funds - Reimbursements (Electrical) |  |  |  |  | 6298.31 | 0 | 6298.31
| 16 | 17 | Draw 17 Funds - To Be Paid (Electrical) |  |  |  |  | 56500 | 5650 | 50850
| 16 | 1/3 | Order Switch Gear | Greens Distributions - Initial Deposit | 24083.46 | 0 | 24083.46 |  |  |  | Electrical | Greens Electric | Jaimin Uncle |  | NA |  | RIW-CFR-16-001
| 16 | 2/3 | Electrical Material | Elliott Electric | 2197.16 | 0 | 2197.16 |  |  |  | Electrical | Elliott Electric | Rush | 10131 | NA |  | RIW-CFR-16-002
2024-11-26 | 16 | 2/3 | Electrical Material | Elliott Electric | 544.12 | 0 | 544.12 |  |  |  | Electrical | Elliott Electric | Rush | 10132 | NA |  | RIW-CFR-16-003
2024-11-25 | 16 | 2/3 | Electrical Material | Elliott Electric | 184.59 | 0 | 184.59 |  |  |  | Electrical | Elliott Electric | Rush | 10133 | NA |  | RIW-CFR-16-004
2024-11-25 | 16 | 2/3 | Electrical Material | Elliott Electric - Return | -311.81 | 0 | -311.81 |  |  |  | Electrical | Elliott Electric | Rush | 10134 | NA |  | RIW-CFR-16-005
2024-11-25 | 16 | 2/3 | Electrical Material | Elliott Electric | 415.32 | 0 | 415.32 |  |  |  | Electrical | Elliott Electric | Rush | 10135 | NA |  | RIW-CFR-16-006
2024-11-25 | 16 | 2/3 | Electrical Material | Elliott Electric | 2763.11 | 0 | 2763.11 |  |  |  | Electrical | Elliott Electric | Rush | 10136 | NA |  | RIW-CFR-16-007
2024-10-04 | 16 | 2/3 | Electrical Material | Elliott Electric | 46.15 | 0 | 46.15 |  |  |  | Electrical | Elliott Electric | Rush | 10137 | NA |  | RIW-CFR-16-008
2024-10-04 | 16 | 2/3 | Electrical Material | Elliott Electric | 14.22 | 0 | 14.22 |  |  |  | Electrical | Elliott Electric | Rush | 10138 | NA |  | RIW-CFR-16-009
2024-10-03 | 16 | 2/3 | Electrical Material | Elliott Electric | 433.65 | 0 | 433.65 |  |  |  | Electrical | Elliott Electric | Rush | 10139 | NA |  | RIW-CFR-16-010
2024-10-16 | 16 | 2/3 | Electrical Material | Elliott Electric | 127.57 | 0 | 127.57 |  |  |  | Electrical | Elliott Electric | Rush | 10140 | NA |  | RIW-CFR-16-011
2024-10-16 | 16 | 2/3 | Electrical Material | Elliott Electric | 118.84 | 0 | 118.84 |  |  |  | Electrical | Elliott Electric | Rush | 10141 | NA |  | RIW-CFR-16-012
2024-10-15 | 16 | 2/3 | Electrical Material | Elliott Electric | 131.56 | 0 | 131.56 |  |  |  | Electrical | Elliott Electric | Rush | 10142 | NA |  | RIW-CFR-16-013
2024-10-14 | 16 | 2/3 | Electrical Material | Elliott Electric - Return | -368.66 | 0 | -368.66 |  |  |  | Electrical | Elliott Electric | Rush | 10143 | NA |  | RIW-CFR-16-014
2024-10-14 | 16 | 2/3 | Electrical Material | Elliott Electric | 973.45 | 0 | 973.45 |  |  |  | Electrical | Elliott Electric | Rush | 10144 | NA |  | RIW-CFR-16-015
2024-10-24 | 16 | 2 | Electrical Underground Labor | GMC Electric | 10900 | 1090 | 9810 |  |  |  | Electrical | GMC Electric | RI Waxahachie | 10149 | Yes | Check | RIW-CFR-16-016
2024-12-27 | 16 | 4 | Electrical Material | Elliott Electric | 2527.8 | 0 | 2527.8 |  |  |  | Electrical | Elliott Electric | Boulder AMEX | 10176 | NA |  | RIW-CFR-16-017
2025-01-02 | 16 | 4 | Electrical Material | Elliott Electric | 7810.7 | 0 | 7810.7 |  |  |  | Electrical | Elliott Electric | Boulder AMEX | 10177 | NA |  | RIW-CFR-16-018
2025-01-02 | 16 | 4 | Electrical Material | Elliott Electric | 625.48 | 0 | 625.48 |  |  |  | Electrical | Elliott Electric | Boulder AMEX | 10178 | NA |  | RIW-CFR-16-019
2025-01-03 | 16 | 4 | Electrical Material | Elliott Electric | -136.22 | 0 | -136.22 |  |  |  | Electrical | Elliott Electric | Boulder AMEX | 10179 | NA |  | RIW-CFR-16-020
2025-01-07 | 16 | 4 | Electrical Material | Elliott Electric | 5451.95 | 0 | 5451.95 |  |  |  | Electrical | Elliott Electric | Boulder AMEX | 10180 | NA |  | RIW-CFR-16-021
2025-01-06 | 16 | 4 | Electrical Material | Elliott Electric | 123.02 | 0 | 123.02 |  |  |  | Electrical | Elliott Electric | Boulder AMEX | 10181 | NA |  | RIW-CFR-16-022
2025-01-06 | 16 | 4 | Electrical Material | Elliott Electric | 833.31 | 0 | 833.31 |  |  |  | Electrical | Elliott Electric | Boulder AMEX | 10182 | NA |  | RIW-CFR-16-023
2025-01-06 | 16 | 4 | Electrical Material | Elliott Electric | 993.58 | 0 | 993.58 |  |  |  | Electrical | Elliott Electric | Boulder AMEX | 10183 | NA |  | RIW-CFR-16-024
2025-01-08 | 16 | 4 | Electrical Material | Elliott Electric | 80.97 | 0 | 80.97 |  |  |  | Electrical | Elliott Electric | Boulder AMEX | 10184 | NA |  | RIW-CFR-16-025
2025-03-07 | 16 | 5 | Switch Gear | Greens Distribution - Additional Payment | 82160.36 | 0 | 82160.36 |  |  |  | Electrical | Greens Electric | RI Waxahachie | 10295 | NA | Wire Transfer | RIW-CFR-16-026
2025-02-11 | 16 | 2 | Electrical Labor | GMC Electric | 5500 | 550 | 4950 |  |  |  | Electrical | GMC Electric | RI Waxahachie | 10318 | Yes | ACH | RIW-CFR-16-027
2025-02-01 | 16 | 6 | Electrical Material | Elliott Electric | 37.69 | 0 | 37.69 |  |  |  | Electrical | Elliott Electric | Boulder AMEX | 10229 | NA | Credit Card | RIW-CFR-16-028
2025-02-03 | 16 | 6 | Electrical Material | Elliott Electric | 364.83 | 0 | 364.83 |  |  |  | Electrical | Elliott Electric | Boulder AMEX | 10230 | NA | Credit Card | RIW-CFR-16-029
2025-02-03 | 16 | 6 | Electrical Material | Elliott Electric | 1126.38 | 0 | 1126.38 |  |  |  | Electrical | Elliott Electric | Boulder AMEX | 10231 | NA | Credit Card | RIW-CFR-16-030
2025-02-03 | 16 | 6 | Electrical Material | Elliott Electric | 2229.42 | 0 | 2229.42 |  |  |  | Electrical | Elliott Electric | Boulder AMEX | 10232 | NA | Credit Card | RIW-CFR-16-031
2025-02-04 | 16 | 6 | Electrical Material | Elliott Electric | 127.41 | 0 | 127.41 |  |  |  | Electrical | Elliott Electric | Boulder AMEX | 10233 | NA | Credit Card | RIW-CFR-16-032
2025-02-08 | 16 | 6 | Electrical Material | Elliott Electric | 2982.84 | 0 | 2982.84 |  |  |  | Electrical | Elliott Electric | Boulder AMEX | 10234 | NA | Credit Card | RIW-CFR-16-033
2025-02-10 | 16 | 6 | Electrical Material | Elliott Electric | 567.76 | 0 | 567.76 |  |  |  | Electrical | Elliott Electric | Boulder AMEX | 10235 | NA | Credit Card | RIW-CFR-16-034
2025-01-21 | 16 | 6 | Electrical Material | Elliott Electric | 3269.15 | 0 | 3269.15 |  |  |  | Electrical | Elliott Electric | Boulder AMEX | 10236 | NA | Credit Card | RIW-CFR-16-035
2025-01-23 | 16 | 6 | Electrical Material | Elliott Electric | 1307.12 | 0 | 1307.12 |  |  |  | Electrical | Elliott Electric | Boulder AMEX | 10237 | NA | Credit Card | RIW-CFR-16-036
2025-03-07 | 16 | 6 | Electrical Material | Elliott Electric | 248.92 | 0 | 248.92 |  |  |  | Electrical | Elliott Electric | Owner (JP) AMEX | 10238 | NA | Credit Card | RIW-CFR-16-037
2025-03-07 | 16 | 6 | Electrical Material | Elliott Electric | 3498.37 | 0 | 3498.37 |  |  |  | Electrical | Elliott Electric | Owner (JP) AMEX | 10239 | NA | Credit Card | RIW-CFR-16-038
2025-04-08 | 16 | 6 | Fire Alarm Rough | From Safe Life FP (Invoice 02) | 46500 | 4650 | 41850 |  |  |  | Fire Alarm | Safe Life Fire Protection | RI Waxahachie | 10344 | Yes | Wire Transfer | RIW-CFR-16-039
2025-03-11 | 16 | 7 | Electrical Material | Elliott Electric | 190.52 | 0 | 190.52 |  |  |  | Electrical | Elliott Electric | Owner (JP) AMEX | 10373 | NA | Credit Card | RIW-CFR-16-040
2025-03-31 | 16 | 7 | Electrical Material | Elliott Electric | 115.11 | 0 | 115.11 |  |  |  | Electrical | Elliott Electric | Owner (JP) AMEX | 10374 | NA | Credit Card | RIW-CFR-16-041
2025-03-31 | 16 | 7 | Electrical Material | Elliott Electric | 2257.88 | 0 | 2257.88 |  |  |  | Electrical | Elliott Electric | Owner (JP) AMEX | 10375 | NA | Credit Card | RIW-CFR-16-042
2025-03-31 | 16 | 7 | Electrical Material | Elliott Electric | 6928 | 0 | 6928 |  |  |  | Electrical | Elliott Electric | Owner (JP) AMEX | 10376 | NA | Credit Card | RIW-CFR-16-043
2025-04-03 | 16 | 7 | Electrical Material | Elliott Electric | 31.42 | 0 | 31.42 |  |  |  | Electrical | Elliott Electric | Owner (JP) AMEX | 10377 | NA | Credit Card | RIW-CFR-16-044
2025-04-03 | 16 | 7 | Electrical Material | Elliott Electric | 39.34 | 0 | 39.34 |  |  |  | Electrical | Elliott Electric | Owner (JP) AMEX | 10378 | NA | Credit Card | RIW-CFR-16-045
2025-04-03 | 16 | 7 | Electrical Material | Elliott Electric | 972.67 | 0 | 972.67 |  |  |  | Electrical | Elliott Electric | Owner (JP) AMEX | 10379 | NA | Credit Card | RIW-CFR-16-046
2025-04-04 | 16 | 7 | Electrical Material | Elliott Electric | 13.6 | 0 | 13.6 |  |  |  | Electrical | Elliott Electric | Owner (JP) AMEX | 10382 | NA | Credit Card | RIW-CFR-16-047
2025-04-04 | 16 | 7 | Electrical Material | Elliott Electric | 15.74 | 0 | 15.74 |  |  |  | Electrical | Elliott Electric | Owner (JP) AMEX | 10380 | NA | Credit Card | RIW-CFR-16-048
2025-04-04 | 16 | 7 | Electrical Material | Elliott Electric | 22.35 | 0 | 22.35 |  |  |  | Electrical | Elliott Electric | Owner (JP) AMEX | 10383 | NA | Credit Card | RIW-CFR-16-049
2025-04-04 | 16 | 7 | Electrical Material | Elliott Electric | 89.31 | 0 | 89.31 |  |  |  | Electrical | Elliott Electric | Owner (JP) AMEX | 10384 | NA | Credit Card | RIW-CFR-16-050
2025-04-04 | 16 | 7 | Electrical Material | Elliott Electric | 771.01 | 0 | 771.01 |  |  |  | Electrical | Elliott Electric | Owner (JP) AMEX | 10381 | NA | Credit Card | RIW-CFR-16-051
2025-04-08 | 16 | 7 | Electrical Material | Elliott Electric | 5296.67 | 0 | 5296.67 |  |  |  | Electrical | Elliott Electric | Owner (JP) AMEX | 10407 | NA | Credit Card | RIW-CFR-16-052
2025-04-25 | 16 | 7 | Switch Gear | Greens Distribution - Additional Payment | 69121.18 | 0 | 69121.18 |  |  |  | Electrical | Greens Electric | RI Waxahachie | 10434 | NA | Wire Transfer | RIW-CFR-16-053
2025-04-09 | 16 | 8 | Electrical Material | Elliott Electric | 7.13 | 0 | 7.13 |  |  |  | Electrical | Elliott Electric | Owner (JP) AMEX | 10408 | NA | Credit Card | RIW-CFR-16-054
2025-05-01 | 16 | 8 | Structured Cabling - First Payment | From PSM Tech | 18750 | 1875 | 16875 |  |  |  | Structural Cabling | PSM Tech | RI Waxahachie | 10448 | No | Wire Transfer | RIW-CFR-16-055
2025-05-21 | 16 | 2/8 | Electrical Rough In Labor | GMC Electric | 30000 | 3000 | 27000 |  |  |  | Electrical | GMC Electric | RI Waxahachie | 10504 | Yes | ACH | RIW-CFR-16-056
2025-05-12 | 16 | 9 | Electrical Material | Elliott Electric | 23592.05 | 0 | 23592.05 |  |  |  | Electrical | Elliott Electric | Owner (JP) AMEX | 10481 | NA | Credit Card | RIW-CFR-16-057
2025-05-13 | 16 | 9 | Electrical Material | Elliott Electric | 15728.03 | 0 | 15728.03 |  |  |  | Electrical | Elliott Electric | Owner (JP) AMEX | 10484 | NA | Credit Card | RIW-CFR-16-058
2025-05-13 | 16 | 9 | Electrical Material | Elliott Electric | 5158.98 | 0 | 5158.98 |  |  |  | Electrical | Elliott Electric | Owner (JP) AMEX | 10485 | NA | Credit Card | RIW-CFR-16-059
2025-05-13 | 16 | 9 | Electrical Material | Elliott Electric | 3109.45 | 0 | 3109.45 |  |  |  | Electrical | Elliott Electric | Owner (JP) AMEX | 10486 | NA | Credit Card | RIW-CFR-16-060
2025-05-13 | 16 | 9 | Electrical Material | Elliott Electric | 105.28 | 0 | 105.28 |  |  |  | Electrical | Elliott Electric | Owner (JP) AMEX | 10487 | NA | Credit Card | RIW-CFR-16-061
2025-05-15 | 16 | 9 | Electrical Material | Elliott Electric | 66.28 | 0 | 66.28 |  |  |  | Electrical | Elliott Electric | Owner (JP) AMEX | 10491 | NA | Credit Card | RIW-CFR-16-062
2025-05-15 | 16 | 9 | Electrical Material | Elliott Electric | 381.95 | 0 | 381.95 |  |  |  | Electrical | Elliott Electric | Owner (JP) AMEX | 10492 | NA | Credit Card | RIW-CFR-16-063
2025-05-16 | 16 | 9 | Electrical Material | Elliott Electric | 931.92 | 0 | 931.92 |  |  |  | Electrical | Elliott Electric | Owner (JP) AMEX | 10468 | NA | Credit Card | RIW-CFR-16-064
2025-05-16 | 16 | 9 | Electrical Material | Elliott Electric | 17403.24 | 0 | 17403.24 |  |  |  | Electrical | Elliott Electric | Owner (JP) AMEX | 10498 | NA | Credit Card | RIW-CFR-16-065
2025-05-19 | 16 | 9 | Electrical Material | Elliott Electric | 47953.64 | 0 | 47953.64 |  |  |  | Electrical | Elliott Electric | Owner (JP) AMEX | 10499 | NA | Credit Card | RIW-CFR-16-066
2025-05-20 | 16 | 9 | Electrical Material | Elliott Electric | 1106.59 | 0 | 1106.59 |  |  |  | Electrical | Elliott Electric | Owner (JP) AMEX | 10500 | NA | Credit Card | RIW-CFR-16-067
2025-05-20 | 16 | 9 | Electrical Material | Elliott Electric | 301.84 | 0 | 301.84 |  |  |  | Electrical | Elliott Electric | Owner (JP) AMEX | 10501 | NA | Credit Card | RIW-CFR-16-068
2025-05-23 | 16 | 9 | Electrical Material | Elliott Electric | 1050.72 | 0 | 1050.72 |  |  |  | Electrical | Elliott Electric | Owner (JP) AMEX | 10508 | NA | Credit Card | RIW-CFR-16-069
2025-05-27 | 16 | 9 | Electrical Material | Elliott Electric | 66.28 | 0 | 66.28 |  |  |  | Electrical | Elliott Electric | Owner (JP) AMEX | 10525 | NA | Credit Card | RIW-CFR-16-070
2025-05-27 | 16 | 9 | Electrical Material | Elliott Electric | 24708.06 | 0 | 24708.06 |  |  |  | Electrical | Elliott Electric | Owner (JP) AMEX | 10521 | NA | Credit Card | RIW-CFR-16-071
2025-06-13 | 16 | 9 | Electrical Rough In Labor | GMC Electric | 27500 | 2750 | 24750 |  |  |  | Electrical | GMC Electric | RI Waxahachie | 10522 | Yes | ACH | RIW-CFR-16-072
2025-05-28 | 16 | 9 | Electrical Material | Elliott Electric | 706.33 | 0 | 706.33 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10526 | NA | Credit Card | RIW-CFR-16-073
2025-05-29 | 16 | 9 | Electrical Material | Elliott Electric | 24058.56 | 0 | 24058.56 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10527 | NA | Credit Card | RIW-CFR-16-074
2025-05-30 | 16 | 10 | Electrical Material | Elliott Electric | 3678.71 | 0 | 3678.71 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10528 | NA | Credit Card | RIW-CFR-16-075
2025-06-02 | 16 | 10 | Electrical Material | Elliott Electric | 292.4 | 0 | 292.4 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10529 | NA | Credit Card | RIW-CFR-16-076
2025-06-03 | 16 | 10 | Electrical Material | Elliott Electric | 322.82 | 0 | 322.82 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10530 | NA | Credit Card | RIW-CFR-16-077
2025-06-03 | 16 | 10 | Electrical Material | Elliott Electric | 124.73 | 0 | 124.73 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10531 | NA | Credit Card | RIW-CFR-16-078
2025-06-05 | 16 | 10 | Electrical Material | Elliott Electric | 649.5 | 0 | 649.5 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10532 | NA | Credit Card | RIW-CFR-16-079
2025-06-05 | 16 | 10 | Electrical Material | Elliott Electric | 649.5 | 0 | 649.5 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10533 | NA | Credit Card | RIW-CFR-16-080
2025-06-05 | 16 | 10 | Electrical Material | Elliott Electric | 579.84 | 0 | 579.84 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10534 | NA | Credit Card | RIW-CFR-16-081
2025-06-09 | 16 | 10 | Electrical Material | Elliott Electric | -649.5 | 0 | -649.5 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10535 | NA | Credit Card | RIW-CFR-16-082
2025-06-09 | 16 | 10 | Electrical Material | Elliott Electric | -649.5 | 0 | -649.5 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10536 | NA | Credit Card | RIW-CFR-16-083
2025-06-10 | 16 | 10 | Electrical Material | Elliott Electric | 25584.55 | 0 | 25584.55 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10537 | NA | Credit Card | RIW-CFR-16-084
2025-06-10 | 16 | 10 | Electrical Material | Elliott Electric | 1277.35 | 0 | 1277.35 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10538 | NA | Credit Card | RIW-CFR-16-085
2025-06-11 | 16 | 10 | Electrical Material | Elliott Electric | 337.56 | 0 | 337.56 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10539 | NA | Credit Card | RIW-CFR-16-086
2025-06-12 | 16 | 10 | Electrical Material | Elliott Electric | 640.07 | 0 | 640.07 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10540 | NA | Credit Card | RIW-CFR-16-087
2025-06-17 | 16 | 10 | Electrical Material | Elliott Electric | 49.67 | 0 | 49.67 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10600 | NA | Credit Card | RIW-CFR-16-088
2025-06-17 | 16 | 10 | Electrical Material | Elliott Electric | 5758.82 | 0 | 5758.82 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10601 | NA | Credit Card | RIW-CFR-16-089
2025-06-18 | 16 | 10 | Electrical Material | Elliott Electric | 162.38 | 0 | 162.38 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10602 | NA | Credit Card | RIW-CFR-16-090
2025-06-24 | 16 | 10 | Electrical Material | Elliott Electric | 59.13 | 0 | 59.13 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10603 | NA | Credit Card | RIW-CFR-16-091
2025-06-25 | 16 | 10 | Electrical Material | Elliott Electric | 1202.93 | 0 | 1202.93 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10611 | NA | Credit Card | RIW-CFR-16-092
2025-07-18 | 16 | 10 | Electrical Rough In Labor and Unit Feeders | GMC Electric - Pay App 05 | 34000 | 3400 | 30600 |  |  |  | Electrical | GMC Electric | RI Waxahachie | 10614 | No | ACH | RIW-CFR-16-093
2025-06-30 | 16 | 11 | Oncor Easement | From Traverse Land Surveying | 703.63 | 0 | 703.63 |  |  |  | Electrical | Traverse | Boulder AMEX | 10657 | NA | Credit Card | RIW-CFR-16-094
2025-06-30 | 16 | 11 | Electrical Material | From Elliott Electric | 554.78 | 0 | 554.78 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10642 | NA | Credit Card | RIW-CFR-16-095
2025-07-08 | 16 | 11 | Electrical Material | From Elliott Electric | 39.08 | 0 | 39.08 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10650 | NA | Credit Card | RIW-CFR-16-096
2025-07-10 | 16 | 11 | Electrical Material | From Elliott Electric | 785.87 | 0 | 785.87 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10646 | NA | Credit Card | RIW-CFR-16-097
2025-07-10 | 16 | 11 | Electrical Material | From Elliott Electric | 279.05 | 0 | 279.05 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10645 | NA | Credit Card | RIW-CFR-16-098
2025-07-10 | 16 | 11 | Electrical Material | From Elliott Electric | 16.75 | 0 | 16.75 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10643 | NA | Credit Card | RIW-CFR-16-099
2025-07-10 | 16 | 11 | Electrical Material | From Elliott Electric | -18.46 | 0 | -18.46 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10644 | NA | Credit Card | RIW-CFR-16-100
2025-07-11 | 16 | 11 | Electrical Material | From Elliott Electric | 561.95 | 0 | 561.95 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10647 | NA | Credit Card | RIW-CFR-16-101
2025-07-11 | 16 | 11 | Electrical Material | From Elliott Electric | 104.48 | 0 | 104.48 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10648 | NA | Credit Card | RIW-CFR-16-102
2025-07-11 | 16 | 11 | Electrical Material | From Elliott Electric | 91.87 | 0 | 91.87 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10649 | NA | Credit Card | RIW-CFR-16-103
2025-07-15 | 16 | 11 | Electrical Material | From Elliott Electric | 843.96 | 0 | 843.96 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10695 | NA | Credit Card | RIW-CFR-16-104
2025-07-15 | 16 | 11 | Electrical Material | From Elliott Electric | 107.25 | 0 | 107.25 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10696 | NA | Credit Card | RIW-CFR-16-105
2025-07-16 | 16 | 11 | Electrical Material | From Elliott Electric | 1404 | 0 | 1404 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10697 | NA | Credit Card | RIW-CFR-16-106
2025-07-16 | 16 | 11 | Electrical Material | From Elliott Electric | 875.4 | 0 | 875.4 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10698 | NA | Credit Card | RIW-CFR-16-107
2025-07-16 | 16 | 11 | Electrical Material | From Elliott Electric | 505.24 | 0 | 505.24 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10699 | NA | Credit Card | RIW-CFR-16-108
2025-07-16 | 16 | 11 | Electrical Material | From Elliott Electric | 11.28 | 0 | 11.28 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10700 | NA | Credit Card | RIW-CFR-16-109
2025-07-17 | 16 | 11 | Electrical Material | From Elliott Electric | 5224.82 | 0 | 5224.82 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10701 | NA | Credit Card | RIW-CFR-16-110
2025-07-17 | 16 | 11 | Electrical Material | From Elliott Electric | 210.35 | 0 | 210.35 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10702 | NA | Credit Card | RIW-CFR-16-111
2025-07-17 | 16 | 11 | Electrical Material | From Elliott Electric | 164.78 | 0 | 164.78 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10703 | NA | Credit Card | RIW-CFR-16-112
2025-07-17 | 16 | 11 | Electrical Material | From Elliott Electric | 149.43 | 0 | 149.43 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10704 | NA | Credit Card | RIW-CFR-16-113
2025-07-17 | 16 | 11 | Electrical Material | From Elliott Electric | 148.65 | 0 | 148.65 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10705 | NA | Credit Card | RIW-CFR-16-114
2025-07-17 | 16 | 11 | Electrical Material | From Elliott Electric | 119.71 | 0 | 119.71 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10706 | NA | Credit Card | RIW-CFR-16-115
2025-07-18 | 16 | 11 | Electrical Material | From Elliott Electric | 2513.56 | 0 | 2513.56 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10707 | NA | Credit Card | RIW-CFR-16-116
2025-07-21 | 16 | 11 | Electrical Material | From Elliott Electric | 820.32 | 0 | 820.32 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10708 | NA | Credit Card | RIW-CFR-16-117
[Confirm] | 16 | 11 | Electrical Material | From Elliott Electric | 21575.08 | 0 | 21575.08 |  |  |  | Electrical | Elliott Electric | [Confirm] | 10720 | NA | Credit Card | RIW-CFR-16-118
2025-07-25 | 16 | 11 | Electrical Material | From Elliott Electric | 84.63 | 0 | 84.63 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10721 | NA | Credit Card | RIW-CFR-16-119
2025-07-25 | 16 | 11 | Electrical Material | From Elliott Electric | 10180.26 | 0 | 10180.26 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10722 | NA | Credit Card | RIW-CFR-16-120
[Confirm] | 16 | 11 | Electrical Material | From Elliott Electric | 162.39 | 0 | 162.39 |  |  |  | Electrical | Elliott Electric | [Confirm] | 10723 | NA | Credit Card | RIW-CFR-16-121
2025-09-02 | 16 | 11 | Equipment Rentals (For Electrical) | EquipmentShare | 1982.35 | 0 | 1982.35 |  |  |  | Electrical | EquipmentShare | RI Waxahachie | 10728 | NA | ACH | RIW-CFR-16-122
2025-09-18 | 16 | 11 | Fire Sprinkler - Change Order | From Safe Life FP (Invoice 03) - Split (First Payment) | 4666.6667 | 466.6667 | 4200 |  |  |  | Fire Alarm | Safe Life Fire Protection | RI Waxahachie | 10731 | No | ACH | RIW-CFR-16-123
2025-10-07 | 16 | 11 | Fire Sprinkler - Change Order | From Safe Life FP (Invoice 03) - Split (Final Payment) | 48333.3333 | 4833.3333 | 43500 |  |  |  | Fire Alarm | Safe Life Fire Protection | RI Waxahachie | 10731 | No | ACH | RIW-CFR-16-124
2025-07-31 | 16 | 12 | Electrical Material | Elliott Electric | 2259.56 | 0 | 2259.56 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10732 | NA | Credit Card | RIW-CFR-16-125
2025-07-31 | 16 | 12 | Electrical Material | Elliott Electric | 907.52 | 0 | 907.52 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10733 | NA | Credit Card | RIW-CFR-16-126
2025-08-01 | 16 | 12 | Electrical Material | Elliott Electric | 3006.12 | 0 | 3006.12 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10734 | NA | Credit Card | RIW-CFR-16-127
2025-08-01 | 16 | 12 | Electrical Material | Elliott Electric | 607.3 | 0 | 607.3 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10735 | NA | Credit Card | RIW-CFR-16-128
2025-08-01 | 16 | 12 | Electrical Material | Elliott Electric | 607.26 | 0 | 607.26 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10736 | NA | Credit Card | RIW-CFR-16-129
2025-08-01 | 16 | 12 | Electrical Material | Elliott Electric | 215.96 | 0 | 215.96 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10737 | NA | Credit Card | RIW-CFR-16-130
2025-08-01 | 16 | 12 | Electrical Material | Elliott Electric | 41.2 | 0 | 41.2 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10738 | NA | Credit Card | RIW-CFR-16-131
2025-08-01 | 16 | 12 | Electrical Material | Elliott Electric | 4.81 | 0 | 4.81 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10739 | NA | Credit Card | RIW-CFR-16-132
2025-08-01 | 16 | 12 | Electrical Material | Elliott Electric - Return | -640.05 | 0 | -640.05 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10740 | NA | Credit Card | RIW-CFR-16-133
2025-08-07 | 16 | 12 | Electrical Material | Elliott Electric - Return | -1267.89 | 0 | -1267.89 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10741 | NA | Credit Card | RIW-CFR-16-134
2025-08-02 | 16 | 12 | Electrical Material | Elliott Electric | 10.99 | 0 | 10.99 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10742 | NA | Credit Card | RIW-CFR-16-135
2025-08-04 | 16 | 12 | Electrical Material | Elliott Electric | 28.49 | 0 | 28.49 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10743 | NA | Credit Card | RIW-CFR-16-136
2025-08-05 | 16 | 12 | Electrical Material | Elliott Electric | 1669.52 | 0 | 1669.52 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10744 | NA | Credit Card | RIW-CFR-16-137
2025-08-05 | 16 | 12 | Electrical Material | Elliott Electric | 63.33 | 0 | 63.33 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10745 | NA | Credit Card | RIW-CFR-16-138
2025-08-06 | 16 | 12 | Electrical Material | Elliott Electric | 1461.38 | 0 | 1461.38 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10746 | NA | Credit Card | RIW-CFR-16-139
2025-08-06 | 16 | 12 | Electrical Material | Elliott Electric | 171.16 | 0 | 171.16 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10747 | NA | Credit Card | RIW-CFR-16-140
2025-08-07 | 16 | 12 | Electrical Material | Elliott Electric | 1007.43 | 0 | 1007.43 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10748 | NA | Credit Card | RIW-CFR-16-141
2025-08-08 | 16 | 12 | Electrical Material | Elliott Electric | 1217.25 | 0 | 1217.25 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10749 | NA | Credit Card | RIW-CFR-16-142
2025-08-09 | 16 | 12 | Electrical Material | Elliott Electric | 2027.07 | 0 | 2027.07 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10750 | NA | Credit Card | RIW-CFR-16-143
2025-08-11 | 16 | 12 | Electrical Material | Elliott Electric | 1231.86 | 0 | 1231.86 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10751 | NA | Credit Card | RIW-CFR-16-144
2025-08-11 | 16 | 12 | Electrical Material | Elliott Electric | 1456.31 | 0 | 1456.31 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10752 | NA | Credit Card | RIW-CFR-16-145
2025-08-12 | 16 | 12 | Electrical Material | Elliott Electric | 308.32 | 0 | 308.32 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10753 | NA | Credit Card | RIW-CFR-16-146
2025-08-13 | 16 | 12 | Electrical Material | Elliott Electric | 27.82 | 0 | 27.82 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10754 | NA | Credit Card | RIW-CFR-16-147
2025-08-14 | 16 | 12 | Electrical Material | Elliott Electric | 38688.38 | 0 | 38688.38 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10755 | NA | Credit Card | RIW-CFR-16-148
2025-08-14 | 16 | 12 | Electrical Material | Elliott Electric | 1727.37 | 0 | 1727.37 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10756 | NA | Credit Card | RIW-CFR-16-149
2025-08-14 | 16 | 12 | Electrical Material | Elliott Electric | 1061.9 | 0 | 1061.9 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10757 | NA | Credit Card | RIW-CFR-16-150
2025-08-14 | 16 | 12 | Electrical Material | Elliott Electric | 170.3 | 0 | 170.3 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10758 | NA | Credit Card | RIW-CFR-16-151
2025-08-14 | 16 | 12 | Electrical Material | Elliott Electric | 78.16 | 0 | 78.16 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10759 | NA | Credit Card | RIW-CFR-16-152
2025-08-14 | 16 | 12 | Electrical Material | Elliott Electric | 66.01 | 0 | 66.01 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10760 | NA | Credit Card | RIW-CFR-16-153
2025-08-14 | 16 | 12 | Electrical Material | Elliott Electric | 40.33 | 0 | 40.33 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10761 | NA | Credit Card | RIW-CFR-16-154
2025-08-15 | 16 | 12 | Electrical Material | Elliott Electric | 363.55 | 0 | 363.55 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10762 | NA | Credit Card | RIW-CFR-16-155
2025-08-16 | 16 | 12 | Electrical Material | Elliott Electric | 1016.46 | 0 | 1016.46 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10763 | NA | Credit Card | RIW-CFR-16-156
2025-08-18 | 16 | 12 | Electrical Material | Elliott Electric | 54.67 | 0 | 54.67 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10766 | NA | Credit Card | RIW-CFR-16-157
2025-08-19 | 16 | 12 | Electrical Material | Elliott Electric | 292.28 | 0 | 292.28 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10816 | NA | Credit Card | RIW-CFR-16-158
2025-08-19 | 16 | 12 | Electrical Material | Elliott Electric | 23.99 | 0 | 23.99 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10817 | NA | Credit Card | RIW-CFR-16-159
2025-08-19 | 16 | 12 | Electrical Material | Elliott Electric | 14.2 | 0 | 14.2 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10818 | NA | Credit Card | RIW-CFR-16-160
2025-08-20 | 16 | 12 | Electrical Material | Elliott Electric | 2196.07 | 0 | 2196.07 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10819 | NA | Credit Card | RIW-CFR-16-161
2025-08-21 | 16 | 12 | Electrical Material | From GMC Electric | 5500 | 550 | 4950 |  |  |  | Electrical | GMC Electric | RI Waxahachie | 10836 | No | Check | RIW-CFR-16-162
2025-09-23 | 16 | 12 | Equipment Rentals (For Electrical) | EquipmentShare | 2028.98 | 0 | 2028.98 |  |  |  | Electrical | EquipmentShare | RI Waxahachie | 10850 | NA | ACH | RIW-CFR-16-163
2025-08-20 | 16 | 12 | Labor & Gas for Generators | From J&S7 Consulting | 1083.0733 | 0 | 1083.0733 |  |  |  | Electrical | J&S7 Consulting | Boulder | 10833 | NA | Check | RIW-CFR-16-164
2025-09-22 | 16 | 13 | Electrical Material | Elliott Electric | 78246.35 | 0 | 78246.35 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 10930 | NA | Credit Card | RIW-CFR-16-165
2025-09-08 | 16 | 13 | Electrical Material | From GMC Electric | 11000 | 1100 | 9900 |  |  |  | Electrical | GMC Electric | RI Waxahachie | 10893 | No | Check | RIW-CFR-16-166
2025-10-17 | 16 | 14 | Electrical Labor | From GMC Electric | 11800 | 1180 | 10620 |  |  |  | Electrical | GMC Electric | RI Waxahachie | 10995 | No | ACH | RIW-CFR-16-167
2025-11-05 | 16 | 14 | Electrical Material | From Elliott Electrical | 93000.01 | 0 | 93000.01 |  |  |  | Electrical | Elliott Electrical | Jaimin AMEX | 11053 | NA | Credit Card | RIW-CFR-16-168
2025-11-20 | 16 | 14 | Electrical Labor | From GMC Electric | 30750 | 3075 | 27675 |  |  |  | Electrical | GMC Electric | RI Waxahachie | 11060 | No | ACH | RIW-CFR-16-169
[To Be Paid] | 16 | 14 | Electrical - Equipment | From EquipmentShare | 4742.58 | 0 | 4742.58 |  |  |  | Electrical | EquipmentShare | RI Waxahachie | 11054 | NA | [To Be Paid] | RIW-CFR-16-170
2025-11-14 | 16 | 15 | Electrical Material | From Home Depot - Electrical Nonmetallic Tubing & Black Oxide Step Drill Bit | 323.18 | 0 | 323.18 |  |  |  | Electrical | Home Depot | Boulder AMEX | 11074 | NA | Credit Card | RIW-CFR-16-171
2025-11-14 | 16 | 15 | Electrical Material | From Home Depot - Electrical Nonmetallic Tubing | 51.96 | 0 | 51.96 |  |  |  | Electrical | Home Depot | Boulder AMEX | 11076 | NA | Credit Card | RIW-CFR-16-172
2025-12-04 | 16 | 15 | Electrical Material | From Home Depot - Indoor Multi-Outlet Extension Cord with Banana Tap | 59.38 | 0 | 59.38 |  |  |  | Electrical | Home Depot | Boulder AMEX | 11115 | NA | Credit Card | RIW-CFR-16-173
2025-12-12 | 16 | 15 | Electrical Material | From Home Depot - Extension Cords and Appliance Replacement Cord | 1251.87 | 0 | 1251.87 |  |  |  | Electrical | Home Depot | Boulder AMEX | 11173 | NA | Credit Card | RIW-CFR-16-174
2025-12-15 | 16 | 15 | Electrical Material | From Home Depot - Extension Cords and Appliance Replacement Cord | 300.5 | 0 | 300.5 |  |  |  | Electrical | Home Depot | Jaimin AMEX | 11179 | NA | Credit Card | RIW-CFR-16-175
2026-01-05 | 16 | 15 | Electrical Material | Elliott Electric | 24792.5 | 0 | 24792.5 |  |  |  | Electrical | Elliott Electric | Jaimin AMEX | 11223 | NA | Credit Card | RIW-CFR-16-176
2026-01-16 | 16 | 16 | Electrical Material | From Home Depot - Electrical Tape & Electrical Switch and Outlet Box | 213.58 | 0 | 213.58 |  |  |  | Electrical | Home Depot | Boulder AMEX | 11234 | NA | Credit Card | RIW-CFR-16-177
2026-01-26 | 16 | 16 | Electrical - Light Pole Staking | From AIM Construction Services | 720 | 0 | 720 |  |  |  | Electrical | AIM Construction Services | Jaimin AMEX | 11273 | NA | Credit Card | RIW-CFR-16-178
2025-12-05 | 16 | 16 | Electrical Material | From Home Depot - PVC Conduit, Cable Zip & Electrical Tape | 148.42 | 0 | 148.42 |  |  |  | Electrical | Home Depot | Boulder AMEX | 11282 | NA | Credit Card | RIW-CFR-16-179
2026-01-05 | 16 | 16 | Light Pole Removal and Relocation | From Oncor Electric Delivery Company LLC | 5003.22 | 0 | 5003.22 |  |  |  | Electrical | Oncor Electric Delivery Company | Jai | 11284 | NA | Credit Card | RIW-CFR-16-180
2026-02-18 | 16 | 16 | Structured Cabling | From PSM Tech LLC - Pay App 02 | 37500 | 3750 | 33750 |  |  |  | Structural Cabling | PSM Tech | RI Waxahachie | 12183 | NA | ACH | RIW-CFR-16-181
[To Be Paid] | 16 | 16 | Electrical Labor | From GMC Electric - Pay App 09 | 20000 | 2000 | 18000 |  |  |  | Electrical | GMC Electrical | [To Be Paid] | 12186 | NA | [To Be Paid] | RIW-CFR-16-182
2026-02-14 | 16 | 17 | Electrical Material | From Home Depot - Electrical MaterialsTape, Pipe Clamp, Gauge and Gloves | 268.23 | 0 | 268.23 |  |  |  | Electrical | Home Depot | Boulder AMEX | 12206 | NA | Credit Card
2026-02-16 | 16 | 17 | Electrical Material | From Home Depot - Extension Cords And Cable Connectors | 127.03 | 0 | 127.03 |  |  |  | Electrical | Home Depot | Boulder AMEX | 12208 | NA | Credit Card
2026-02-10 | 16 | 17 | Electrical Material | From Home Depot - Electrical MaterialsConduit Fittings and Clamp Connectors | 21.4 | 0 | 21.4 |  |  |  | Electrical | Home Depot | Boulder AMEX | 12217 | NA | Credit Card
2026-02-17 | 16 | 17 | Electrical Material | From Home Depot - AC Disconnect Switches And Electrical Rough Materials | 277.02 | 0 | 277.02 |  |  |  | Electrical | Home Depot | Boulder AMEX | 12239 | NA | Credit Card
2026-02-17 | 16 | 17 | Electrical Material | From Home Depot - Duplex Outlet, Anchors, Screws | 125.05 | 0 | 125.05 |  |  |  | Electrical | Home Depot | Boulder AMEX | 12240 | NA | Credit Card
2026-02-16 | 16 | 17 | Electrical Material | From Home Depot - LED Light Bulbs Selected Color Temperature | 129.58 | 0 | 129.58 |  |  |  | Electrical | Home Depot | Boulder AMEX | 12245 | NA | Credit Card
2026-02-14 | 16 | 17 | Electrical Material | From Home Depot - Electrical DevicesSingle and Duplex Outlet and Wall Plate | 136.84 | 0 | 136.84 |  |  |  | Electrical | Home Depot | Boulder AMEX | 12251 | NA | Credit Card
2026-02-14 | 16 | 17 | Electrical Material | From Home Depot - LED Light Bulb | 581.04 | 0 | 581.04 |  |  |  | Electrical | Home Depot | Boulder AMEX | 12254 | NA | Credit Card
2026-02-12 | 16 | 17 | Electrical Material | From Home Depot - Electrical MaterialsRange Cord, Outlet, Blade Kit and Tape | 921.87 | 0 | 921.87 |  |  |  | Electrical | Home Depot | Boulder AMEX | 12267 | NA | Credit Card
2026-02-20 | 16 | 17 | Electrical Material | From Home Depot - Wires, Conduits, Duplex Outlet, Rod | 1472.15 | 0 | 1472.15 |  |  |  | Electrical | Home Depot | Boulder AMEX | 12323 | NA | Credit Card
2026-02-20 | 16 | 17 | Electrical Material | From Home Depot - PVC Conduit, Support Rod, Connectors | 747.74 | 0 | 747.74 |  |  |  | Electrical | Home Depot | Boulder AMEX | 12326 | NA | Credit Card
2026-02-21 | 16 | 17 | Electrical Material | From Home Depot - Circular Saw Blade, Plunger and Brush | 49.13 | 0 | 49.13 |  |  |  | Electrical | Home Depot | Boulder AMEX | 12327 | NA | Credit Card
2026-02-23 | 16 | 17 | Electrical Material | From Home Depot - Duplex Outlet, GDCI Outlet. | 466.91 | 0 | 466.91 |  |  |  | Electrical | Home Depot | Boulder AMEX | 12330 | NA | Credit Card
2026-02-23 | 16 | 17 | Electrical Material | From Home Depot - Wire Dryer Cord, Ciruit Breaker, Outlet Cover and Clamp Connector | 95.94 | 0 | 95.94 |  |  |  | Electrical | Home Depot | Boulder AMEX | 12331 | NA | Credit Card
2026-02-25 | 16 | 17 | Electrical Material | From Home Depot - Light Bulb, Switches & Outlet | 352.99 | 0 | 352.99 |  |  |  | Electrical | Home Depot | Boulder AMEX | 12454 | NA | Credit Card
2026-03-02 | 16 | 17 | Electrical Material | From Home Depot - Thermostat Wire & Switches | 83.29 | 0 | 83.29 |  |  |  | Electrical | Home Depot | Boulder AMEX | 12489 | NA | Credit Card
2026-02-07 | 16 | 17 | Pendant Lantern | From Amazon | 265.26 | 0 | 265.26 |  |  |  | Electrical | Amazon | Boulder AMEX | [TBD] | NA | Credit Card
2026-02-07 | 16 | 17 | Pendant Lantern | From Amazon | 176.84 | 0 | 176.84 |  |  |  | Electrical | Amazon | Boulder AMEX | [TBD] | NA | Credit Card
[To Be Paid] | 16 | 17 | Fire Sprinkler Trim | From Safelife Fire protection - Pay App 05 | 46500 | 4650 | 41850 |  |  |  | Fire Alarm | Safelife Fire protection | [To Be Paid] | [TBD] | No | [To Be Paid]
[To Be Paid] | 16 | 17 | Electrical Labor | From GMC Electrical - Pay App 10 (Split) | 10000 | 1000 | 9000 |  |  |  | Electrical | GMC Electrical | [To Be Paid] | [TBD] | NA | [To Be Paid]
17. General Liability
| 17 | 1 | Draw 1 Funds |  |  |  |  | 19553.08 | 0 | 19553.08
| 17 | 3 | Draw 3 Funds |  |  |  |  | 573.03 | 0 | 573.03
| 17 | 4 | Draw 4 Funds |  |  |  |  | 3538.35 | 0 | 3538.35
| 17 | 6 | Draw 6 Funds - Reimbursements |  |  |  |  | 6908.14 | 0 | 6908.14
| 17 | 7 | Draw 7 Funds - Reimbursements |  |  |  |  | 20675.19 | 0 | 20675.19
| 17 | 13 | Draw 13 Funds - Reimbursements |  |  |  |  | 170.23 | 0 | 170.23
| 17 | 14 | Draw 14 Funds - Reimbursements |  |  |  |  | 13323.06 | 0 | 13323.06
| 17 | 15 | Draw 15 Funds - Reimbursements |  |  |  |  | 5299.36 | 0 | 5299.36
| 17 | 16 | Draw 16 Funds - Reimbursements |  |  |  |  | 18319.46 | 0 | 18319.46
| 17 | 17 | Draw 17 Funds - Reimbursements |  |  |  |  | 3640.1 | 0 | 3640.1
2024-08-16 | 17 | 1/3 | Equipment Insurance | Liberty Mutual | 161.97 | 0 | 161.97 |  |  |  | General Liability | Liberty Mutual | Jai |  | NA |  | RIW-CFR-17-001
2024-08-15 | 17 | 1/3 | General Liability Insurance | Dayalji Insurance Agency | 1938.98 | 0 | 1938.98 |  |  |  | General Liability | Dayalji Insurance Agency | Jai |  | NA |  | RIW-CFR-17-002
2024-09-17 | 17 | 1/3 | Equipment Insurance | Liberty Mutual | 170.3 | 0 | 170.3 |  |  |  | General Liability | Liberty Mutual | Jai |  | NA |  | RIW-CFR-17-003
2024-09-15 | 17 | 1/3 | General Liability Insurance | Dayalji Insurance Agency | 941.87 | 0 | 941.87 |  |  |  | General Liability | Dayalji Insurance Agency | Jai |  | NA |  | RIW-CFR-17-004
2024-09-26 | 17 | 1/3 | Equipment Insurance | Liberty Mutual | 1620.35 | 0 | 1620.35 |  |  |  | General Liability | Liberty Mutual | Jai | 10054 | NA |  | RIW-CFR-17-005
2024-09-25 | 17 | 1/3 | General Liability Insurance | Dayalji Insurance Agency | 8476.83 | 0 | 8476.83 |  |  |  | General Liability | Dayalji Insurance Agency | Jai | 10055 | NA |  | RIW-CFR-17-006
| 17 | 1/3 | Builder's Risk Insurance | Liberty Mutual | 3371.31 | 0 | 3371.31 |  |  |  | General Liability | Liberty Mutual | Jaimin Uncle | 10111 | NA |  | RIW-CFR-17-007
2024-11-22 | 17 | 1/3 | Builder's Risk Insurance | Liberty Mutual | 3444.5 | 0 | 3444.5 |  |  |  | General Liability | Liberty Mutual | Jaimin Uncle |  | NA |  | RIW-CFR-17-008
| 17 | 4 | Builder's Risk Insurance | Liberty Mutual - Remaining Charge Amount from Prior Transaction | 82.76 | 0 | 82.76 |  |  |  | General Liability | Liberty Mutual | Jaimin Uncle |  | NA |  | RIW-CFR-17-009
| 17 | 4 | Builder's Risk Insurance | Liberty Mutual | 3455.59 | 0 | 3455.59 |  |  |  | General Liability | Liberty Mutual | Jaimin Uncle |  | NA |  | RIW-CFR-17-010
2025-01-22 | 17 | 6 | Builder's Risk Insurance | Liberty Mutual | 3454.07 | 0 | 3454.07 |  |  |  | General Liability | Liberty Mutual | Jaimin Uncle |  | NA |  | RIW-CFR-17-011
2025-02-22 | 17 | 6 | Builder's Risk Insurance | Liberty Mutual | 3454.07 | 0 | 3454.07 |  |  |  | General Liability | Liberty Mutual | Jaimin Uncle |  | NA |  | RIW-CFR-17-012
2025-03-25 | 17 | 7 | Builder's Risk Insurance | Liberty Mutual | 20675.19 | 0 | 20675.19 |  |  |  | General Liability | Liberty Mutual | Owner (JP) AMEX | 10387 | NA | Credit Card | RIW-CFR-17-013
2025-09-17 | 17 | 13 | Equipment Insurance | Liberty Mutual | 170.23 | 0 | 170.23 |  |  |  | General Liability | Liberty Mutual | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-17-014
2025-10-17 | 17 | 14 | Equipment Insurance | Liberty Mutual | 170.23 | 0 | 170.23 |  |  |  | General Liability | Liberty Mutual | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-17-015
2025-10-21 | 17 | 14 | Builder's Risk Insurance | Newman & Trucker | 9698.76 | 0 | 9698.76 |  |  |  | General Liability | Newman & Tucker | Boulder | [TBD] | NA | Direct Debit | RIW-CFR-17-016
2025-03-22 | 17 | 14 | Builder's Risk Insurance | Liberty Mutual | 3454.07 | 0 | 3454.07 |  |  |  | General Liability | Liberty Mutual | Jaimin Uncle | [TBD] | NA | Credit Card | RIW-CFR-17-017
2025-11-21 | 17 | 15 | General Liability Insurance | General Liability Insurance | 2479.45 | 0 | 2479.45 |  |  |  | General Liability | General Liability Insurance | Boulder | [TBD] | No | Direct Debit | RIW-CFR-17-018
2025-12-22 | 17 | 15 | General Liability Insurance | General Liability Insurance | 2479.45 | 0 | 2479.45 |  |  |  | General Liability | General Liability Insurance | Boulder | [TBD] | No | Direct Debit | RIW-CFR-17-019
2025-11-18 | 17 | 15 | Equipment Insurance | From Liberty Mutual | 170.23 | 0 | 170.23 |  |  |  | General Liability | Liberty Mutual | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-17-020
2025-12-17 | 17 | 15 | Equipment Insurance | From Liberty Mutual | 170.23 | 0 | 170.23 |  |  |  | General Liability | Liberty Mutual | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-17-021
2025-12-23 | 17 | 16 | Builder's Risk Insurance | Liberty Mutual | 3454.07 | 0 | 3454.07 |  |  |  | General Liability | Liberty Mutual | Jaimin Uncle | [TBD] | NA | Credit Card | RIW-CFR-17-022
2025-11-22 | 17 | 16 | Builder's Risk Insurance | Liberty Mutual | 3454.07 | 0 | 3454.07 |  |  |  | General Liability | Liberty Mutual | Jaimin Uncle | [TBD] | NA | Credit Card | RIW-CFR-17-023
2025-10-22 | 17 | 16 | Builder's Risk Insurance | Liberty Mutual | 3454.23 | 0 | 3454.23 |  |  |  | General Liability | Liberty Mutual | Jaimin Uncle | [TBD] | NA | Credit Card | RIW-CFR-17-024
2026-01-17 | 17 | 16 | Equipment Insurance | From Liberty Mutual | 170.23 | 0 | 170.23 |  |  |  | General Liability | Liberty Mutual | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-17-025
2026-01-21 | 17 | 16 | General Liability Insurance | Newman & Trucker | 3893.43 | 0 | 3893.43 |  |  |  | General Liability | Newman & Tucker | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-17-026
2026-01-22 | 17 | 16 | General Liability Insurance | Newman & Trucker | 3893.43 | 0 | 3893.43 |  |  |  | General Liability | Newman & Tucker | Boulder AMEX | [TBD] | NA | Credit Card | RIW-CFR-17-027
2026-02-23 | 17 | 17 | General Liability Insurance | Newman & Trucker | 3640.1 | 0 | 3640.1 |  |  |  | General Liability | Newman & Tucker | Boulder | [TBD] | NA | Credit Card
18. Contractor's Fee
| 18 | 1 | Draw 1 Funds |  |  |  |  | 18750 | 1875 | 16875
| 18 | 2 | Draw 2 Funds |  |  |  |  | 37500 | 3750 | 33750
| 18 | 3 | Draw 3 Funds |  |  |  |  | 10416.6667 | 1041.6667 | 9375
| 18 | 4 | Draw 4 Funds |  |  |  |  | 33333.3333 | 3333.3333 | 30000
| 18 | 5 | Draw 5 Funds |  |  |  |  | 16666.6667 | 1666.6667 | 15000
| 18 | 6 | Draw 6 Funds - To Be Paid |  |  |  |  | 16666.6667 | 1666.6667 | 15000
| 18 | 7 | Draw 7 Funds - To Be Paid |  |  |  |  | 16666.6667 | 1666.6667 | 15000
| 18 | 8 | Draw 8 Funds - To Be Paid |  |  |  |  | 16666.6667 | 1666.6667 | 15000
| 18 | 9 | Draw 9 Funds - To Be Paid |  |  |  |  | 16666.6667 | 1666.6667 | 15000
| 18 | 11 | Draw 11 Funds - To Be Paid |  |  |  |  | 16666.6667 | 1666.6667 | 15000
| 18 | 12 | Draw 12 Funds - To Be Paid |  |  |  |  | 16666.6667 | 1666.6667 | 15000
| 18 | 13 | Draw 13 Funds - To Be Paid |  |  |  |  | 16666.6667 | 1666.6667 | 15000
| 18 | 14 | Draw 14 Funds - To Be Paid |  |  |  |  | 16666.6667 | 1666.6667 | 15000
| 18 | 15 | Draw 15 Funds - To Be Paid |  |  |  |  | 33333.3333 | 3333.3333 | 30000
| 18 | 1 | Contractor's Fee | Boulder Construction - For August 2024 | 18750 | 1875 | 16875 |  |  |  | Contractor's Fee | Boulder Construction | RI Waxahachie | NA | NA |  | RIW-CFR-18-001
| 18 | 2 | Contractor's Fee | Boulder Construction - For September 2024 | 18750 | 1875 | 16875 |  |  |  | Contractor's Fee | Boulder Construction | RI Waxahachie | NA | NA |  | RIW-CFR-18-002
| 18 | 2 | Contractor's Fee | Boulder Construction - For October 2024 | 18750 | 1875 | 16875 |  |  |  | Contractor's Fee | Boulder Construction | RI Waxahachie | NA | NA |  | RIW-CFR-18-003
| 18 | 3 | Contractor's Fee | Boulder Construction - For November 2024 (True Up Prior - 18 Mo) | 10416.6667 | 1041.6667 | 9375 |  |  |  | Contractor's Fee | Boulder Construction | RI Waxahachie | NA | NA |  | RIW-CFR-18-004
| 18 | 4 | Contractor's Fee | Boulder Construction - For December 2024 | 16666.6667 | 1666.6667 | 15000 |  |  |  | Contractor's Fee | Boulder Construction | RI Waxahachie | NA | NA |  | RIW-CFR-18-005
| 18 | 4 | Contractor's Fee | Boulder Construction - For January 2025 | 16666.6667 | 1666.6667 | 15000 |  |  |  | Contractor's Fee | Boulder Construction | RI Waxahachie | NA | NA |  | RIW-CFR-18-006
| 18 | 5 | Contractor's Fee | Boulder Construction - For February 2025 | 16666.6667 | 1666.6667 | 15000 |  |  |  | Contractor's Fee | Boulder Construction | RI Waxahachie | NA | NA |  | RIW-CFR-18-007
| 18 | 6 | Contractor's Fee | Boulder Construction - For March 2025 | 16666.6667 | 1666.6667 | 15000 |  |  |  | Contractor's Fee | Boulder Construction | RI Waxahachie | NA | NA |  | RIW-CFR-18-008
| 18 | 7 | Contractor's Fee | Boulder Construction - For April 2025 | 16666.6667 | 1666.6667 | 15000 |  |  |  | Contractor's Fee | Boulder Construction | RI Waxahachie | NA | NA |  | RIW-CFR-18-009
| 18 | 8 | Contractor's Fee | Boulder Construction - For May 2025 | 16666.6667 | 1666.6667 | 15000 |  |  |  | Contractor's Fee | Boulder Construction | RI Waxahachie | NA | NA |  | RIW-CFR-18-010
[To Be Paid] | 18 | 9 | Contractor's Fee | Boulder Construction - For June 2025 | 16666.6667 | 1666.6667 | 15000 |  |  |  | Contractor's Fee | Boulder Construction | [To Be Paid] | NA | NA | [To Be Paid] | RIW-CFR-18-011
[To Be Paid] | 18 | 11 | Contractor's Fee | Boulder Construction - For July 2025 | 16666.6667 | 1666.6667 | 15000 |  |  |  | Contractor's Fee | Boulder Construction | [To Be Paid] | NA | NA | [To Be Paid] | RIW-CFR-18-012
[To Be Paid] | 18 | 12 | Contractor's Fee | Boulder Construction - For August 2025 | 16666.6667 | 1666.6667 | 15000 |  |  |  | Contractor's Fee | Boulder Construction | [To Be Paid] | NA | NA | [To Be Paid] | RIW-CFR-18-013
[To Be Paid] | 18 | 13 | Contractor's Fee | Boulder Construction - For September 2025 | 16666.6667 | 1666.6667 | 15000 |  |  |  | Contractor's Fee | Boulder Construction | [To Be Paid] | NA | NA | [To Be Paid] | RIW-CFR-18-014
[To Be Paid] | 18 | 14 | Contractor's Fee | Boulder Construction - For October 2025 | 16666.6667 | 1666.6667 | 15000 |  |  |  | Contractor's Fee | Boulder Construction | [To Be Paid] | NA | NA | [To Be Paid] | RIW-CFR-18-015
[To Be Paid] | 18 | 15 | Contractor's Fee | Boulder Construction - For November 2025 | 16666.6667 | 1666.6667 | 15000 |  |  |  | Contractor's Fee | Boulder Construction | [To Be Paid] | NA | NA | [To Be Paid] | RIW-CFR-18-016
[To Be Paid] | 18 | 15 | Contractor's Fee | Boulder Construction - For December 2025 | 16666.6667 | 1666.6667 | 15000 |  |  |  | Contractor's Fee | Boulder Construction | [To Be Paid] | NA | NA | [To Be Paid] | RIW-CFR-18-017
Note on J1248: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pay App needs to be revised upward by $500 before Docusign. Actual Retainage Amount for Past Draw is $34,335 instead of $33,835.
Note on J1249: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pay App needs to be revised upward by $500 before Docusign. Actual Retainage Amount for Past Draw is $34,335 instead of $33,835.
Note on J1376: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pay App needs to be revised upward by $500 before Docusign. Actual Retainage Amount for Past Draw is $34,335 instead of $33,835.
Note on J1731: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pay App needs to be revised upward by $3,000 before Docusign. Actual Gross Amount for Past Draw is $80,848 instead of $70,848.
Note on J1794: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pay App needs to be revised upward by $3,000 before Docusign. Actual Gross Amount for Past Draw is $80,848 instead of $70,848.
Note on J1795: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pay App needs to be revised upward by $3,000 before Docusign. Actual Gross Amount for Past Draw is $80,848 instead of $70,848.