## G702
APPLICATION AND CERTIFICATION FOR PAYMENT |  |  |  |  | AIA DOCUMENT G702 | [5 empty] | Print
TO OWNER: |  |  | PROJECT: |  |  | APPLICATION NO: | 17 |  | Distribution to: |  | 0
Prevail Waxahachie, LLC |  |  | Residence Inn |  |  | PERIOD TO: | 2026-03-05 |  | X | OWNER
|  |  | Waxahachie, Texas |  |  | CONTRACT DATE: | 2024-06-18 |  |  | ARCHITECT
CONTRACTOR
FROM CONTRACTOR: |  |  | VIA ARCHITECT:
Divine Force JD RI Waxahachie, LLC |  |  | Maust Architectural Services
CONTRACT FOR:
CONTRACTOR'S APPLICATION FOR PAYMENT |  |  |  |  | The undersigned Contractor certifies that to the best of the Contractor's knowledge,
Application is made for payment, as shown below, in connection with the Contract. |  |  |  |  | information and belief the Work covered by this Application for Payment has been
Continuation Sheet, AIA Document G703, is attached. |  |  |  |  | completed in accordance with the Contract Documents, that all amounts have been paid by
the Contractor for Work for which previous Certificates for Payment were issued and
payments received from the Owner, and that current payment shown herein is now due.
1. ORIGINAL CONTRACT SUM |  |  |  | 11800000
2. Net change by Change Orders |  |  |  | 0 | CONTRACTOR:
3. CONTRACT SUM TO DATE (Line 1 ± 2) |  |  |  | 11800000
4. TOTAL COMPLETED & STORED TO |  |  |  | 11347285.217
DATE (Column G on G703) |  |  |  |  | By: |  |  |  | Date:
5. RETAINAGE:
a. |  | % of Completed Work $ |  |  | State of: |  |  | County of:
| (Column D + E on G703) |  |  |  | Subscribed and sworn to before me this |  |  | day of
b. |  | % of Stored Material $ |  |  | Notary Public:
| (Column F on G703) |  |  |  | My Commission expires:
Total Retainage (Lines 5a + 5b or
| Total in Column I of G703) |  | $ | 539680.007 | ARCHITECT'S CERTIFICATE FOR PAYMENT
6. TOTAL EARNED LESS RETAINAGE |  |  | $ | 10807605.21 | In accordance with the Contract Documents, based on on-site observations and the data
| (Line 4 Less Line 5 Total) |  |  |  | comprising the application, the Architect certifies to the Owner that to the best of the
7. LESS PREVIOUS CERTIFICATES FOR |  |  |  |  | Architect's knowledge, information and belief the Work has progressed as indicated,
PAYMENT (Line 6 from prior Certificate) |  |  | $ | 10083915.56 | the quality of the Work is in accordance with the Contract Documents, and the Contractor
8. CURRENT PAYMENT DUE |  |  | $ | 723689.65 | is entitled to payment of the AMOUNT CERTIFIED.
9. BALANCE TO FINISH, INCLUDING RETAINAGE $ |  |  |  | 992394.79
| (Line 3 less Line 6) |  |  |  | AMOUNT CERTIFIED . . . . . . . . . . . $
CHANGE ORDER SUMMARY |  |  | ADDITIONS | DEDUCTIONS | (Attach explanation if amount certified differs from the amount applied. Initial all figures on this
Total changes approved |  |  |  |  | Application and onthe Continuation Sheet that are changed to conform with the amount certified.)
in previous months by Owner |  |  | 0 | 0 | ARCHITECT:
Total approved this Month |  |  | 0 | 0 | By: |  |  |  | Date:
TOTALS |  |  | 0 | 0 | This Certificate is not negotiable. The AMOUNT CERTIFIED is payable only to the
Contractor named herein. Issuance, payment and acceptance of payment are without
NET CHANGES by Change Order |  |  | 0 |  | prejudice to any rights of the Owner or Contractor under this Contract.
AIA DOCUMENT G702 · APPLICATION AND CERTIFICATION FOR PAYMENT · 1992 EDITION · AIA® · © 1992 |  |  |  |  | THE AMERICAN INSTITUTE OF ARCHITECTS, 1735 NEW YORK AVE., N.W., WASHINGTON, DC 20006-5292
Users may obtain validation of this document by requesting a completed AIA Document D401 - Certification of Document's Authenticity from the Licensee.

## G703
CONTINUATION SHEET |  |  |  | AIA DOCUMENT G703 | [5 empty] | Print
AIA Document G702, APPLICATION AND CERTIFICATION FOR PAYMENT, containing | [6 empty] | APPLICATION NO: | 17 |  | 0
Contractor's signed certification is attached. | [6 empty] | APPLICATION DATE: | 2026-03-05
In tabulations below, amounts are stated to the nearest dollar. | [6 empty] | PERIOD TO: | 2026-03-05
Use Column I on Contracts where variable retainage for line items may apply. | [6 empty] | PROJECT NO:
A | B | C | D | E | F | G |  | H | I
|  |  | WORK COMPLETED |  | MATERIALS | TOTAL
ITEM | DESCRIPTION OF WORK | SCHEDULED | FROM PREVIOUS |  | PRESENTLY | COMPLETED | % | BALANCE | RETAINAGE
NO. |  | VALUE | APPLICATION | THIS PERIOD | STORED | AND STORED | (G ÷ C) | TO FINISH | (IF VARIABLE
|  |  | (D + E) |  | (NOT IN | TO DATE |  | (C - G) | RATE)
[5 empty] | D OR E) | (D+E+F)
1 | GENERAL CONDITIONS | 650000 | 603546.7983 | 26201.96 | 0 | 629748.7583 | 96.88% | 20251.2417 | 0
2 | SITEWORK | 886000 | 886000.0043 | 0 | 0 | 886000.0043 | 100% | -0.0043056 | 13347.7456
3 | CONCRETE | 1074000 | 952636.72 | 84710.29 | 0 | 1037347.01 | 96.59% | 36652.99 | 47363
4 | MASONRY | 9000 | 8964.51 | 0 | 0 | 8964.51 | 99.61% | 35.49 | 800
5 | METALS | 155000 | 92352.34 | 8284.57 | 0 | 100636.91 | 64.93% | 54363.09 | 5167.5
6 | WOOD, PLASTICS AND COMPOSITES | 1301000 | 1301000 | 0 | 0 | 1301000 | 100% | -1.8626e-09 | 37147.813
7 | THERMAL AND MOISTURE PROTECTION | 1006000 | 971543.1656 | 22887.23 | 0 | 994430.3956 | 98.85% | 11569.6044 | 81440.4932
8 | OPENINGS | 805000 | 517620.48 | 167429.52 | 0 | 685050 | 85.1% | 119950 | 1887.5
9 | FINISHES | 1040000 | 899100.26 | 67800.31 | 0 | 966900.57 | 92.97% | 73099.43 | 66615
10 | SPECIALTIES AND EQUIPMENT | 430000 | 392687.33 | 12912.44 | 0 | 405599.77 | 94.33% | 24400.23 | 0
11 | FURNISHINGS | 290000 | 182625.92 | 41539.63 | 0 | 224165.55 | 77.3% | 65834.45 | 0
12 | SWIMMING POOL | 215000 | 130472.6189 | 76391.08 | 0 | 206863.6989 | 96.22% | 8136.3011 | 14294.5989
13 | CONVEYING EQUIPMENT | 270000 | 270000 | 0 | 0 | 270000 | 100% | 0 | 25820
14 | FIRE SUPPRESSION | 197000 | 197000 | 0 | 0 | 197000 | 100% | 0 | 19700
15 | PLUMBING/HVAC | 1891000 | 1705404.8733 | 183001.41 | 0 | 1888406.2833 | 99.86% | 2593.7167 | 157843.023
16 | ELECTRICAL | 1189000 | 1107040.1133 | 62798.31 | 0 | 1169838.4233 | 98.39% | 19161.5767 | 39920
17 | GENERAL LIABILITY | 92000 | 88359.9 | 3640.1 | 0 | 92000 | 100% | 0 | 0
18 | CONTRACTOR'S FEE | 300000 | 283333.3333 | 0 | 0 | 283333.3333 | 94.44% | 16666.6667 | 28333.3333
| GRAND TOTAL | 11800000 | 10589688.367 | 757596.85 | 0 | 11347285.217 | 96.16% | 452714.783 | 539680.007
Users may obtain validation of this document by requesting of the license a completed AIA Document D401 - Certification of Document's Authenticity

## Boulder Invoice
Print
0
| Boulder Construction |  |  |  |  | Invoice / Payment Voucher
Divine Force I, LLC
| 2775 Villa Creek Dr, Suite B-240 |  |  |  | Invoice # | Date
| Farmers Branch, TX 75234 |  |  |  | 1017 | 2026-03-05
(561) 889-4988
admin@boulderconstruction.com
Bill To:
Prevail Waxahachie, LLC
205 Murphy Drive
Southlake, Texas 76092
Paid
Draw | G703 # | Description | Commentary | Amount | Retainage | Net Amount
17 | 1 | Jobsite Office - Recurring Rental | From Willscott | 160.4 | 0 | 160.4 | 12205
17 | 1 | Misc. Jobsite Material Expenses | From Home Depot - Mount Starter Kit with Ball and Lock | 72.47 | 0 | 72.47 | 12212
17 | 1 | Misc. Jobsite Material Expenses | From Home Depot - Bottled Water And Utility Knife, Blades | 60.9 | 0 | 60.9 | 12221
17 | 1 | Final Cleaning Supplies | From Home Depot - Jobsite Cleaning SuppliesCleaning Wipes and Cleaners | 104.83 | 0 | 104.83 | 12248
17 | 1 | Temporary Toilets - Recurring Payment | A-1 Little John | 954.77 | 0 | 954.77 | 12258
17 | 1 | Jobsite Dumpster | From Advantage Waste Disposal | 1449.48 | 0 | 1449.48 | 12260
17 | 1 | Jobsite Office - Recurring Rental | From Willscott | 677.87 | 0 | 677.87 | 12269
17 | 1 | Jobsite Office - Recurring Rental | From Willscott | 136.31 | 0 | 136.31 | 12270
17 | 1 | Jobsite Office - Recurring Rental | From Willscott | 420.28 | 0 | 420.28 | 12271
17 | 1 | Jobsite Dumpster | From Waste Connections | 2105.22 | 0 | 2105.22 | 12274
17 | 1 | Jobsite Dumpster | From Waste Connections | 1613.43 | 0 | 1613.43 | 12275
17 | 1 | Jobsite Office - Recurring Rental | From Willscott | 24.09 | 0 | 24.09 | 12286
17 | 1 | Jobsite Office - Recurring Rental | From Willscott | 214.06 | 0 | 214.06 | 12307
17 | 1 | Misc. Jobsite Material Expenses | From Home Depot | 87.35 | 0 | 87.35 | 12356
17 | 1 | Misc. Jobsite Material Expenses | From Home Depot | 1 | 0 | 1 | 12358
17 | 1 | Jobsite Dumpster | From Waste Connections | 1613.43 | 0 | 1613.43 | 12461
17 | 1 | Jobsite Dumpster | From Advantage Waste Disposal | 1449.48 | 0 | 1449.48 | 12492
17 | 1 | Notary Fees | For Draw | 13.46 | 0 | 13.46 | [TBD]
17 | 1 | Jobsite Dumpster | From Waste Connections | -491.79 | 0 | -491.79 | [TBD]
17 | 1 | Jobsite Material Refund | From Home Depot - Refund | -11.08 | 0 | -11.08 | [TBD]
17 | 1 | Jobsite Material Refund | From Home Depot - Refund | -57.68 | 0 | -57.68 | [TBD]
17 | 1 | Jobsite Material Refund | From Home Depot - Refund | -855.97 | 0 | -855.97 | [TBD]
17 | 1 | Notary Fees | For Draw | 25 | 0 | 25 | [TBD]
17 | 1 | Notary Fees | For Draw | 25 | 0 | 25 | [TBD]
17 | 1 | Travel for Labor During Ice Storm | From Lyft | 66.95 | 0 | 66.95 | [TBD]
17 | 1 | Travel for Labor During Ice Storm | From Lyft | 44.94 | 0 | 44.94 | [TBD]
17 | 1 | Travel for Labor During Ice Storm | From Lyft | 46.96 | 0 | 46.96 | [TBD]
17 | 1 | Travel for Labor During Ice Storm | From Lyft | 63.93 | 0 | 63.93 | [TBD]
17 | 1 | Travel for Labor During Ice Storm | From Lyft | 49.93 | 0 | 49.93 | [TBD]
17 | 1 | Travel for Labor During Ice Storm | From Lyft | 47.98 | 0 | 47.98 | [TBD]
17 | 1 | Booking for Security/Labor During Ice Storm | From Expedia | 571.56 | 0 | 571.56 | [TBD]
17 | 1 | Booking for Security/Labor During Ice Storm | From Expedia | 179.67 | 0 | 179.67 | [TBD]
17 | 1 | Booking for Security/Labor During Ice Storm | From Expedia | 213.57 | 0 | 213.57 | [TBD]
17 | 1 | Booking for Security/Labor During Ice Storm | From Expedia | 161.76 | 0 | 161.76 | [TBD]
17 | 1 | Meals | For Jobsite Travel | 491.43 | 0 | 491.43 | [TBD]
17 | 1 | Fuel | For Jobsite | 711.24 | 0 | 711.24 | [TBD]
17 | 1 | Notary Fees | For Draw | 10 | 0 | 10 | [TBD]
17 | 1 | David Salinas - Jobsite Labor | From Waltons Muffler | 1844.35 | 0 | 1844.35 | [TBD]
17 | 1 | Misc. Wire and ACH Fees for RIW | From Austin Bank for Wires and ACH | 130.3 | 0 | 130.3 | [TBD]
17 | 1 | Misc. Jobsite Expenses (Softwares, etc.) - True Up | Takeoffs, Scheduling / Forecasting, Punch Lists, etc. | 1202.23 | 0 | 1202.23 | [TBD]
17 | 1 | Cellular Data & WiFi for Jobsite Office | From Google One | 269.04 | 0 | 269.04 | [TBD]
17 | 1 | Cellular Data & WiFi for Jobsite Office - True Up | From AT&T | 303.81 | 0 | 303.81 | [TBD]
17 | 3 | Concrete Anchors | From Home Depot - Concrete Anchors, Drill Bit and Screws | 74.77 | 0 | 74.77 | 12216
17 | 3 | Concrete Mix | From Home Depot - Concrete Mix And Snacks | 50.03 | 0 | 50.03 | 12218
17 | 3 | Concrete Anchors | From Home Depot - LED Bulb, Cable, Zinc Washer and Concrete Anchors | 373.27 | 0 | 373.27 | 12247
17 | 3 | Concrete Mix | From Home Depot - Concrete Mix | 213.69 | 0 | 213.69 | 12250
17 | 3 | Concrete Block | From Home Depot - Concrete Block | 445.99 | 0 | 445.99 | 12287
17 | 3 | Concrete Material | From Home Depot - Cement, Cutter and Glove | 102.54 | 0 | 102.54 | 12359
17 | 5 | Structural Steel Labor (CO) | From Go Construction - Pay App 09 (Split) | 1609.57 | 380 | 1229.57 | 12344
17 | 5 | Structural Steel Labor (CO) | From Go Construction - Pay App 10 & 11 | 6675 | 667.5 | 6007.5 | 12345
17 | 7 | Stone Material | From Metro Brick & Stone | 909.82 | 0 | 909.82 | 12312
17 | 7 | Window Cleaning & Back Fixes | From VG Stucco | 4000 | 0 | 4000 | 12469
17 | 7 | Stone Material | From Metro Brick & Stone | 722.5 | 0 | 722.5 | [TBD]
17 | 7 | Stone Material | From Metro Brick & Stone | 454.91 | 0 | 454.91 | [TBD]
17 | 8 | Door Material | From Home Depot - Door Lock Installation Saw Set | 57.26 | 0 | 57.26 | 12455
17 | 8 | Electronic Locksets | From Onity | 28640.68 | 0 | 28640.68 | 12468
17 | 8 | Door Material | From Home Depot - Aluminium Channel | 59.06 | 0 | 59.06 | 12500
17 | 8 | Windows Installation Labor | From GW Glass Construction | 5450 | 0 | 5450 | [TBD]
17 | 8 | Closers | From Amazon | 3195.74 | 0 | 3195.74 | [TBD]
17 | 8 | Locks | From Amazon | 1106.67 | 0 | 1106.67 | [TBD]
17 | 8 | Window Stops | From Amazon | 582.2 | 0 | 582.2 | [TBD]
17 | 8 | Passage Locks | From Amazon | 416.5 | 0 | 416.5 | [TBD]
17 | 8 | Door Hardware | From Amazon | 1375.68 | 0 | 1375.68 | [TBD]
17 | 8 | Door Hinge Pins | From Amazon | 136.35 | 0 | 136.35 | [TBD]
17 | 8 | Passage Locks | From Amazon | 1332.8 | 0 | 1332.8 | [TBD]
17 | 8 | Hinges | From Amazon | 272.76 | 0 | 272.76 | [TBD]
17 | 8 | Hinges | From Amazon | 248.96 | 0 | 248.96 | [TBD]
17 | 8 | Push / Pull | From Amazon | 84.36 | 0 | 84.36 | [TBD]
17 | 8 | Push / Pull | From Amazon | 28.12 | 0 | 28.12 | [TBD]
17 | 8 | Hinges | From Amazon | 470.67 | 0 | 470.67 | [TBD]
17 | 8 | Window Stops | From Amazon | 291.1 | 0 | 291.1 | [TBD]
17 | 8 | Dummy Locks | From Amazon | 108.14 | 0 | 108.14 | [TBD]
17 | 8 | Passage Locks | From Amazon | 91.91 | 0 | 91.91 | [TBD]
17 | 8 | Panic Bars | From Amazon | 1704.42 | 0 | 1704.42 | [TBD]
17 | 8 | Automatic Door Bottom | From Amazon | 151.52 | 0 | 151.52 | [TBD]
17 | 8 | Doors Hardware | From DK Hardware | 388.5 | 0 | 388.5 | [TBD]
17 | 8 | Labor And Diesel | From J&S7 Consulting | 2589 | 0 | 2589 | 12314
17 | 8 | Framing Material | From Lowes - Rough Cedar Lumber (2x4x12) | 3089.8 | 0 | 3089.8 | 12341
17 | 8 | Framing Material | From Lowes - Framing Lumber And Fasteners | 5931.69 | 0 | 5931.69 | 12342
17 | 8 | Parking Lot Striping And ADA Markings | From H&W Extreme Cleaning Solutions - Parking Lot Striping And ADA Markings | 8451.79 | 0 | 8451.79 | 12343
17 | 8 | Landscaping | From 4 Nature Landscape | 13500 | 0 | 13500 | 12309
17 | 8 | Elevator Engineering, Materials And Installation Labor | From KONE - Elevator Engineering, Materials And Installation Labor | 18875 | 1887.5 | 16987.5 | 12313
17 | 8 | Jobsite Labor | From J&S7 Consulting | 7735 | 0 | 7735 | 12314
17 | 8 | Final Cleaning | From Americo Concrete | 9620 | 0 | 9620 | 12476
17 | 8 | Landscaping | From 4 Nature Landscape | 10237.31 | 0 | 10237.31 | [TBD]
17 | 8 | Final Cleaning | From Americo Concrete | 9435 | 0 | 9435 | [TBD]
17 | 8 | Equipment Costs | From EquipmentShare | 16271.53 | 0 | 16271.53 | [TBD]
17 | 9 | Drywall Material | From Home Depot - Gypsum Board, Joint Compound and Drywall Screws and Tape | 109.85 | 0 | 109.85 | 12207
17 | 9 | Drywall Material | From Home Depot - Joint Compound For Drywall Finishing | 55.53 | 0 | 55.53 | 12210
17 | 9 | Drywall Material | From Home Depot - Gypsum Board, Drywall Screws and Zip Bit | 79.74 | 0 | 79.74 | 12211
17 | 9 | Drywall Material | From Home Depot - Drywall Sheets (1/2 In Ultralight) | 96.32 | 0 | 96.32 | 12219
17 | 9 | Flooring Material | From Home Depot - Tile Mortar and Sponge | 297.62 | 0 | 297.62 | 12220
17 | 9 | Flooring Material | From Home Depot - Whitewood Stud, Saw, Drill Bit | 126.43 | 0 | 126.43 | 12222
17 | 9 | Painting Material | From Home Depot - Painting ToolsPaint Roller Frame | 10.95 | 0 | 10.95 | 12224
17 | 9 | Flooring Material | From Home Depot - Temporary Heat Supplies (Kerosene And Heaters) | 551.88 | 0 | 551.88 | 12225
17 | 9 | Painting Material Refund | From Home Depot - Refund | -26.63 | 0 | -26.63 | 12226
17 | 9 | Painting Material | From Home Depot - Painting Supplies (Roller Covers, Trays) | 54.62 | 0 | 54.62 | 12226
17 | 9 | Drywall Material | From Home Depot - Drywall Screws box And Carpenter Pencils | 20.58 | 0 | 20.58 | 12228
17 | 9 | Painting Material | From Home Depot - Wood Moving Dolly, Water Primer and Sealerand Roller | 413.53 | 0 | 413.53 | 12231
17 | 9 | Painting Material Refund | From Home Depot - Refund | -47.62 | 0 | -47.62 | 12231
17 | 9 | Flooring Material | From Home Depot - Machine Washable Mop, Contractor Bags, Joint Compound | 257.96 | 0 | 257.96 | 12236
17 | 9 | Drywall Material | From Home Depot - Joint Coumpound, Drywall Tape and Sanding Sponge | 47.08 | 0 | 47.08 | 12238
17 | 9 | Flooring Material | From Home Depot - Drill Bits, Anchors and Snacks | 97.87 | 0 | 97.87 | 12241
17 | 9 | Flooring Material | From Home Depot - Joint Compound | 30.96 | 0 | 30.96 | 12257
17 | 9 | Flooring Material | From Home Depot - Misc. And SuppliesSelf Adhesive Film | 140.68 | 0 | 140.68 | 12259
17 | 9 | Painting Material | From Home Depot - Jobsite SuppliesSpray Paint | 7.03 | 0 | 7.03 | 12265
17 | 9 | Drywall Material | From Home Depot - Drywall Corner Bead Materials | 182.51 | 0 | 182.51 | 12266
17 | 9 | Flooring Material | From Home Depot - Carpet Adhesive And Hinge and Latch Set | 285.27 | 0 | 285.27 | 12276
17 | 9 | Flooring Material | From Home Depot - Carpet Flooring Adhesive | 285.08 | 0 | 285.08 | 12277
17 | 9 | Painting Material | From Home Depot - Painting SuppliesFlat Paint Brush and Plastic Sheeting | 50.77 | 0 | 50.77 | 12278
17 | 9 | Flooring Material | From Home Depot - Polyblend Grout and Tile Trim | 132.69 | 0 | 132.69 | 12289
17 | 9 | Painting Material | From Home Depot - Spray Foam Sealant | 35.85 | 0 | 35.85 | 12291
17 | 9 | Drywall Material | From Home Depot - Wall Shelf Bracket and Drywall Anchor | 250.69 | 0 | 250.69 | 12292
17 | 9 | Flooring Material | From Home Depot - Tile Grout And Grout Float | 246.73 | 0 | 246.73 | 12294
17 | 9 | Painting Material | From Home Depot - Primer Spray And Metal Cut | 71.94 | 0 | 71.94 | 12295
17 | 9 | Painting Material | From Home Depot - Cedar Stain and Sealer, Framing Nails and Roller | 81.49 | 0 | 81.49 | 12296
17 | 9 | Painting Material | From Home Depot - Paint Brush, Gloves, Blades and Cleaners | 75.47 | 0 | 75.47 | 12297
17 | 9 | Flooring Material | From Home Depot - Motar Mix, Tile Spacer and Vinyl sealer | 118.04 | 0 | 118.04 | 12298
17 | 9 | Flooring Material | From Home Depot - Self Adhesive and Microfibre Cloth | 209.18 | 0 | 209.18 | 12300
17 | 9 | Flooring Material | From Home Depot - Wall Base Floor Adhesive | 103.83 | 0 | 103.83 | 12301
17 | 9 | Flooring Material | From Home Depot - Vinly Adhesive, Vinly Roller, Tape Roller and Flooring Trowel | 394.94 | 0 | 394.94 | 12302
17 | 9 | Flooring Material | From Home Depot - Tile Setting Materials Thinset Mortar | 171.08 | 0 | 171.08 | 12303
17 | 9 | Painting Material | From Home Depot - PaintingPaint, Brush Sprays | 316.92 | 0 | 316.92 | 12306
17 | 9 | Painting Materials | From Home Depot - Soap, Painter's Tape, Cleaner and Polish | 215.41 | 0 | 215.41 | 12315
17 | 9 | Drywall Material | From Home Depot - Roller Catch, Tooth Rachet, Drywall Screws | 208.26 | 0 | 208.26 | 12321
17 | 9 | Drywall Material | From Home Depot - Extension Cord, Drywall Screws. | 231.82 | 0 | 231.82 | 12322
17 | 9 | Painting Material | From Home Depot - Roll and Paint Bucket | 17.26 | 0 | 17.26 | 12324
17 | 9 | Drywall Material | From Home Depot - Drywall Anchors, Magnetic Holder, Wood Screw | 30.44 | 0 | 30.44 | 12325
17 | 9 | Flooring Material | From Home Depot - Grout | 57.09 | 0 | 57.09 | 12328
17 | 9 | Flooring Material | From Home Depot - Rubber Wall Cove Base | 134.34 | 0 | 134.34 | 12329
17 | 9 | Flooring Material | From Lowes - Flooring Transitions And Vinyl Divider | 399.33 | 0 | 399.33 | 12335
17 | 9 | Flooring Material | From Lowes - Tile Setting Materials (Grout | 267.19 | 0 | 267.19 | 12336
17 | 9 | Flooring Material | From Lowes - Transition Reducers And Flooring Trim Materials | 149.26 | 0 | 149.26 | 12339
17 | 9 | Painting Material | From Home Depot - Painting SuppliesPaint Pail and Gloves and Brushes | 94.37 | 0 | 94.37 | 12346
17 | 9 | Drywall Material | From Lowe's - Drywall | 527.09 | 0 | 527.09 | 12401
17 | 9 | Flooring Material | From Lowes - Tile Setting Materials | 440.76 | 0 | 440.76 | 12402
17 | 9 | Painting Material | From Home Depot - Metal Interior/Exterior Paint | 162.72 | 0 | 162.72 | 12457
17 | 9 | Painting Material | From Lowes - Ultracolor Plus, and Sctch Blue Painter | 150.9 | 0 | 150.9 | 12460
17 | 9 | Flooring Material | From Home Depot - Joint Compound & Sheetrock | 65.76 | 0 | 65.76 | 12465
17 | 9 | Public Area Tile Carpet | From J&JR Construction | 19111 | 0 | 19111 | 12471
17 | 9 | Flooring Material | From Lowes - Type 1Mastic Gal And Ultracolor Plus | 141.74 | 0 | 141.74 | [TBD]
17 | 9 | Flooring Material | From Lowes - Ultracolor Plus, and Ultra Flex White | 687.08 | 0 | 687.08 | [TBD]
17 | 9 | Flooring Material | From Floor & Décor | 200.04 | 0 | 200.04 | [TBD]
17 | 9 | Painting Material | From Sherwin Williams | 822.67 | 0 | 822.67 | [TBD]
17 | 9 | Rubber Edge Trim | From Amazon | 29.18 | 0 | 29.18 | [TBD]
17 | 9 | Rubber Trims | From Amazon | 38.72 | 0 | 38.72 | [TBD]
17 | 9 | Stair Edging Strip | From Amazon | 25.97 | 0 | 25.97 | [TBD]
17 | 9 | Flooring Material | From Floor & Décor | 1920.44 | 0 | 1920.44 | [TBD]
17 | 9 | Flooring Material | From Floor & Décor | 2940.94 | 0 | 2940.94 | [TBD]
17 | 9 | Flooring Material | From Floor & Décor | 554.74 | 0 | 554.74 | [TBD]
17 | 9 | Flooring Material | From Cazares Carpet | 310.02 | 0 | 310.02 | [TBD]
17 | 9 | Flooring Material | From Cazares Carpet | 116.26 | 0 | 116.26 | [TBD]
17 | 9 | Flooring Material | From Floor & Décor | 2446.26 | 0 | 2446.26 | [TBD]
17 | 9 | Flooring Material | From Cazares Carpet | 1317.4 | 0 | 1317.4 | [TBD]
17 | 9 | Carpet | From C&C Wholesale | 494.49 | 0 | 494.49 | [TBD]
17 | 9 | ACT | From Gilbert | 154.5 | 0 | 154.5 | [TBD]
17 | 10 | Bathroom Partitions | From Normex Construction | 8505 | 0 | 8505 | 12234
17 | 10 | Misc. Shower/Surround Install Material | From Lowes - Low Profile Sidewall Vent Materials | 345.97 | 0 | 345.97 | 12340
17 | 10 | Misc. Shower/Surround Install Material | From Home Depot - Lavatory Protector | 236.2 | 0 | 236.2 | 12453
17 | 10 | Toilet Material | From Home Depot - Grab Bar | 152.85 | 0 | 152.85 | 12458
17 | 10 | Misc. Shower/Surround Install Material | From Home Depot - Kitchen & Bath Sealant, Empoxy & Resins | 80.82 | 0 | 80.82 | 12485
17 | 10 | Misc. Shower/Surround Install Material | From Home Depot - Silicone Caulk & Thinset Mortar | 139 | 0 | 139 | 12486
17 | 10 | Misc. Shower/Surround Install Material | From Home Depot - Silicone Caulk & Gun | 129.75 | 0 | 129.75 | 12488
17 | 10 | Misc. Shower/Surround Install Material | From Home Depot - Flush Right Hand Wing & Drywall Material | 263.91 | 0 | 263.91 | 12501
17 | 10 | Toilet Material | From Home Depot - Grab Bar | 297.23 | 0 | 297.23 | 12512
17 | 10 | ADA Shower Seat | From Amazon | 184.01 | 0 | 184.01 | [TBD]
17 | 10 | Soap Trap Showers | From Amazon | 51.94 | 0 | 51.94 | [TBD]
17 | 10 | Soap Dish Showers | From Amazon | 75.76 | 0 | 75.76 | [TBD]
17 | 11 | Granite Installation | From Home Depot - Sealant, Adhesive And Silicone Caulk | 218.62 | 0 | 218.62 | 12229
17 | 11 | Granite Installation | From Home Depot - Silicone Caulk, Caulk Guns and Sealant Cleaner | 580.22 | 0 | 580.22 | 12262
17 | 11 | Granite Installation | From Home Depot - Silicone Caulk and Sealant | 136.78 | 0 | 136.78 | 12304
17 | 11 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 1401.25 | 0 | 1401.25 | 12332
17 | 11 | Granite Installation | From Home Depot - Granite, Slate, Ceramic & Glass Tiles Drill Bit | 78.85 | 0 | 78.85 | 12355
17 | 11 | Granite Installation | From Home Depot - Caulk, Cleaner, And Contractor Trash Bags | 218.11 | 0 | 218.11 | 12357
17 | 11 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 1686.25 | 0 | 1686.25 | 12496
17 | 11 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 373.75 | 0 | 373.75 | 12497
17 | 11 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 1812.5 | 0 | 1812.5 | 12498
17 | 11 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 1812.5 | 0 | 1812.5 | [TBD]
17 | 11 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 371.25 | 0 | 371.25 | [TBD]
17 | 11 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 2600 | 0 | 2600 | [TBD]
17 | 11 | Closet Shelves | From Amazon | 503.35 | 0 | 503.35 | [TBD]
17 | 11 | Closet Shelves | From Amazon | 573.2 | 0 | 573.2 | [TBD]
17 | 11 | Closet Shelves | From Amazon | 515.88 | 0 | 515.88 | [TBD]
17 | 11 | Closet Shelves | From Amazon | 630.52 | 0 | 630.52 | [TBD]
17 | 11 | Closet Magnet | From Amazon | 16.23 | 0 | 16.23 | [TBD]
17 | 11 | Closet Magnet | From Amazon | 10.37 | 0 | 10.37 | [TBD]
17 | 12 | Framing Material | From Home Depot - Lumber, Screws, Sheathing, Panel | 1394.07 | 0 | 1394.07 | 12209
17 | 12 | Framing Material | From Home Depot - Tape Measure, Aviation Snips and Gypsum Board | 165.16 | 0 | 165.16 | 12213
17 | 12 | Framing Material | From Home Depot - Sanded Pine Plywood Sheets | 653.64 | 0 | 653.64 | 12215
17 | 12 | Framing Material | From Home Depot - Parawedge Wedge Anchors Pcket | 31.44 | 0 | 31.44 | 12249
17 | 12 | Framing Material | From Home Depot - Pine Plywood, Lumber and Screws | 302.03 | 0 | 302.03 | 12263
17 | 12 | Framing Material | From Home Depot - Flathead Screws and Insert Bit | 35.76 | 0 | 35.76 | 12264
17 | 12 | Framing Material | From Home Depot - 5/8 In Firecode Gypsum Board Sheets | 25.59 | 0 | 25.59 | 12268
17 | 12 | CMU Block Material | From Home Depot - CMU Blocks-Concrete Block and Brick Tie | 663.73 | 0 | 663.73 | 12288
17 | 12 | CMU Block Material | From Home Depot - Refund | -602.96 | 0 | -602.96 | 12288
17 | 12 | Framing Material | From Home Depot - Lumber, machine wash Mop and Cleaning Products | 621.97 | 0 | 621.97 | 12293
17 | 12 | Framing Material | From Home Depot - Pine Plywood and Lumber | 526.12 | 0 | 526.12 | 12299
17 | 12 | Framing Material | From Home Depot - Dimensional Lumber (2x6x10) | 188.23 | 0 | 188.23 | 12305
17 | 12 | Framing Material | From Lowes - Framing Lumber And Hardware Kit | 241.9 | 0 | 241.9 | 12338
17 | 12 | Framing Material | From Home Depot - Screws | 36.53 | 0 | 36.53 | 12347
17 | 12 | Trench Safety Box Rental For Utility Work | From National Trench Safety - Trench Safety Box Rental For Utility Work | 1159.58 | 0 | 1159.58 | 12403
17 | 12 | Framing Material | From Home Depot - Scissors & Elastic Straps | 73.46 | 0 | 73.46 | 12464
17 | 12 | Framing Material | From Home Depot - Washer, Bolt & Drill Bits | 68.11 | 0 | 68.11 | 12466
17 | 12 | Swimming Pool Labor and Material | From San Diego Pools and Shotcrete | 39440 | 3944 | 35496 | 12477
17 | 12 | Framing Labor - Misc. Punch List | From Martin Aguilar | 2000 | 0 | 2000 | 12481
17 | 12 | Framing Material | From Home Depot - Zinc Flat Washer, Nut & Alloy Bit | 156.17 | 0 | 156.17 | 12499
17 | 12 | Jobsite Material Expense | From Home Depot | 552.95 | 0 | 552.95 | 12510
17 | 12 | Framing Material | From Martin Aguilar | 1900 | 0 | 1900 | [TBD]
17 | 12 | Framing Material | From Harbor Freight | 376.38 | 0 | 376.38 | [TBD]
17 | 12 | Equipment Insurance | From Liberty Mutual | 170.23 | 0 | 170.23 | [TBD]
17 | 12 | Jobsite Expense | From Home Depot | 290.39 | 0 | 290.39 | [TBD]
17 | 12 | Jobsite Expense | From Home Depot | 187.58 | 0 | 187.58 | [TBD]
17 | 12 | Jobsite Expense | From Home Depot | 144.71 | 0 | 144.71 | [TBD]
17 | 12 | Framing Material | From Lowes - Framing Lumber And Fasteners Refund | -3332.89 | 0 | -3332.89 | [TBD]
17 | 12 | Jobsite Expense | From Home Depot | 421.2 | 0 | 421.2 | [TBD]
17 | 12 | Jobsite Expense | From Home Depot | 16.79 | 0 | 16.79 | [TBD]
17 | 12 | Pool Sconces | From Amazon | 235.76 | 0 | 235.76 | [TBD]
17 | 12 | Sconces | From Amazon | 71.94 | 0 | 71.94 | [TBD]
17 | 12 | Linen Chute | From Amazon | 67.64 | 0 | 67.64 | [TBD]
17 | 12 | Linen Chute | From Amazon | 18.39 | 0 | 18.39 | [TBD]
17 | 12 | Sconces | From Amazon | 497 | 0 | 497 | [TBD]
17 | 12 | Equipment Rental/Repair |  | 1488.12 | 0 | 1488.12 | [TBD]
17 | 12 | Jobsite Office Equipment | From Best Buy | 1110.82 | 0 | 1110.82 | [TBD]
17 | 12 | Jobsite Office Equipment | From Best Buy | 714.43 | 0 | 714.43 | [TBD]
17 | 12 | Liquid Rubber Elevator | From Amazon | 865.75 | 0 | 865.75 | [TBD]
17 | 12 | Glasses |  | 257.21 | 0 | 257.21 | [TBD]
17 | 16 | Electrical Material | From Home Depot - Electrical MaterialsTape, Pipe Clamp, Gauge and Gloves | 268.23 | 0 | 268.23 | 12206
17 | 16 | Electrical Material | From Home Depot - Extension Cords And Cable Connectors | 127.03 | 0 | 127.03 | 12208
17 | 16 | Electrical Material | From Home Depot - Electrical MaterialsConduit Fittings and Clamp Connectors | 21.4 | 0 | 21.4 | 12217
17 | 16 | Electrical Material | From Home Depot - AC Disconnect Switches And Electrical Rough Materials | 277.02 | 0 | 277.02 | 12239
17 | 16 | Electrical Material | From Home Depot - Duplex Outlet, Anchors, Screws | 125.05 | 0 | 125.05 | 12240
17 | 16 | Electrical Material | From Home Depot - LED Light Bulbs Selected Color Temperature | 129.58 | 0 | 129.58 | 12245
17 | 16 | Electrical Material | From Home Depot - Electrical DevicesSingle and Duplex Outlet and Wall Plate | 136.84 | 0 | 136.84 | 12251
17 | 16 | Electrical Material | From Home Depot - LED Light Bulb | 581.04 | 0 | 581.04 | 12254
17 | 16 | Electrical Material | From Home Depot - Electrical MaterialsRange Cord, Outlet, Blade Kit and Tape | 921.87 | 0 | 921.87 | 12267
17 | 16 | Electrical Material | From Home Depot - Wires, Conduits, Duplex Outlet, Rod | 1472.15 | 0 | 1472.15 | 12323
17 | 16 | Electrical Material | From Home Depot - PVC Conduit, Support Rod, Connectors | 747.74 | 0 | 747.74 | 12326
17 | 16 | Electrical Material | From Home Depot - Circular Saw Blade, Plunger and Brush | 49.13 | 0 | 49.13 | 12327
17 | 16 | Electrical Material | From Home Depot - Duplex Outlet, GDCI Outlet. | 466.91 | 0 | 466.91 | 12330
17 | 16 | Electrical Material | From Home Depot - Wire Dryer Cord, Ciruit Breaker, Outlet Cover and Clamp Connector | 95.94 | 0 | 95.94 | 12331
17 | 16 | Electrical Material | From Home Depot - Light Bulb, Switches & Outlet | 352.99 | 0 | 352.99 | 12454
17 | 16 | Electrical Material | From Home Depot - Thermostat Wire & Switches | 83.29 | 0 | 83.29 | 12489
17 | 16 | Pendant Lantern | From Amazon | 265.26 | 0 | 265.26 | [TBD]
17 | 16 | Pendant Lantern | From Amazon | 176.84 | 0 | 176.84 | [TBD]
17 | 17 | General Liability Insurance | Newman & Trucker | 3640.1 | 0 | 3640.1 | [TBD]
| Total |  |  | 310739.29 | 6879 | 303860.29
To Be Paid
Draw | G703 # | Description | Commentary | Amount | Retainage | Net Amount
17 | 1 | Job Supervisor | For February 2026 | 10000 | 0 | 10000 | NA
17 | 3 | Concrete Labor | From MD Bowles Construction - Pay App 11 | 83450 | 8345 | 75105 | [TBD]
17 | 7 | EFIS Material | From VG Stucco - Pay App 11 | 16800 | 1680 | 15120 | [TBD]
17 | 8 | Guest Room Doors | From TKG Construction - Pay App 11 | 1500 | 0 | 1500 | [TBD]
17 | 8 | Public Area Doors & Other Doors & Caulking | From TKG Construction - Pay App 11 | 14000 | 0 | 14000 | [TBD]
17 | 9 | Flooring Labor | From TKG Construction - Pay App 11 | 28000 | 0 | 28000 | [TBD]
17 | 10 | Shower Glass Doors | From TKG Construction - Pay App 11 | 2450 | 0 | 2450 | [TBD]
17 | 11 | Guestroom Granite Install | From TKG Construction - Pay App 11 | 1000 | 0 | 1000 | [TBD]
17 | 11 | FF&E/Delivery/Others | From TKG Construction - Pay App 11 | 27000 | 0 | 27000 | [TBD]
17 | 12 | Marriott Requirement - 360 Capture Subscription | From Openspace | 6156.15 | 0 | 6156.15 | 11288
17 | 12 | Extra Labor Per Discussion - Sai & Aniket | From Boulder Construction | 6000 | 0 | 6000 | NA
17 | 12 | Extra Labor Per Discussion - Sai & Aniket | From Boulder Construction | 6000 | 0 | 6000 | NA
17 | 12 | Exterior Fence | From TKG Construction - Pay App 11 | 5000 | 0 | 5000 | [TBD]
17 | 15 | Plumbing Material & Labor | From MA William Plumbing - Pay App 06 | 89232 | 8923.2 | 80308.8 | [TBD]
17 | 15 | Electrical Material | From Elliott Electrical | 69469.41 | 0 | 69469.41 | [TBD]
17 | 15 | Electrical Labor | From GMC Electrical - Pay App 10 (Split) | 24300 | 2430 | 21870 | [TBD]
17 | 16 | Fire Sprinkler Trim | From Safelife Fire protection - Pay App 05 | 46500 | 4650 | 41850 | [TBD]
17 | 16 | Electrical Labor | From GMC Electrical - Pay App 10 (Split) | 10000 | 1000 | 9000 | [TBD]
| Total |  |  | 446857.56 | 27028.2 | 419829.36
| Aggregate Total |  |  | 757596.85 | 33907.2 | 723689.65
Prior Transactions / Draws
Draw | G703 # | Description | Commentary | Amount | Retainage | Net Amount
1 | 2 | Water Meter Payment | Reimbursement for Payment to the City of Waxahachie | 2233 | 0 | 2233
1 | 1 | Blueprint Printing | Reimbursement for Payment to Stewart Engineering | 278.74 | 0 | 278.74
1 | 1 | Blueprint Printing | Reimbursement for Payment to Stewart Engineering | 321.5 | 0 | 321.5
1 | 1 | Temporary Toilets | Reimbursement for Payment to A-1 Little John | 211.63 | 0 | 211.63
1 | 1 | Temporary Fencing (Chain Link) | Reimbursement for Payment to Viking Fence Co | 5179.6542 | 0 | 5179.6542
1 | 2 | Temporary Fencing (Dirt Screening for Sitework) | Reimbursement for Payment to Viking Fence Co | 4830.6658 | 0 | 4830.6658
1 | 2 | Earthwork - SW3P / Site Clearing | Reimbursement for Payment to Raul Sandoval Construction | 10000 | 1000 | 9000
1 | 2 | Earthwork - Mobilization | Reimbursement for Payment to Raul Sandoval Construction | 12000 | 1200 | 10800
1 | 2 | Utility - Sanitary Sewer & Water Material | Reimbursement for Payment to Ferguson Waterworks | 81563.63 | 0 | 81563.63
1 | 2 | Earthwork - SW3P | Reimbursement for Payment to Cardinal Strategies | 1100 | 0 | 1100
1 | 1 | Mobilization | Boulder Construction | 22000 | 0 | 22000
1 | 2 | Sitework - Surveyor | AIM Construction Services | 1140 | 0 | 1140
1 | 2 | Earthwork - Import Dirt Material | Superman Trucking and Delivery Inc | 3500 | 0 | 3500
1 | 2 | Earthwork - Import Dirt Material | Superman Trucking and Delivery Inc | 20995 | 0 | 20995
1 | 1 | Project Manager | For August 2024 | 4375 | 0 | 4375
1 | 1 | Job Accounting / Administration | For August 2024 | 4062.5 | 0 | 4062.5
1 | 18 | Contractor's Fee | For August 2024 | 18750 | 1875 | 16875
1 | 17 | Insurance | General liability Insurance | 15466.08 | 0 | 15466.08
1 | 17 | Insurance | Equipment Insurance | 4087 | 0 | 4087
1 | 2 | Order Storm Sewer Material | Ferguson Waterworks | 35700 | 0 | 35700
1 | 5 | Order Structural Steel Material | Norton Metals | 20032.34 | 0 | 20032.34
1 | 5 | Structural Steel Fabrication | Go Construction | 12000 | 1200 | 10800
1 | 16 | Order Switch Gear | Greens Distributions - Initial Deposit | 23382 | 0 | 23382
1 | 8 | Order Windows | Top Bright Windows and Door - Initial Deposit | 50500 | 0 | 50500
1 | 13 | Order Elevator | Kone - Initial Deposit | 77100 | 0 | 77100
1 | 2 | Earthwork - Import Dirt & Gravel Material | Trucking and Material | 35000 | 0 | 35000
1 | 2 | Sitework - Earthwork | Raul Sandoval Construction - August 2024 Forecasted Payments | 58000 | 5800 | 52200
1 | 2 | Sitework - Utilities | Raul Sandoval Construction - August 2024 Forecasted Payments | 50000 | 5000 | 45000
1 | 2 | Sitework - Equipment | Equipment Share - August 2024 Forecasted Cost | 25000 | 0 | 25000
2 | 18 | Contractor's Fee | Reimbursement for September 2024 | 18750 | 1875 | 16875
2 | 1 | Project Manager | Reimbursement for September 2024 | 4375 | 0 | 4375
2 | 1 | Job Accounting / Administration | Reimbursement for September 2024 | 4062.5 | 0 | 4062.5
2 | 1 | Project Superintendent | Reimbursement for August (Partial) and September 2024 | 12500 | 0 | 12500
2 | 1 | Safety | Invoice from Cornerstone Safety | 2995 | 0 | 2995
2 | 1 | Temporary Fencing (Chain Link) | Viking Fence Co - Additional Payment | 110.41 | 0 | 110.41
2 | 1 | Blueprint Printing | Stewart Engineering | 617.28 | 0 | 617.28
2 | 1 | Temporary Toilets - Recurring Payment | A-1 Little John | 130.44 | 0 | 130.44
2 | 1 | Temporary Toilets - Recurring Payment | A-1 Little John | 130.44 | 0 | 130.44
2 | 1 | OpenSpace - Camera | Testing and Inspection Services - Monitoring | 969.9 | 0 | 969.9
2 | 1 | OpenSpace - Camera Accessories | Testing and Inspection Services - Monitoring | 106.21 | 0 | 106.21
2 | 1 | OpenSpace - Subscription | Testing and Inspection Services - Monitoring | 5863 | 0 | 5863
2 | 1 | Construction Signage & Safety Equipment |  | 340.05 | 0 | 340.05
2 | 1 | Construction Signage & Safety Equipment |  | 26.96 | 0 | 26.96
2 | 1 | Construction Signage & Safety Equipment |  | 64.32 | 0 | 64.32
2 | 1 | Construction Signage & Safety Equipment |  | 82.91 | 0 | 82.91
2 | 1 | Construction Signage & Safety Equipment |  | 140.62 | 0 | 140.62
2 | 1 | Water Station Tent | Required by Safety Consultant | 215.42 | 0 | 215.42
2 | 1 | Notary Fees |  | 20 | 0 | 20
2 | 1 | Misc. Jobsite Materials |  | 374.55 | 0 | 374.55
2 | 15 | Plumbing | Underground Rough-In | 160000 | 16000 | 144000
2 | 18 | Contractor's Fee - Forecast | For October 2024 | 18750 | 1875 | 16875
2 | 1 | Project Manager - Forecast | For October 2024 | 4375 | 0 | 4375
2 | 1 | Job Accounting / Administration - Forecast | For October 2024 | 4062.5 | 0 | 4062.5
2 | 1 | Project Superintendent - Forecast | For October 2024 | 10000 | 0 | 10000
2 | 2 | Sitework - Forecast | Site Utilities + Paving + Remaining Dirt Work | 211391.1 | 0 | 211391.1
2 | 3 | Concrete - Forecast | Partial Paving Completed + Building Pad & Other Paving Forecast | 570500 | 0 | 570500
2 | 6 | Wood, Plastics, and Composites - Forecast | Framing Labor | 50000 | 5000 | 45000
2 | 16 | Electrical - Forecast | Rough-In Completed + Future Work | 35000 | 3000 | 32000
2 | 5 | Metals - Forecast | Structural Steel Erection + Materials | 60000 | 2600 | 57400
3 | 1 | Cornerstone Safety | Per Ownership Requirements - Adjusted Balance (True Up) | 44.85 | 0 | 44.85
3 | 1 | Cornerstone Safety | Per Ownership Requirements | 1544.85 | 0 | 1544.85
3 | 1 | Cornerstone Safety | Per Ownership Requirements | 1544.85 | 0 | 1544.85
3 | 1 | Jobsite Storage Container | From Willscot | 150.74 | 0 | 150.74
3 | 1 | Jobsite Storage Container | From Willscot | 781.84 | 0 | 781.84
3 | 1 | Jobsite Storage Container | From Willscot | 150.74 | 0 | 150.74
3 | 1 | Jobsite Storage Container | From Willscot | 150.74 | 0 | 150.74
3 | 1 | Jobsite Storage Container | From Willscot | 781.84 | 0 | 781.84
3 | 1 | Jobsite Storage Container | From Willscot | 150.74 | 0 | 150.74
3 | 1 | Jobsite Office | From Willscot | 817.83 | 0 | 817.83
3 | 1 | Jobsite Office | From Willscot | 1997.75 | 0 | 1997.75
3 | 1 | Temporary Toilets - Recurring Payment | A-1 Little John | 260.88 | 0 | 260.88
3 | 1 | Temporary Toilets - Recurring Payment | A-1 Little John | 342.07 | 0 | 342.07
3 | 1 | Temporary Fencing (Chain Link) | Viking Fence Co | 457.36 | 0 | 457.36
3 | 1 | Temporary Fencing (Chain Link) | Viking Fence Co | 98.54 | 0 | 98.54
3 | 1 | Misc. Jobsite Materials | From Home Depot | 430.19 | 0 | 430.19
3 | 1 | Misc. Jobsite Materials | From Home Depot | 104.67 | 0 | 104.67
3 | 1 | Misc. Jobsite Materials | From Home Depot | 200.47 | 0 | 200.47
3 | 1 | Misc. Jobsite Materials | From Home Depot | 23.6 | 0 | 23.6
3 | 1 | Misc. Jobsite Materials | From Home Depot | 238.58 | 0 | 238.58
3 | 1 | Misc. Jobsite Materials | From Home Depot | 112.11 | 0 | 112.11
3 | 1 | Misc. Jobsite Materials | From Home Depot | 56.13 | 0 | 56.13
3 | 1 | Misc. Jobsite Materials | From Home Depot | 45.4 | 0 | 45.4
3 | 1 | Misc. Jobsite Materials | From Home Depot | 83.67 | 0 | 83.67
3 | 1 | Misc. Jobsite Materials | From Home Depot | 207.27 | 0 | 207.27
3 | 1 | Misc. Jobsite Materials | From Home Depot | 202.58 | 0 | 202.58
3 | 1 | Misc. Jobsite Materials | From Home Depot | 48.84 | 0 | 48.84
3 | 1 | Misc. Jobsite Materials | From Lowe's | 331.7 | 0 | 331.7
3 | 1 | Sidewalk Closed Signs - Per City Requirements | From Lite & Barricade | 151.55 | 0 | 151.55
3 | 1 | Diesel for Equipment | Job Supervisor | 1000 | 0 | 1000
3 | 1 | Jobsite Dumpster | From Advantage Waste Disposal | 724.74 | 0 | 724.74
3 | 1 | Jobsite Dumpster | From Advantage Waste Disposal | 206 | 0 | 206
3 | 1 | Jobsite Dumpster | From Advantage Waste Disposal | 724.74 | 0 | 724.74
3 | 1 | Jobsite Dumpster | From Advantage Waste Disposal | 1540.74 | 0 | 1540.74
3 | 1 | Jobsite Dumpster | From Advantage Waste Disposal | 703.63 | 0 | 703.63
3 | 1 | Jobsite Dumpster | From Advantage Waste Disposal | 703.63 | 0 | 703.63
3 | 1 | Security Cameras | Birdseye Surveillance | 1665.5 | 0 | 1665.5
3 | 1 | Notary Fees | For Draw | 10 | 0 | 10
3 | 1 | Job Supervisor | For November 2024 | 10000 | 0 | 10000
3 | 1 | Job Supervisor | For December 2024 | 10000 | 0 | 10000
3 | 1 | Project Manager | Boulder Construction - For November 2024 (True Up Prior - 18 Mo) | 2430.5556 | 0 | 2430.5556
3 | 1 | Job Accounting / Administration | Boulder Construction - For November 2024 (True Up Prior - 18 Mo) | 2256.9444 | 0 | 2256.9444
3 | 1 | Blueprint Printing | Stewart Engineering | 399.4 | 0 | 399.4
3 | 6 | Lumber Takeoff | Joe Cruz | 1300 | 0 | 1300
3 | 6 | Framing Efforts + Takeoff/Discussion | Go Construction | 5000 | 0 | 5000
3 | 6 | Millwork Shop Drawings | Dreamwood | 3000 | 0 | 3000
3 | 6 | Framing First Floor | For Reytex Framing Corporation | 2850 | 0 | 2850
3 | 6 | Framing Labor | For Reytex Framing Corporation - Adjusted Balance (True Up) | 15032 | 1503.2 | 13528.8
3 | 6 | Framing Labor | For Reytex Framing Corporation | 32895 | 3289.5 | 29605.5
3 | 6 | Framing Material | From Home Depot | 98557.93 | 0 | 98557.93
3 | 6 | Framing Material | From Home Depot | 2753.19 | 0 | 2753.19
3 | 6 | Framing Material | From Home Depot | 723.28 | 0 | 723.28
3 | 6 | Framing Material | From Home Depot | 49749.95 | 0 | 49749.95
3 | 6 | Framing Material | From Home Depot | 6594.76 | 0 | 6594.76
3 | 6 | Framing Material | From Home Depot | 28345.61 | 0 | 28345.61
3 | 6 | Framing Material | From Home Depot | 2238.76 | 0 | 2238.76
3 | 6 | Framing Material | From Home Depot | 11690.87 | 0 | 11690.87
3 | 6 | Framing Material | From Home Depot | 37265.28 | 0 | 37265.28
3 | 6 | Framing Material | From Home Depot | 405.67 | 0 | 405.67
3 | 6 | Framing Material | From Home Depot | 63 | 0 | 63
3 | 6 | Framing Material | From Cowtown Materials | 453.76 | 0 | 453.76
3 | 6 | Truss Material | From Ranger Truss | 49299.87 | 0 | 49299.87
3 | 8 | Window Deposit True Up | Additional Deposit Amount for Windows (Increased Scope) | 34534.21 | 0 | 34534.21
3 | 13 | Kone Initial Deposit - Partial True Up | Partial True Up of Retainage | 3748 | 3748 | 0
3 | 15 | Plumbing - Misc. Material | From Home Depot | 70.63 | 0 | 70.63
3 | 15 | Plumbing - Misc. Material | From Home Depot | 90.95 | 0 | 90.95
3 | 15 | Plumbing - Misc. Material | From Home Depot | 12.89 | 0 | 12.89
3 | 15 | Plumbing - Misc. Material | From Home Depot | 204.02 | 0 | 204.02
3 | 15 | Plumbing - Misc. Material | From Home Depot | 106.81 | 0 | 106.81
3 | 16 | Electrical - Switch Gear True Up | Additional Deposit Amount for Switch Gear | 701.46 | 0 | 701.46
3 | 16 | Electrical Material | Elliott Electric - Adjusted Balance (True Up) | 2269.27 | 0 | 2269.27
3 | 17 | Insurance | Additional Insurance Costs (Less Funds From Prior Draw) | 573.03 | 0 | 573.03
3 | 18 | Contractor's Fee | Boulder Construction - For November 2024 (True Up Prior - 18 Mo) | 10416.6667 | 1041.6667 | 9375
3 | 6 | Truss Material | From Ranger Truss | 48189.65 | 0 | 48189.65
3 | 6 | Truss Material | From Ranger Truss | 48189.65 | 0 | 48189.65
3 | 6 | Framing - Equipment | EquipmentShare | 7083.62 | 0 | 7083.62
4 | 1 | Job Supervisor | For January 2025 | 10000 | 0 | 10000
4 | 1 | Project Manager | Boulder Construction - For December 2024 | 3888.8889 | 0 | 3888.8889
4 | 1 | Job Accounting / Administration | Boulder Construction - For December 2024 | 3611.1111 | 0 | 3611.1111
4 | 1 | Project Manager | Boulder Construction - For January 2025 | 3888.8889 | 0 | 3888.8889
4 | 1 | Job Accounting / Administration | Boulder Construction - For January 2025 | 3611.1111 | 0 | 3611.1111
4 | 1 | Cornerstone Safety | Per Ownership Requirements | 1500 | 0 | 1500
4 | 1 | Cornerstone Safety | Per Ownership Requirements | 1500 | 0 | 1500
4 | 1 | Blueprint Printing | Office Depot | 5.54 | 0 | 5.54
4 | 1 | Blueprint Printing | Office Depot | 20.5 | 0 | 20.5
4 | 1 | Jobsite Labor | Clean Up | 380 | 0 | 380
4 | 1 | Jobsite Labor | Clean Up | 950 | 0 | 950
4 | 1 | Jobsite Labor | Clean Up | 370 | 0 | 370
4 | 1 | Jobsite Labor | Clean Up | 475 | 0 | 475
4 | 1 | Jobsite Labor | Clean Up | 807.5 | 0 | 807.5
4 | 1 | Jobsite Dumpster | From Advantage Waste Disposal | 807.19 | 0 | 807.19
4 | 1 | Jobsite Dumpster | From Advantage Waste Disposal | 990.11 | 0 | 990.11
4 | 1 | Jobsite Dumpster | From Advantage Waste Disposal | 811.93 | 0 | 811.93
4 | 1 | Security Cameras | Birdseye Surveillance | 1515.5 | 0 | 1515.5
4 | 1 | Jobsite Storage Container | From Willscot | 150.74 | 0 | 150.74
4 | 1 | Jobsite Storage Container | From Willscot | 150.74 | 0 | 150.74
4 | 1 | Jobsite Office | From Willscot | 817.83 | 0 | 817.83
4 | 1 | Temporary Toilets - Recurring Payment | A-1 Little John | 260.88 | 0 | 260.88
4 | 1 | Misc. Jobsite Materials | From Home Depot | 71.87 | 0 | 71.87
4 | 1 | Misc. Jobsite Materials | From Home Depot | 115.41 | 0 | 115.41
4 | 1 | Procore Subscription | For Jobsite Reporting | 6502.6 | 0 | 6502.6
4 | 1 | Notary Fees | For Draw | 10 | 0 | 10
4 | 3 | Concrete - Labor + Material | To M D Bowles Construction - Adjusted Balance (True Up Prior) | 31000 | 15000 | 16000
4 | 3 | Concrete - Misc. Material | From Home Depot | 91.84 | 0 | 91.84
4 | 3 | Concrete - Misc. Material | From Home Depot | 183.55 | 0 | 183.55
4 | 3 | Rebar | From Ready Cable | 621.36 | 0 | 621.36
4 | 3 | Concrete - Misc. Material | From Home Depot | 70.22 | 0 | 70.22
4 | 3 | Concrete - Light Pole Locations | AIM Construction Services | 700 | 0 | 700
4 | 3 | Concrete - Termite Control | From Bug Stop Pest Solutions (Reimbursement to MD Bowles Const.) | 5412.5 | 0 | 5412.5
4 | 3 | Concrete - Clearing Area for Paving | Haul Off Excess Dirt/Rock | 13080 | 0 | 13080
4 | 6 | Framing Material | From Home Depot | 21398.51 | 0 | 21398.51
4 | 6 | Framing Material | From Home Depot | 17049.67 | 0 | 17049.67
4 | 6 | Framing Material | From Home Depot | 52825.48 | 0 | 52825.48
4 | 6 | Framing Material | From Home Depot | 9190.86 | 0 | 9190.86
4 | 6 | Framing Material | From Home Depot | 16716.45 | 0 | 16716.45
4 | 6 | Framing Material | From Home Depot | 1436.52 | 0 | 1436.52
4 | 6 | Framing Labor | For Reytex Framing Corporation | 23450 | 0 | 23450
4 | 6 | Framing Labor | For Reytex Framing Corporation | 28398 | 2839.8 | 25558.2
4 | 6 | Framing Labor | For Reytex Framing Corporation | 26250 | 4970 | 21280
4 | 6 | Framing Labor | For Reytex Framing Corporation | 28750 | 0 | 28750
4 | 6 | Framing Labor | For Reytex Framing Corporation | 22500 | 5125 | 17375
4 | 6 | Framing Material | From Home Depot | 912.07 | 0 | 912.07
4 | 6 | Framing Material - Marking Material | From Home Depot | 110.29 | 0 | 110.29
4 | 6 | Framing Material | From Home Depot | 412.57 | 0 | 412.57
4 | 10 | Tub and Shower Surrounds | 50% Deposit (Pre-Tax & Shipping) | 20323.92 | 0 | 20323.92
4 | 10 | Toilet Accessories (Dish, Foot Rest, Ledge, Trim) | 50% Deposit (Pre-Tax & Shipping) | 6054.89 | 0 | 6054.89
4 | 16 | Electrical Material | Elliott Electric | 2527.8 | 0 | 2527.8
4 | 16 | Electrical Material | Elliott Electric | 7810.7 | 0 | 7810.7
4 | 16 | Electrical Material | Elliott Electric | 625.48 | 0 | 625.48
4 | 16 | Electrical Material | Elliott Electric | -136.22 | 0 | -136.22
4 | 16 | Electrical Material | Elliott Electric | 5451.95 | 0 | 5451.95
4 | 16 | Electrical Material | Elliott Electric | 123.02 | 0 | 123.02
4 | 16 | Electrical Material | Elliott Electric | 833.31 | 0 | 833.31
4 | 16 | Electrical Material | Elliott Electric | 993.58 | 0 | 993.58
4 | 16 | Electrical Material | Elliott Electric | 80.97 | 0 | 80.97
4 | 17 | Builder's Risk Insurance | Liberty Mutual - Remaining Charge Amount from Prior Transaction | 82.76 | 0 | 82.76
4 | 17 | Builder's Risk Insurance | Liberty Mutual | 3455.59 | 0 | 3455.59
4 | 18 | Contractor's Fee | Boulder Construction - For December 2024 | 16666.6667 | 1666.6667 | 15000
4 | 18 | Contractor's Fee | Boulder Construction - For January 2025 | 16666.6667 | 1666.6667 | 15000
4 | 3 | Concrete - Rock for Pump Truck on Dirt | Import Rock | 700 | 0 | 700
4 | 6 | Framing - Equipment | EquipmentShare | 3750.43 | 0 | 3750.43
4 | 8 | Onity Locks | 65% Deposit (For Discount) | 30327 | 0 | 30327
4 | 14 | Fire Alarm/Sprinkler Designs | Initial Invoice - 01 | 30000 | 3000 | 27000
4 | 15 | Plumbing - Top Out Labor | MA Williams Plumbing Invoice | 66666.66 | 6666.66 | 60000
5 | 1 | Job Supervisor | For February 2025 | 10000 | 0 | 10000
5 | 1 | Project Manager | Boulder Construction - For February 2025 | 3888.8889 | 0 | 3888.8889
5 | 1 | Job Accounting / Administration | Boulder Construction - For February 2025 | 3611.1111 | 0 | 3611.1111
5 | 3 | Pouring Temporary Approach and Clean Up | M D Bowles Construction (Change Order) | 8600 | 0 | 8600
5 | 6 | Framing Labor | For Reytex Framing Corporation | 22000 | 2200 | 19800
5 | 6 | Framing Labor | For Reytex Framing Corporation | 25960 | 2596 | 23364
5 | 8 | Order Windows | Top Bright Windows and Door - Additional Deposit | 36604.21 | 0 | 36604.21
5 | 15 | Plumbing Underground and Top Out Material | From Moore Supply | 121688.63 | 0 | 121688.63
5 | 18 | Contractor's Fee | Boulder Construction - For February 2025 | 16666.6667 | 1666.6667 | 15000
5 | 6 | Truss Material | From Ranger Truss | 78653.15 | 0 | 78653.15
5 | 8 | Order Windows | Top Bright Windows and Door - Additional Deposit | 56541.12 | 0 | 56541.12
5 | 7 | Roofing Material and Labor | First Invoice - LED Roofing | 150000 | 15000 | 135000
5 | 10 | Tub and Shower Surrounds | Remaining Deposit (Pre-Tax) | 20323.92 | 0 | 20323.92
5 | 10 | Toilet Accessories (Dish, Foot Rest, Ledge, Trim) | Remaining Deposit (Pre-Tax) | 6054.89 | 0 | 6054.89
5 | 10 | Tub and Shower Surrounds | Allocated Shipping Costs | 7539.2201 | 0 | 7539.2201
5 | 10 | Toilet Accessories (Dish, Foot Rest, Ledge, Trim) | Allocated Shipping Costs | 2246.0799 | 0 | 2246.0799
5 | 15 | HVAC/Mechanical Material and Labor | First Invoice - Iceberg Heating & AC | 150000 | 15000 | 135000
5 | 15 | Plumbing Top Out Labor | MA Williams Plumbing Invoice | 44444.44 | 4444.44 | 40000
5 | 16 | Switch Gear Payment | From Greens Distribution | 82160.36 | 0 | 82160.36
6 | 1 | Notary Fees | For Draw | 10 | 0 | 10
6 | 1 | Jobsite Dumpster | From Waste Connections | 1216.12 | 0 | 1216.12
6 | 1 | Jobsite Dumpster | From Waste Connections | 1 | 0 | 1
6 | 1 | Jobsite Dumpster | From Waste Connections | 1009.79 | 0 | 1009.79
6 | 1 | Jobsite Dumpster | From Waste Connections | 1149.9 | 0 | 1149.9
6 | 1 | Jobsite Dumpster | From Waste Connections | 943.58 | 0 | 943.58
6 | 1 | Jobsite Dumpster | From Waste Connections | 1009.79 | 0 | 1009.79
6 | 1 | Jobsite Office - Recurring Rental | From Willscot | 817.83 | 0 | 817.83
6 | 1 | Jobsite Storage Container - Rental + Drop Off | From Willscot | 1031.62 | 0 | 1031.62
6 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 150.74 | 0 | 150.74
6 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 150.74 | 0 | 150.74
6 | 1 | Jobsite Storage Container - Rental + Drop Off | From Willscot | 1031.62 | 0 | 1031.62
6 | 1 | Jobsite Office - Recurring Rental | From Willscot | 817.83 | 0 | 817.83
6 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27
6 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 150.74 | 0 | 150.74
6 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 150.74 | 0 | 150.74
6 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27
6 | 1 | Jobsite Storage Container - Rental + Drop Off | From Willscot | 1031.62 | 0 | 1031.62
6 | 1 | Misc. Jobsite Materials | From Home Depot - Bags, Fuel and Oil, Spray Paint | 181.8 | 0 | 181.8
6 | 1 | Misc. Jobsite Materials | From Home Depot - Spray Paint & Other for Marriott Walk | 216.51 | 0 | 216.51
6 | 1 | Misc. Jobsite Materials | From Home Depot - Spray Paint for Marriott Walk | 43.21 | 0 | 43.21
6 | 1 | Temporary Toilets - Recurring Payment | A-1 Little John | 260.88 | 0 | 260.88
6 | 1 | Misc. Jobsite Materials | From Home Depot - Fuel and Oil | 22.64 | 0 | 22.64
6 | 1 | Misc. Jobsite Materials | From Home Depot - Cable Ties | 31.37 | 0 | 31.37
6 | 1 | Misc. Jobsite Materials | From Home Depot - Ice Melt Bag | 86.44 | 0 | 86.44
6 | 1 | Misc. Jobsite Materials | From Home Depot - Gas Can | 48.65 | 0 | 48.65
6 | 1 | Temporary Toilets - Recurring Payment | A-1 Little John | 260.88 | 0 | 260.88
6 | 1 | Misc. Jobsite Materials | From Home Depot - Combination Lock | 32.65 | 0 | 32.65
6 | 1 | Jobsite Dumpster | From Advantage Waste Disposal | 57.81 | 0 | 57.81
6 | 1 | Jobsite Dumpster | From Advantage Waste Disposal | 724.74 | 0 | 724.74
6 | 1 | Notary Fees | For Draw | 10 | 0 | 10
6 | 1 | Jobsite Dumpster | From Waste Connections | 943.58 | 0 | 943.58
6 | 1 | Security Cameras | Birdseye Surveillance | 1515.5 | 0 | 1515.5
6 | 1 | Security Cameras | Birdseye Surveillance | 1515.5 | 0 | 1515.5
6 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 760 | 0 | 760
6 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 1185.75 | 0 | 1185.75
6 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 1282.5 | 0 | 1282.5
6 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 665 | 0 | 665
6 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 546.25 | 0 | 546.25
6 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 617.5 | 0 | 617.5
6 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 356.25 | 0 | 356.25
6 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 1068.75 | 0 | 1068.75
6 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 950 | 0 | 950
6 | 1 | Cornerstone Safety | Per Ownership Requirements | 1500 | 0 | 1500
6 | 3 | Concrete - Surveyor to Stake Out Paving | AIM Construction Services | 700 | 0 | 700
6 | 3 | Concrete - Surveyor to Stake Out Multiple Areas | AIM Construction Services | 1460 | 0 | 1460
6 | 3 | Rebar Shop Drawings | From Post-Tension Services | 1400.8 | 0 | 1400.8
6 | 6 | Framing - Required Fire Hydrants | From Texas Fire Extinguisher | 2776.29 | 0 | 2776.29
6 | 6 | Framing Material | From Home Depot - Fall Protection | 150.45 | 0 | 150.45
6 | 6 | Framing Material | From Home Depot - Fall Protection & Anchor | 404.16 | 0 | 404.16
6 | 6 | Framing Material | From Home Depot - Parawedge Anchor | 235.99 | 0 | 235.99
6 | 6 | Framing Material | From Home Depot - Return for Parawedge Anchor | -353.98 | 0 | -353.98
6 | 6 | Framing Material | From Home Depot - Misc. Return | -1.65 | 0 | -1.65
6 | 6 | Framing Material | From Home Depot - Misc. | 100 | 0 | 100
6 | 6 | Framing Material | From Home Depot - Washers and Screws | 85.7 | 0 | 85.7
6 | 6 | Framing Material | From Home Depot - Hurricane Ties | 179.7 | 0 | 179.7
6 | 6 | Framing Material | From Home Depot - Zip System Tape | 1329.71 | 0 | 1329.71
6 | 6 | Framing Material | From Home Depot - Hex Nut | 90.75 | 0 | 90.75
6 | 6 | Framing Material | From Home Depot - Het Nut and Washer | 51.9 | 0 | 51.9
6 | 6 | Framing Material | From Office Depot - Truss Layout Pages | 40.85 | 0 | 40.85
6 | 6 | Framing Material | From Home Depot - Hex Nut and Dimensional Lumber | 1938.43 | 0 | 1938.43
6 | 6 | Framing Material | From Home Depot - Sheathing and Strand Board | 8551.62 | 0 | 8551.62
6 | 6 | Framing Material | From Home Depot - OSB Subfloor | 3384.41 | 0 | 3384.41
6 | 6 | Framing Material | From Home Depot - Simpson Strong-Ties | 1400.76 | 0 | 1400.76
6 | 6 | Framing Material | From Home Depot - LVL | 570.46 | 0 | 570.46
6 | 6 | Framing Material | From Home Depot - Standard and Treated Lumber | 2871.09 | 0 | 2871.09
6 | 6 | Framing Material | From Home Depot - OSB Subfloor | 2538.31 | 0 | 2538.31
6 | 6 | Framing Material | From Home Depot - Hurricane Ties | 1185.12 | 0 | 1185.12
6 | 6 | Framing Material | From Home Depot - Washer/Nuts, Strong Ties, Flashing Tape | 2792.31 | 0 | 2792.31
6 | 6 | Framing Material | From Home Depot - Anchor Bolts and Epoxy | 9937.53 | 0 | 9937.53
6 | 6 | Framing Material | From Home Depot - Sheathing and Dimensional Lumber | 5549.41 | 0 | 5549.41
6 | 6 | Framing Labor | For Reytex Framing Corporation - Invoice 14 | 5400 | 540 | 4860
6 | 6 | Framing Labor | For Reytex Framing Corporation - Revised Invoice 15 | 6380 | 638 | 5742
6 | 6 | Framing Labor | For Reytex Framing Corporation - Revised Invoice 17 | 4333.33 | 433.333 | 3899.997
6 | 6 | Framing Labor | For Reytex Framing Corporation - Invoice 18 | 4500 | 450 | 4050
6 | 6 | Framing Labor | For Reytex Framing Corporation - Invoice 19 (Partial Payment) | 4500 | 450 | 4050
6 | 7 | Corridor Insulation Inspection | From Geoscience Engineers | 255 | 0 | 255
6 | 8 | Deposit for Doors | For Ongoing Windows & Doors | 8280 | 0 | 8280
6 | 8 | Deposit for Doors | For Ongoing Windows & Doors | 8280 | 0 | 8280
6 | 8 | Deposit for Doors | For Ongoing Windows & Doors | 8280 | 0 | 8280
6 | 8 | Deposit for Doors | For Ongoing Windows & Doors | 8280 | 0 | 8280
6 | 10 | Tub and Shower Surrounds | Additional Invoice Amount | 190 | 0 | 190
6 | 15 | Sample VTAC | From Greens Electric - For Mock Up Room | 2177.84 | 0 | 2177.84
6 | 16 | Electrical Material | Elliott Electric | 37.69 | 0 | 37.69
6 | 16 | Electrical Material | Elliott Electric | 364.83 | 0 | 364.83
6 | 16 | Electrical Material | Elliott Electric | 1126.38 | 0 | 1126.38
6 | 16 | Electrical Material | Elliott Electric | 2229.42 | 0 | 2229.42
6 | 16 | Electrical Material | Elliott Electric | 127.41 | 0 | 127.41
6 | 16 | Electrical Material | Elliott Electric | 2982.84 | 0 | 2982.84
6 | 16 | Electrical Material | Elliott Electric | 567.76 | 0 | 567.76
6 | 16 | Electrical Material | Elliott Electric | 3269.15 | 0 | 3269.15
6 | 16 | Electrical Material | Elliott Electric | 1307.12 | 0 | 1307.12
6 | 16 | Electrical Material | Elliott Electric | 248.92 | 0 | 248.92
6 | 16 | Electrical Material | Elliott Electric | 3498.37 | 0 | 3498.37
6 | 17 | Builder's Risk Insurance | Liberty Mutual | 3454.07 | 0 | 3454.07
6 | 17 | Builder's Risk Insurance | Liberty Mutual | 3454.07 | 0 | 3454.07
6 | 1 | Job Supervisor | For March 2025 | 10000 | 0 | 10000
6 | 1 | Project Manager | Boulder Construction - For March 2025 | 3888.8889 | 0 | 3888.8889
6 | 1 | Job Accounting / Administration | Boulder Construction - For March 2025 | 3611.1111 | 0 | 3611.1111
6 | 1 | Cornerstone Safety | Per Ownership Requirements | 1500 | 0 | 1500
6 | 2 | Equipment Rental + Purchase of Safety Platforms | EquipmentShare | 8660.01 | 0 | 8660.01
6 | 3 | As Built Drawings | From A U Design (For Confirmation of Slab/Other Dimensions) | 7200 | 0 | 7200
6 | 3 | Concrete - Additional Paving Section | From M D Bowles Construction | 102000 | 10200 | 91800
6 | 3 | Concrete - Select Fill Material to Grade Paving | From M D Bowles Construction | 1100 | 0 | 1100
6 | 6 | Framing - Equipment | EquipmentShare | 18343.82 | 0 | 18343.82
6 | 7 | Prerock / Insulation for Top of Corridor | RFM Ventures - First Invoice | 25000 | 2500 | 22500
6 | 8 | Additional Deposit for Doors | For Ongoing Windows & Doors | 32935.4 | 0 | 32935.4
6 | 8 | Order Windows | Top Bright Windows and Door - Additional Deposit | 48589.27 | 0 | 48589.27
6 | 14 | Fire Standpipe | From Safe Life FP | 15000 | 1500 | 13500
6 | 15 | VTAC Sleeves | From Greens Electric | 22490.02 | 0 | 22490.02
6 | 15 | VTAC Costs - 50% Deposit | From Greens Electric | 107476 | 0 | 107476
6 | 16 | Fire Alarm Rough | From Safe Life FP | 46500 | 4650 | 41850
6 | 18 | Contractor's Fee | Boulder Construction - For March 2025 | 16666.6667 | 1666.6667 | 15000
6 | 3 | Concrete - Future Forecast Payments |  | 50000 | 5000 | 45000
7 | 1 | Jobsite Office - Recurring Rental | From Willscot | 817.83 | 0 | 817.83 | 10349
7 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 10350
7 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 150.74 | 0 | 150.74 | 10352
7 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 150.74 | 0 | 150.74 | 10353
7 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 10351
7 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 10354
7 | 1 | Jobsite Storage Container - Rental + Drop Off | From Willscot | 1031.62 | 0 | 1031.62 | 10355
7 | 1 | Jobsite Storage Container - Rental + Drop Off | From Willscot | 1031.62 | 0 | 1031.62 | 10356
7 | 1 | Temporary Toilets - Recurring Payment | A-1 Little John | 260.88 | 0 | 260.88 | 10357
7 | 1 | Notary Fees | For Draw | 10 | 0 | 10
7 | 1 | Meal for Jobsite Crew | From Dominos | 121.16 | 0 | 121.16
7 | 1 | Jobsite Dumpster | From Waste Connections | 1009.79 | 0 | 1009.79 | 10358
7 | 1 | Generators for Jobsite Office + Building | From Harbor Freight Tools | 3355.71 | 0 | 3355.71 | 10359
7 | 1 | Misc. Jobsite Materials | From Home Depot - Hand Truck (Dolley) | 75.26 | 0 | 75.26 | 10363
7 | 1 | Misc. Jobsite Materials | From Home Depot - Coil Chain, Deck Screws, and Padlock | 50.55 | 0 | 50.55 | 10367
7 | 1 | Misc. Jobsite Materials | From Home Depot - Deck Screws and Padlock/Combination Locks | 80.17 | 0 | 80.17 | 10369
7 | 1 | Permit and New Construction Display Board | From Minuteman Press | 909.3 | 0 | 909.3 | 10388
7 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 502.5 | 0 | 502.5 | 10395
7 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 1045 | 0 | 1045 | 10396
7 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 500 | 0 | 500 | 10397
7 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 1467.5 | 0 | 1467.5 | 10398
7 | 2 | Water Meter Usage | City of Waxahachie - Adjusted Balance (True Up) | 240.883 | 0 | 240.883 | 10210
7 | 2 | Water Meter Usage | City of Waxahachie | 771.09 | 0 | 771.09 | 10210
7 | 2 | Import Washed Rock | Superman Trucking and Delivery Inc | 2490 | 0 | 2490 | 10213
7 | 2 | Import Washed Rock | Superman Trucking and Delivery Inc | 1245 | 0 | 1245 | 10214
7 | 2 | Import Washed Rock | Superman Trucking and Delivery Inc | 1245 | 0 | 1245 | 10215
7 | 2 | Traffic Control Plan | For Utility Tie-In | 162.38 | 0 | 162.38 | 10240
7 | 2 | Utilities - Misc. Material | From Home Depot - Hose and Pump for Drainage | 214.77 | 0 | 214.77 | 10257
7 | 2 | Earthwork - Misc. Material | From Home Depot - Zip Ties | 47.93 | 0 | 47.93 | 10276
7 | 2 | Earthwork - Misc. Material | From Home Depot - Zip Ties and Silt Fence | 259.12 | 0 | 259.12 | 10277
7 | 2 | Earthwork - Testing | Geoscience Engineers | 3219 | 0 | 3219 | 10287
7 | 2 | Utilities - Additional Material | From Moore Supply - Allocated Payment (Excl. Plumbing Allocation) | 11829.93 | 0 | 11829.93 | 10288
7 | 2 | Earthwork - SW3P | Cardinal Strategies | 1125 | 0 | 1125 | 10319
7 | 2 | Material for Utility Tie In on Rae Blvd | From Britton Meter Supply | 19170.76 | 0 | 19170.76 | 10386
7 | 2 | Water Meter Usage | City of Waxahachie | 985.24 | 0 | 985.24 | 10389
7 | 2 | Trench Safety Boxes for Utility Tie In | From National Trench Safety | 2966.4 | 0 | 2966.4 | 10390
7 | 2 | Trench Safety Boxes for Utility Tie In | From National Trench Safety | -662.91 | 0 | -662.91 | 10390
7 | 2 | Traffic Control Material for the Utility Tie In | From Buyers Barricades | 347.92 | 0 | 347.92 | 10391
7 | 2 | Earthwork - SW3P | Cardinal Strategies | 375 | 0 | 375 | 10393
7 | 2 | Earthwork - SW3P | Cardinal Strategies | 375 | 0 | 375 | 10394
7 | 3 | Dirt Import to Backfill Curbs | From Alliance Trucking | 5566 | 0 | 5566 | 10401
7 | 3 | Pouring and Forming Inlet Lids for Utilities | From Americo Concrete | 3200 | 0 | 3200 | 10402
7 | 4 | CMU Block Material | From Home Depot - Concrete Block | 964.51 | 0 | 964.51 | 10362
7 | 6 | Framing Material | From Home Depot - Common Nails and Sheathing | 203.36 | 0 | 203.36 | 10360
7 | 6 | Framing Material | From Home Depot - Sheathing, Panel, and Step Stone | 105.18 | 0 | 105.18 | 10361
7 | 6 | Framing Material | From Home Depot - Window Sealant and Cutting Saws | 844.92 | 0 | 844.92 | 10368
7 | 6 | Framing Material | From Home Depot - Zip Tape | 880.72 | 0 | 880.72 | 10370
7 | 6 | Framing Material | From Home Depot - Joist Hanger | 108.94 | 0 | 108.94 | 10371
7 | 6 | Framing Material | From Home Depot - Hurricane Ties | 89.85 | 0 | 89.85 | 10372
7 | 6 | Framing Material | From Home Depot - Strong Ties, Hex Nuts, and Washers | 1255.09 | 0 | 1255.09 | 10403
7 | 6 | Framing Material | From Home Depot - Dimensional Lumber | 1606.15 | 0 | 1606.15 | 10404
7 | 6 | Framing Material | From Home Depot - Dimensional Lumber | 1972.62 | 0 | 1972.62 | 10405
7 | 6 | Framing Labor | For Reytex Framing Corporation - Invoice 20 | 3500 | 350 | 3150 | 10399
7 | 6 | Framing Labor | For Reytex Framing Corporation - Invoice 21/22 | 8500 | 850 | 7650 | 10400
7 | 6 | Framing Labor | For Reytex Framing Corporation - Invoice 23 | 4475 | 447.5 | 4027.5 | 10406
7 | 7 | Stucco Material | From Imperial Wallboard Supply - HFP, Basecoat, Washers | 14914.9 | 0 | 14914.9 | 10385
7 | 9 | Misc. Jobsite Materials | From Home Depot - Paint for Model Room | 197.45 | 0 | 197.45 | 10364
7 | 9 | Misc. Jobsite Materials | From Home Depot - Paint for Model Room | 90.06 | 0 | 90.06 | 10365
7 | 9 | Misc. Jobsite Materials | From Home Depot - Paint for Model Room | 234.69 | 0 | 234.69 | 10366
7 | 16 | Electrical Material | Elliott Electric | 190.52 | 0 | 190.52 | 10373
7 | 16 | Electrical Material | Elliott Electric | 115.11 | 0 | 115.11 | 10374
7 | 16 | Electrical Material | Elliott Electric | 2257.88 | 0 | 2257.88 | 10375
7 | 16 | Electrical Material | Elliott Electric | 6928 | 0 | 6928 | 10376
7 | 16 | Electrical Material | Elliott Electric | 31.42 | 0 | 31.42 | 10377
7 | 16 | Electrical Material | Elliott Electric | 39.34 | 0 | 39.34 | 10378
7 | 16 | Electrical Material | Elliott Electric | 972.67 | 0 | 972.67 | 10379
7 | 16 | Electrical Material | Elliott Electric | 13.6 | 0 | 13.6 | 10382
7 | 16 | Electrical Material | Elliott Electric | 15.74 | 0 | 15.74 | 10380
7 | 16 | Electrical Material | Elliott Electric | 22.35 | 0 | 22.35 | 10383
7 | 16 | Electrical Material | Elliott Electric | 89.31 | 0 | 89.31 | 10384
7 | 16 | Electrical Material | Elliott Electric | 771.01 | 0 | 771.01 | 10381
7 | 16 | Electrical Material | Elliott Electric | 5296.67 | 0 | 5296.67 | 10407
7 | 17 | Builder's Risk Insurance | Liberty Mutual | 20675.19 | 0 | 20675.19 | 10387
7 | 1 | Job Supervisor | For April 2025 | 10000 | 0 | 10000
7 | 1 | Project Manager | Boulder Construction - For April 2025 | 3888.8889 | 0 | 3888.8889
7 | 1 | Job Accounting / Administration | Boulder Construction - For April 2025 | 3611.1111 | 0 | 3611.1111
7 | 2 | Equipment Rentals (For Utility) | EquipmentShare | 5536.28 | 0 | 5536.28
7 | 2 | Equipment Rentals (For General) | EquipmentShare | 9435.06 | 0 | 9435.06
7 | 4 | Dumpster Block Install | For VG Stucco | 8000 | 800 | 7200
7 | 7 | Stucco Labor Rough | For VG Stucco | 40000 | 4000 | 36000
7 | 7 | EFIS/Stone - Equipment | EquipmentShare | 5452.21 | 0 | 5452.21
7 | 15 | HVAC/Mechanical Material and Labor | Second Invoice - Iceberg Heating & AC | 86000 | 8600 | 77400
7 | 15 | HVAC/Mechanical Material and Labor | Second Invoice - True Up for Funds Received From Prior Draw | -25000 | -2500 | -22500
7 | 15 | Plumbing - Remaining Top Out Invoice | From MA Williams Plumbing | 123950.27 | 24563.9 | 99386.37
7 | 16 | Switch Gear | Greens Distribution - Additional Payment | 69121.18 | 0 | 69121.18
7 | 18 | Contractor's Fee | Boulder Construction - For April 2025 | 16666.6667 | 1666.6667 | 15000
8 | 1 | Jobsite Office - Recurring Rental | From Willscot | 817.83 | 0 | 817.83 | 10416
8 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 10419
8 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 10422
8 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 150.74 | 0 | 150.74 | 10423
8 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 150.74 | 0 | 150.74 | 10424
8 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 10430
8 | 1 | Jobsite Dumpster | From Waste Connections | 538 | 0 | 538 | 10418
8 | 1 | Temporary Toilets - Recurring Payment | A-1 Little John | 260.88 | 0 | 260.88 | 10411
8 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 1438.75 | 0 | 1438.75 | 10435
8 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 1575 | 0 | 1575 | 10436
8 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 950 | 0 | 950 | 10437
8 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 973.75 | 0 | 973.75 | 10455
8 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 240 | 0 | 240 | 10456
8 | 1 | Misc. Jobsite Materials | From Home Depot - Gloves, Glass Cleaner, Shop Vac, Cloth, Broom | 165.05 | 0 | 165.05 | 10425
8 | 1 | Misc. Jobsite Materials | From Home Depot - Gas String Trimmer and Fuel | 254.72 | 0 | 254.72 | 10438
8 | 1 | Misc. Jobsite Materials | From Home Depot - Return | -90.06 | 0 | -90.06
8 | 1 | Misc. Jobsite Materials - Model Room | From Home Depot - Wire Shelving and Closet Shelf | 39.42 | 0 | 39.42 | 10421
8 | 1 | Petty Cash | Reimbursement for Expenses/Petty Cash to Job Supervisor | 1500 | 0 | 1500 | 10445
8 | 1 | Diesel for Equipment |  | 33.96 | 0 | 33.96
8 | 1 | Diesel for Equipment |  | 27.57 | 0 | 27.57
8 | 1 | Diesel for Equipment |  | 28 | 0 | 28
8 | 1 | Diesel for Equipment |  | 31.16 | 0 | 31.16
8 | 1 | Diesel for Equipment |  | 13.4 | 0 | 13.4
8 | 1 | Diesel for Equipment |  | 11.83 | 0 | 11.83
8 | 1 | Security Cameras | Birdseye Surveillance | 1515.5 | 0 | 1515.5 | 10451
8 | 1 | Security Cameras | Birdseye Surveillance | 1515.5 | 0 | 1515.5 | 10452
8 | 2 | Material for Utility Tie In on Rae Blvd | From Britton Meter Supply | 13163.61 | 0 | 13163.61 | 10409
8 | 2 | Traffic Control Material for the Utility Tie In | From Buyers Barricades | 2002.63 | 0 | 2002.63 | 10410
8 | 2 | Earthwork - SW3P | Cardinal Strategies | 375 | 0 | 375 | 10453
8 | 3 | Concrete - Testing | Geoscience Engineers | 3060 | 0 | 3060 | 10454
8 | 6 | Framing Material | From Home Depot - Hold Downs and Strong Ties | 5102.78 | 0 | 5102.78 | 10417
8 | 6 | Framing Material | From Home Depot - Drill Bit, Hex Nuts, and Washer | 138.99 | 0 | 138.99 | 10414
8 | 6 | Framing Material | From Home Depot - Nailing Hammer, Zip Tape, Extension Cord, Shovel | 253.74 | 0 | 253.74 | 10415
8 | 6 | Framing Material | From Home Depot - Washer, Hex Nuts, Bolts, Cooler | 130.66 | 0 | 130.66 | 10420
8 | 6 | Framing Material | From Home Depot - Washer, Hex Nuts, Rods | 912.43 | 0 | 912.43 | 10413
8 | 6 | Framing Material | From Home Depot - Hex Nuts | 70.74 | 0 | 70.74 | 10412
8 | 6 | Framing Material | From Home Depot - Zip Tape | 880.72 | 0 | 880.72 | 10428
8 | 6 | Framing Material | From Home Depot - Zip Tape | 535.3 | 0 | 535.3 | 10429
8 | 6 | Framing Material | From Home Depot - Zip Tape | 2159.56 | 0 | 2159.56 | 10449
8 | 6 | Truss Material - Dog Houses | From American Truss - 50% Deposit | 5405.4 | 0 | 5405.4 | 10450
8 | 6 | Framing Labor | For Reytex Framing Corporation - Invoice 24 | 3000 | 300 | 2700 | 10431
8 | 6 | Framing Labor | For Reytex Framing Corporation - Invoice 25 | 2800 | 280 | 2520 | 10432
8 | 6 | Framing Labor | For Reytex Framing Corporation - Invoice 26 | 8100 | 810 | 7290 | 10441
8 | 7 | Stucco Material | From Red River Brick (A General Shale Company) | 10327.72 | 0 | 10327.72 | 10426
8 | 7 | Stucco/Stone Material | From Red River Brick (A General Shale Company) | 2868.2 | 0 | 2868.2
8 | 13 | Linen Chute | From Kasl Enterprises | 11800 | 0 | 11800 | 10427
8 | 16 | Electrical Material | Elliott Electric | 7.13 | 0 | 7.13 | 10408
8 | 16 | Structured Cabling - First Payment | From PSM Tech | 18750 | 1875 | 16875 | 10448
8 | 1 | Job Supervisor | For May 2025 | 10000 | 0 | 10000
8 | 1 | Project Manager | Boulder Construction - For May 2025 | 3888.8889 | 0 | 3888.8889
8 | 1 | Job Accounting / Administration | Boulder Construction - For May 2025 | 3611.1111 | 0 | 3611.1111
8 | 2 | Import Limestone and Cushion Sand Material | Superman Trucking and Delivery Inc | 1710 | 0 | 1710
8 | 2 | Equipment Rentals (For Utility) | EquipmentShare - Allocated to General (Due to Budget) | 3625.58 | 0 | 3625.58
8 | 2 | Equipment Rentals (For General) | EquipmentShare | 8917.11 | 0 | 8917.11
8 | 7 | Stucco Rough and Finish Labor | From VG Stucco - Second Invoice | 90000 | 9000 | 81000
8 | 7 | EFIS/Stone - Equipment | From Equipment Share | 5149.11 | 0 | 5149.11
8 | 9 | Model Room Labor and Material | Change Order - RFM Ventures | 13150 | 1315 | 11835
8 | 15 | HVAC/Mechanical Material and Labor | Third Invoice | 52000 | 5200 | 46800
8 | 16 | Electrical Rough In Labor | GMC Electric - Adjusted Balance (True Up From Prior Draw) | 16400 | 1640 | 14760
8 | 18 | Contractor's Fee | Boulder Construction - For May 2025 | 16666.6667 | 1666.6667 | 15000
9 | 1 | Notary Fees | For Draw | 10 | 0 | 10
9 | 1 | Jobsite Office - Recurring Rental | From Willscot | 817.83 | 0 | 817.83 | 10467
9 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 10466
9 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 10465
9 | 1 | Jobsite Storage Container - Rental + Drop Off | From Willscot | 1038.12 | 0 | 1038.12 | 10464
9 | 1 | Jobsite Storage Container - Rental + Drop Off | From Willscot | 1038.12 | 0 | 1038.12 | 10463
9 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 10462
9 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 10461
9 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 150.74 | 0 | 150.74 | 10460
9 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 150.74 | 0 | 150.74 | 10459
9 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 81.19 | 0 | 81.19 | 10458
9 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 225 | 0 | 225 | 10473
9 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 950 | 0 | 950 | 10474
9 | 1 | Cornerstone Safety | Per Ownership Requirements | 1500 | 0 | 1500 | 10493
9 | 1 | Jobsite Dumpster | From Waste Connections | 1720.9 | 0 | 1720.9 | 10469
9 | 1 | Misc. Jobsite Materials | From Home Depot - Bags, Paper Towels, Cleaner, Bucket | 77.27 | 0 | 77.27 | 10470
9 | 1 | Temporary Toilets - Recurring Payment | A-1 Little John | 260.88 | 0 | 260.88 | 10479
9 | 1 | Misc. Jobsite Materials | From Home Depot - Adjustable Table | 56.01 | 0 | 56.01 | 10480
9 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 135 | 0 | 135 | 10476
9 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 902.5 | 0 | 902.5 | 10477
9 | 1 | Jobsite Dumpster | From Waste Connections | 538 | 0 | 538 | 10503
9 | 1 | Jobsite Dumpster | From Waste Connections | 1198.66 | 0 | 1198.66 | 10509
9 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 10510
9 | 2 | Earthwork - SW3P | Cardinal Strategies | 375 | 0 | 375 | 10483
9 | 2 | Water Meter Usage | City of Waxahachie | 978.85 | 0 | 978.85 | 10507
9 | 6 | Framing Material | From Home Depot - Lumber | 5499.57 | 0 | 5499.57 | 10457
9 | 6 | Framing Material | From Home Depot - Hurricane Ties | 71.88 | 0 | 71.88 | 10471
9 | 6 | Framing Material | From Home Depot - Washers and Screws | 168.13 | 0 | 168.13 | 10472
9 | 6 | Framing Material | From Home Depot - Screws | 86.45 | 0 | 86.45 | 10478
9 | 6 | Framing Material | From Home Depot - Lumber | 1445.87 | 0 | 1445.87 | 10496
9 | 6 | Framing Material | From Home Depot - Zip Tape | 749.41 | 0 | 749.41 | 10497
9 | 6 | Framing Material | From Home Depot - Zip Tape | 440.36 | 0 | 440.36 | 10495
9 | 6 | Framing Material | From Home Depot - OSB Subfloor | 1476.7 | 0 | 1476.7 | 10502
9 | 6 | Framing Labor | For Reytex Framing Corporation - Invoice 28 | 17275 | 1725.5 | 15549.5 | 10511
9 | 6 | Framing Material | From Home Depot - RigidLam | 5129.91 | 0 | 5129.91 | 10512
9 | 6 | Framing Material | From Home Depot - Hurricane Ties | 522.85 | 0 | 522.85 | 10518
9 | 6 | Framing Material | From Home Depot - Lumber | 1801.97 | 0 | 1801.97 | 10519
9 | 6 | Truss Material - Dog Houses | From American Truss - Remaining Payment | 5405.4 | 0 | 5405.4 | 10450
9 | 16 | Electrical Material | Elliott Electric | 23592.05 | 0 | 23592.05 | 10481
9 | 16 | Electrical Material | Elliott Electric | 15728.03 | 0 | 15728.03 | 10484
9 | 16 | Electrical Material | Elliott Electric | 5158.98 | 0 | 5158.98 | 10485
9 | 16 | Electrical Material | Elliott Electric | 3109.45 | 0 | 3109.45 | 10486
9 | 16 | Electrical Material | Elliott Electric | 105.28 | 0 | 105.28 | 10487
9 | 16 | Electrical Material | Elliott Electric | 66.28 | 0 | 66.28 | 10491
9 | 16 | Electrical Material | Elliott Electric | 381.95 | 0 | 381.95 | 10492
9 | 16 | Electrical Material | Elliott Electric | 931.92 | 0 | 931.92 | 10468
9 | 16 | Electrical Material | Elliott Electric | 17403.24 | 0 | 17403.24 | 10498
9 | 16 | Electrical Material | Elliott Electric | 47953.64 | 0 | 47953.64 | 10499
9 | 16 | Electrical Material | Elliott Electric | 1106.59 | 0 | 1106.59 | 10500
9 | 16 | Electrical Material | Elliott Electric | 301.84 | 0 | 301.84 | 10501
9 | 16 | Electrical Material | Elliott Electric | 1050.72 | 0 | 1050.72 | 10508
9 | 16 | Electrical Material | Elliott Electric | 66.28 | 0 | 66.28 | 10525
9 | 16 | Electrical Material | Elliott Electric | 24708.06 | 0 | 24708.06 | 10521
9 | 1 | Job Supervisor | For June 2025 | 10000 | 0 | 10000
9 | 1 | Project Manager | Boulder Construction - For June 2025 | 3888.8889 | 0 | 3888.8889
9 | 1 | Job Accounting / Administration | Boulder Construction - For June 2025 | 3611.1111 | 0 | 3611.1111
9 | 2 | Equipment Rentals (For General) | EquipmentShare | 8910.79 | 0 | 8910.79 | [To Be Paid]
9 | 7 | EFIS/Stone - Equipment | From Triple A Stucco | 12384 | 1238.4 | 11145.6 | 10523
9 | 7 | Stucco Rough and Finish Labor | From VG Stucco - Basecoat, Stone & Stucco Finish | 104000 | 9307.53 | 94692.47 | [To Be Paid]
9 | 8 | Additional Deposit for Doors | For Ongoing Windows & Doors | 98376.6 | 0 | 98376.6 | [To Be Paid]
9 | 15 | VTAC Costs - Remaining Payment | From Greens Electric | 71598.73 | 0 | 71598.73 | [To Be Paid]
9 | 16 | Electrical Rough In Labor | GMC Electric | 27500 | 2750 | 24750 | 10522
9 | 16 | Electrical Material | Elliott Electric | 706.33 | 0 | 706.33 | 10526
9 | 16 | Electrical Material | Elliott Electric | 24058.56 | 0 | 24058.56 | 10527
9 | 18 | Contractor's Fee | Boulder Construction - For June 2025 | 16666.6667 | 1666.6667 | 15000 | NA
10 | 1 | Diesel for Equipment |  | 13.61 | 0 | 13.61 | [TBD]
10 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 10583
10 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 10584
10 | 1 | Misc. Jobsite Materials | From Home Depot - Paint/Canyew Panel/Dark Walnut | 131.6 | 0 | 131.6 | 10585
10 | 1 | Jobsite Office - Recurring Rental | From Willscot | 817.83 | 0 | 817.83 | 10560
10 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 10565
10 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 190.52 | 0 | 190.52 | 10563
10 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 190.52 | 0 | 190.52 | 10564
10 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 10566
10 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 150.74 | 0 | 150.74 | 10561
10 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 150.74 | 0 | 150.74 | 10562
10 | 1 | Temporary Toilets - Recurring Payment | From A-1 Little John | 684.14 | 0 | 684.14 | 10568
10 | 1 | Jobsite Dumpster | From Waste Connections | 1521.58 | 0 | 1521.58 | 10545
10 | 1 | Misc. Jobsite Materials | From Home Depot - Padlock | 62.09 | 0 | 62.09 | 10604
10 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 10605
10 | 1 | Notary Fees | For Draw | 10 | 0 | 10 | [TBD]
10 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 926.25 | 0 | 926.25 | 10548
10 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 210 | 0 | 210 | 10549
10 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 360 | 0 | 360 | 10550
10 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 973.75 | 0 | 973.75 | 10551
10 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 240 | 0 | 240 | 10552
10 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 760 | 0 | 760 | 10553
10 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 1211.25 | 0 | 1211.25 | 10579
10 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 555 | 0 | 555 | 10580
10 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 500 | 0 | 500 | 10597
10 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 641.25 | 0 | 641.25 | 10613
10 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 285 | 0 | 285 | 10612
10 | 1 | Jobsite Dumpster | From Waste Connections | 2059.58 | 0 | 2059.58 | 10610
10 | 2 | Earthwork - SW3P | Cardinal Strategies | 375 | 0 | 375 | 10590
10 | 3 | Import Dirt Material for Concrete | Alliance Trucking | 2625 | 0 | 2625 | 10558
10 | 6 | Framing Material | From Home Depot - Plastic Coated Framing Nails | 154.1 | 0 | 154.1 | 10571
10 | 6 | Framing Material | From Home Depot - Plastic Coated Framing Nails/Liquid Nails | 414.53 | 0 | 414.53 | 10574
10 | 6 | Framing Material | From Home Depot - Saw Blad/Dimensional Lumber | 79.07 | 0 | 79.07 | 10573
10 | 6 | Framing Material | From Home Depot - Utility Knife | 49.62 | 0 | 49.62 | 10572
10 | 6 | Framing Material | From Home Depot - Wood Dolly | 86.54 | 0 | 86.54 | 10586
10 | 6 | Framing Material | From Home Depot - Anchor/Hex Drive/Drill Bit/Cut Washer | 57.11 | 0 | 57.11 | 10559
10 | 6 | Framing Material | From Home Depot - Marking Paint for Trusses | 21.61 | 0 | 21.61 | 10567
10 | 6 | Framing Material | From Home Depot - Drill Bit/Screw/Dimensional Lumber | 217.21 | 0 | 217.21 | 10575
10 | 6 | Framing Material | From Home Depot - Dimensional Lumber/Spray Paint | 283.81 | 0 | 283.81 | 10576
10 | 6 | Framing Material | From Home Depot - Cedar Lumber/Wood Screw | 88.07 | 0 | 88.07 | 10546
10 | 6 | Framing Material | From Home Depot - Dimensional Lumber | 2305.64 | 0 | 2305.64 | 10542
10 | 6 | Framing Material | From Home Depot - OSB Subfloor | 22.56 | 0 | 22.56 | 10543
10 | 6 | Framing Material | From Lowe's | 167.33 | 0 | 167.33 | 10544
10 | 6 | Framing Labor | For Reytex Framing Corporation - Truss Change Order | 3500 | 0 | 3500 | 10555
10 | 6 | Framing Material | From Home Depot - Wood Screws & Lag Screws | 453.03 | 0 | 453.03 | 10598
10 | 6 | Framing Material | From Home Depot - Drywall Screws | 105.98 | 0 | 105.98 | 10599
10 | 6 | Framing Material | From Home Depot - Lag Screws | 87.28 | 0 | 87.28 | 10606
10 | 6 | Framing Labor | For Reytex Framing Corporation - Invoice 30 | 2610 | 261 | 2349 | 10594
10 | 6 | Framing Material | From Home Depot - Galvanized Joist Hanger | 64.08 | 0 | 64.08 | 10607
10 | 6 | Framing Material | From Home Depot - OSB Wall Sheathing | 346.51 | 0 | 346.51 | 10608
10 | 6 | Framing Material | From Home Depot - OSB Wall Sheathing & Ratcheting Suspension | 627.88 | 0 | 627.88 | 10609
10 | 6 | Framing Material | From Harbor Freight | 397.23 | 0 | 397.23 | [TBD]
10 | 16 | Electrical Material | Elliott Electric | 3678.71 | 0 | 3678.71 | 10528
10 | 16 | Electrical Material | Elliott Electric | 292.4 | 0 | 292.4 | 10529
10 | 16 | Electrical Material | Elliott Electric | 322.82 | 0 | 322.82 | 10530
10 | 16 | Electrical Material | Elliott Electric | 124.73 | 0 | 124.73 | 10531
10 | 16 | Electrical Material | Elliott Electric | 649.5 | 0 | 649.5 | 10532
10 | 16 | Electrical Material | Elliott Electric | 649.5 | 0 | 649.5 | 10533
10 | 16 | Electrical Material | Elliott Electric | 579.84 | 0 | 579.84 | 10534
10 | 16 | Electrical Material | Elliott Electric | -649.5 | 0 | -649.5 | 10535
10 | 16 | Electrical Material | Elliott Electric | -649.5 | 0 | -649.5 | 10536
10 | 16 | Electrical Material | Elliott Electric | 25584.55 | 0 | 25584.55 | 10537
10 | 16 | Electrical Material | Elliott Electric | 1277.35 | 0 | 1277.35 | 10538
10 | 16 | Electrical Material | Elliott Electric | 337.56 | 0 | 337.56 | 10539
10 | 16 | Electrical Material | Elliott Electric | 640.07 | 0 | 640.07 | 10540
10 | 16 | Electrical Material | Elliott Electric | 49.67 | 0 | 49.67 | 10600
10 | 16 | Electrical Material | Elliott Electric | 5758.82 | 0 | 5758.82 | 10601
10 | 16 | Electrical Material | Elliott Electric | 162.38 | 0 | 162.38 | 10602
10 | 16 | Electrical Material | Elliott Electric | 59.13 | 0 | 59.13 | 10603
10 | 16 | Electrical Material | Elliott Electric | 1202.93 | 0 | 1202.93 | 10611
10 | 2 | Equipment Rentals (For General) | EquipmentShare | 10962.19 | 0 | 10962.19 | [To Be Paid]
10 | 3 | Flume, Sidewalk and CO | From MD Bowles Construction - Pay App 09 | 33080 | 1168 | 31912 | [To Be Paid]
10 | 6 | Framing and Trusses Labor | From RFM Ventures | 15680 | 1568 | 14112 | [To Be Paid]
10 | 7 | Stucco/Stone Material | From VG Stucco - Pay App 04 | 95816.15 | 4900 | 90916.15 | [To Be Paid]
10 | 7 | EFIS/Stone - Equipment | From EquipmentShare | 10537.64 | 0 | 10537.64 | [To Be Paid]
10 | 8 | Windows Installation | From GW Glass Construction | 12000 | 0 | 12000 | 10596
10 | 12 | Swimming Pool Labor and Material | From San Diego Pool's and Shotcrete - Pay App 01 | 76560 | 7656 | 68904 | [To Be Paid]
10 | 15 | HVAC/Mechanical Material and Labor | From Iceberg Heating & AC - Pay App 04 | 100000 | 10000 | 90000 | [To Be Paid]
10 | 15 | VTAC Grilles | From Greens Electric | 18932.93 | 0 | 18932.93 | [To Be Paid]
10 | 16 | Electrical Rough In Labor and Unit Feeders | GMC Electric - Pay App 05 | 34000 | 3400 | 30600 | [To Be Paid]
11 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 240 | 0 | 240 | 10659
11 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 380 | 0 | 380 | 10660
11 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 300 | 0 | 300 | 10661
11 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 760 | 0 | 760 | 10662
11 | 1 | Fence Gate Relocation & Addition | From Viking Fence Co | 745.57 | 0 | 745.57 | 10671
11 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 10630
11 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 10631
11 | 1 | Notary Fees | For Draw | 13.39 | 0 | 13.39 | 10651
11 | 1 | Notary Fees | For Draw | 13.39 | 0 | 13.39 | 10652
11 | 1 | Misc. Jobsite Materials | From Home Depot - Pliers | 41.97 | 0 | 41.97 | 10653
11 | 1 | Jobsite Office - Recurring Rental | From Willscot | 817.83 | 0 | 817.83 | 10632
11 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 10635
11 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 190.52 | 0 | 190.52 | 10637
11 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 190.52 | 0 | 190.52 | 10638
11 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 10636
11 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 150.74 | 0 | 150.74 | 10633
11 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 150.74 | 0 | 150.74 | 10634
11 | 1 | Security Cameras | Birdseye Surveillance | 1515.5 | 0 | 1515.5 | 10629
11 | 1 | Temporary Toilets - Recurring Payment | A-1 Little John | 521.77 | 0 | 521.77 | 10641
11 | 1 | Labor & Gas for Generators | From J&S7 Consulting | 410.74 | 0 | 410.74 | 10670
11 | 1 | Misc. Jobsite Materials | From Home Depot - Multi-Surface Primer, Sealer, and Stain Blocker | 21.63 | 0 | 21.63 | 10658
11 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 10682
11 | 1 | Jobsite Dumpster | From Waste Connections | 1521.58 | 0 | 1521.58 | 10681
11 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 420 | 0 | 420 | 10691
11 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 570 | 0 | 570 | 10692
11 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 973.75 | 0 | 973.75 | 10693
11 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 330 | 0 | 330 | 10694
11 | 1 | Security Cameras | Birdseye Surveillance | 1515.5 | 0 | 1515.5 | 10709
11 | 1 | Security Cameras | Birdseye Surveillance | 1515.5 | 0 | 1515.5 | 10710
11 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 10711
11 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 10712
11 | 1 | Cornerstone Safety | Per Ownership Requirements | 1500 | 0 | 1500 | 10663
11 | 1 | Cornerstone Safety | Per Ownership Requirements | 1500 | 0 | 1500 | 10664
11 | 1 | Misc. Jobsite Materials | From Home Depot - Bucket | 124.6 | 0 | 124.6 | 10570
11 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 330 | 0 | 330 | 10714
11 | 1 | Labor & Gas for Generators | From J&S7 Consulting | 312.21 | 0 | 312.21 | 10715
11 | 1 | Monthly Plan Printing Expense | From Great America Financial Services | 1035.14 | 0 | 1035.14 | [TBD]
11 | 1 | Monthly Plan Printing Expense | From Great America Financial Services | 665.18 | 0 | 665.18 | [TBD]
11 | 1 | Monthly Plan Printing Expense | From Great America Financial Services | 302.35 | 0 | 302.35 | [TBD]
11 | 1 | Monthly Plan Printing Expense | From Great America Financial Services | 302.35 | 0 | 302.35 | [TBD]
11 | 1 | Monthly Plan Printing Expense | From Great America Financial Services | 332.59 | 0 | 332.59 | [TBD]
11 | 1 | Misc. Wire and ACH Fees for RIW - True Up | From Austin Bank for Wires and ACH | 1212.8 | 0 | 1212.8 | NA
11 | 1 | Bank Fees for Checks | From Austin Bank for Checks | 112.82 | 0 | 112.82 | NA
11 | 1 | Misc. Jobsite Office Expenses (Computer, etc.) | From Micro Center | 1674.52 | 0 | 1674.52 | NA
11 | 1 | Misc. Jobsite Office Expenses (Radios) | From Rapid Radios | 699 | 0 | 699 | NA
11 | 1 | OpenSpace - Camera Accessories | Testing and Inspection Services - Monitoring | 200.29 | 0 | 200.29 | NA
11 | 1 | Cellular Data & WiFi for Jobsite Office - True Up | From Google Fi | 1427.16 | 0 | 1427.16 | NA
11 | 2 | Inlet Protection | From White Cap | 255.23 | 0 | 255.23 | 10628
11 | 2 | Water Meter Usage | City of Waxahachie | 321.36 | 0 | 321.36 | 10669
11 | 2 | Water Meter Usage | City of Waxahachie | 246.31 | 0 | 246.31 | 10639
11 | 3 | Staking Sidewalk, Flume, & Light Poles | AIM Construction Services | 1400 | 0 | 1400 | 10668
11 | 6 | Framing Material | From Home Depot - Washers | 43.75 | 0 | 43.75 | 10689
11 | 6 | Framing Material | From Home Depot - Loose Lumber | 3604.86 | 0 | 3604.86 | 10690
11 | 6 | Framing Material | From Home Depot - Loose Lumber | 4059.6 | 0 | 4059.6 | 10683
11 | 6 | Framing Material | From Home Depot - Hex Nut, Washers, and Threaded Rods | 315.58 | 0 | 315.58 | 10684
11 | 6 | Framing Material | From Home Depot - Simpson Hold Downs | 4367.94 | 0 | 4367.94 | 10685
11 | 6 | Framing Material | From Home Depot - Washers | 291.41 | 0 | 291.41 | 10686
11 | 6 | Framing Material | From Home Depot - Loose Lumber | 2151.4 | 0 | 2151.4 | 10687
11 | 6 | Framing Material | From Home Depot - Sheathing and Loose Lumber | 3064.86 | 0 | 3064.86 | 10623
11 | 6 | Framing Material | From Home Depot - Galvanized Nuts | 903.62 | 0 | 903.62 | 10624
11 | 6 | Framing Material | From Home Depot - Loose Lumber | 243.13 | 0 | 243.13 | 10626
11 | 6 | Framing Labor | For Reytex Framing Corporation - Invoice 32 | 1700 | 170 | 1530 | 10665
11 | 6 | Framing Material | For Reytex Framing Corporation - Material Reimbursement | 350 | 0 | 350 | 10667
11 | 6 | Framing Material | From Home Depot - Zip Tape | 440.36 | 0 | 440.36 | 10654
11 | 6 | Framing Material | From Home Depot - Framing Nails | 133.36 | 0 | 133.36 | 10656
11 | 6 | Framing Material | From Home Depot - Zip Tape | 440.36 | 0 | 440.36 | 10655
11 | 6 | Framing Labor - Hardware | For Martin Aguilar | 3000 | 0 | 3000 | 10680
11 | 6 | Framing Material | From Home Depot - Liquid Nails | 1047.9 | 0 | 1047.9 | 10569
11 | 6 | Framing Material | From Home Depot - LVL and Hold Downs | 2576.56 | 0 | 2576.56 | 10688
11 | 6 | Framing Material | From Home Depot - LVL and Hold Downs (Refund) | -1389.44 | 0 | -1389.44 | 10688
11 | 6 | Framing Labor | For Reytex Framing Corporation - Invoice 33 | 3508 | 350.98 | 3157.02 | 10666
11 | 6 | Framing Material | From Home Depot - OSB Subfloor | 1360.11 | 0 | 1360.11 | 10713
11 | 6 | Framing Material | From Home Depot - OSB Subfloor | -1360.11 | 0 | -1360.11 | 10713
11 | 6 | Framing Material | From Home Depot - OSB Subfloor | 1360.11 | 0 | 1360.11 | 10713
11 | 6 | Framing Material | From Home Depot - Dimensional Lumber/Flashing Tape/Wall & Roof Panel | 2379.3 | 0 | 2379.3 | 10725
11 | 7 | Stucco/Stone Material | From Silicone Specialities - Pay App 05 | -0.01 | 0 | -0.01 | 10717
11 | 7 | Stucco/Stone Material | From Silicone Specialities - Pay App 05 | 1103.07 | 0 | 1103.07 | 10716
11 | 7 | Stucco/Stone Material | From Red River Brick - Pay App 05 | 3478.07 | 0 | 3478.07 | 10724
11 | 10 | Hook, Bars, Rods, Seats, Glass Shelf, Toilet Holder | From JMHS - Bathroom Scope 50% Deposit - RIWTX-102 | 18423.79 | 0 | 18423.79 | 10679
11 | 10 | Shower Surrounds | From JMHS - Bathroom Scope 50% Deposit - RIWTX-102 | 2009.89 | 0 | 2009.89 | 10679
11 | 11 | Undermount Vanity Sink | From JMHS - Bathroom Scope 50% Deposit - RIWTX-102 | 2428.92 | 0 | 2428.92 | 10679
11 | 11 | Fixed Glass Shower Panel and Hinge Shower Door | From JMHS - Bathroom Scope 50% Deposit - RIWTX-102 | 7859.16 | 0 | 7859.16 | 10679
11 | 16 | Oncor Easement | From Traverse Land Surveying | 703.63 | 0 | 703.63 | 10657
11 | 16 | Electrical Material | From Elliott Electric | 554.78 | 0 | 554.78 | 10642
11 | 16 | Electrical Material | From Elliott Electric | 39.08 | 0 | 39.08 | 10650
11 | 16 | Electrical Material | From Elliott Electric | 785.87 | 0 | 785.87 | 10646
11 | 16 | Electrical Material | From Elliott Electric | 279.05 | 0 | 279.05 | 10645
11 | 16 | Electrical Material | From Elliott Electric | 16.75 | 0 | 16.75 | 10643
11 | 16 | Electrical Material | From Elliott Electric | -18.46 | 0 | -18.46 | 10644
11 | 16 | Electrical Material | From Elliott Electric | 561.95 | 0 | 561.95 | 10647
11 | 16 | Electrical Material | From Elliott Electric | 104.48 | 0 | 104.48 | 10648
11 | 16 | Electrical Material | From Elliott Electric | 91.87 | 0 | 91.87 | 10649
11 | 16 | Electrical Material | From Elliott Electric | 843.96 | 0 | 843.96 | 10695
11 | 16 | Electrical Material | From Elliott Electric | 107.25 | 0 | 107.25 | 10696
11 | 16 | Electrical Material | From Elliott Electric | 1404 | 0 | 1404 | 10697
11 | 16 | Electrical Material | From Elliott Electric | 875.4 | 0 | 875.4 | 10698
11 | 16 | Electrical Material | From Elliott Electric | 505.24 | 0 | 505.24 | 10699
11 | 16 | Electrical Material | From Elliott Electric | 11.28 | 0 | 11.28 | 10700
11 | 16 | Electrical Material | From Elliott Electric | 5224.82 | 0 | 5224.82 | 10701
11 | 16 | Electrical Material | From Elliott Electric | 210.35 | 0 | 210.35 | 10702
11 | 16 | Electrical Material | From Elliott Electric | 164.78 | 0 | 164.78 | 10703
11 | 16 | Electrical Material | From Elliott Electric | 149.43 | 0 | 149.43 | 10704
11 | 16 | Electrical Material | From Elliott Electric | 148.65 | 0 | 148.65 | 10705
11 | 16 | Electrical Material | From Elliott Electric | 119.71 | 0 | 119.71 | 10706
11 | 16 | Electrical Material | From Elliott Electric | 2513.56 | 0 | 2513.56 | 10707
11 | 16 | Electrical Material | From Elliott Electric | 820.32 | 0 | 820.32 | 10708
11 | 16 | Electrical Material | From Elliott Electric | 21575.08 | 0 | 21575.08 | 10720
11 | 16 | Electrical Material | From Elliott Electric | 84.63 | 0 | 84.63 | 10721
11 | 16 | Electrical Material | From Elliott Electric | 10180.26 | 0 | 10180.26 | 10722
11 | 16 | Electrical Material | From Elliott Electric | 162.39 | 0 | 162.39 | 10723
11 | 1 | Job Supervisor | For July 2025 | 10000 | 0 | 10000 | [To Be Paid]
11 | 1 | Project Manager | Boulder Construction - For July 2025 | 3888.8889 | 0 | 3888.8889 | [To Be Paid]
11 | 1 | Job Accounting / Administration | Boulder Construction - For July 2025 | 3611.1111 | 0 | 3611.1111 | [To Be Paid]
11 | 2 | Equipment Rentals (For General) | EquipmentShare | 9030.42 | 0 | 9030.42 | 10727
11 | 7 | EFIS/Stone - Equipment | EquipmentShare | 2574.55 | 0 | 2574.55 | 10726
11 | 7 | Second Invoice - Change Orders | From LED Roofing | 47100 | 4710 | 42390 | 10729
11 | 7 | Stucco/Stone Material | From VG Stucco - Pay App 05 | 47366 | 4736.6 | 42629.4 | 10730
11 | 14 | Fire Sprinkler Rough and Stand Pipe | From Safe Life FP (Invoice 03) - Split | 107000 | 10700 | 96300 | 10731
11 | 14 | Fire Sprinkler - Change Order | From Safe Life FP (Invoice 03) - Split | 35000 | 3500 | 31500 | 10731
11 | 16 | Equipment Rentals (For Electrical) | EquipmentShare | 1982.35 | 0 | 1982.35 | 10728
11 | 16 | Fire Sprinkler - Change Order | From Safe Life FP (Invoice 03) - Split | 53000 | 5300 | 47700 | 10731
11 | 18 | Contractor's Fee | Boulder Construction - For July 2025 | 16666.6667 | 1666.6667 | 15000 | NA
12 | 1 | Jobsite Office - Recurring Rental | From Willscot | 817.83 | 0 | 817.83 | 10767
12 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 10768
12 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 190.52 | 0 | 190.52 | 10769
12 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 190.52 | 0 | 190.52 | 10770
12 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 10771
12 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 10772
12 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 150.74 | 0 | 150.74 | 10773
12 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 150.74 | 0 | 150.74 | 10774
12 | 1 | Temporary Toilets - Recurring Payment | A-1 Little John | 521.77 | 0 | 521.77 | 10778
12 | 1 | Notary Fees | For Draw | 10 | 0 | 10 | 10779
12 | 1 | Jobsite Dumpster | From Waste Connections | 1521.58 | 0 | 1521.58 | 10780
12 | 1 | Misc. Jobsite Materials | From Home Depot - Sprayer, Saftey Vest, Combo Lock, Refill and Hard Hat | 307.42 | 0 | 307.42 | 10789
12 | 1 | Misc. Jobsite Materials | From Home Depot - Black Diamond Trimmer Line | 25.3 | 0 | 25.3 | 10791
12 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 10806
12 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 10807
12 | 1 | Misc. Jobsite Materials | From Home Depot - Caution Sign | 14.99 | 0 | 14.99 | 10810
12 | 1 | Diesel for Equipment | From Racetrac | 27.08 | 0 | 27.08 | [TBD]
12 | 1 | Misc. Jobsite Expenses (Softwares, etc.) | From Docusign | 300 | 0 | 300 | [TBD]
12 | 1 | Misc. Jobsite Expenses (Softwares, etc.) - True Up | From Togal | 1263 | 0 | 1263 | [TBD]
12 | 1 | Misc. Jobsite Expenses (Softwares, etc.) | From Loom | 180 | 0 | 180 | [TBD]
12 | 1 | Misc. Jobsite Expenses (Softwares, etc.) - True Up | From Lydul | 186 | 0 | 186 | [TBD]
12 | 1 | Cellular Data & WiFi for Jobsite Office | From Google Fi | 3.19 | 0 | 3.19 | [TBD]
12 | 1 | Diesel for Generator | From Sunoco Gas | 12.18 | 0 | 12.18 | [TBD]
12 | 1 | Diesel for Generator | From Circle K | 31.59 | 0 | 31.59 | [TBD]
12 | 1 | Diesel for Generator | From Circle K | 28.27 | 0 | 28.27 | [TBD]
12 | 1 | Residence Backpack | From Amazon | 69.26 | 0 | 69.26 | [TBD]
12 | 1 | Residence Backpack | From Amazon | 108.22 | 0 | 108.22 | [TBD]
12 | 1 | Residence Backpack | From Amazon | 35.71 | 0 | 35.71 | [TBD]
12 | 1 | Cellular Data & WiFi for Jobsite Office | From AT&T | 37.11 | 0 | 37.11 | [TBD]
12 | 1 | Cellular Data & WiFi for Jobsite Office - True Up | From AT&T | 308.904 | 0 | 308.904 | [TBD]
12 | 1 | Misc. Jobsite Expenses (Softwares, etc.) | Takeoffs, Scheduling / Forecasting, Punch Lists, etc. - True Up | 2948.85 | 0 | 2948.85 | [TBD]
12 | 2 | Earthwork - SW3P | Cardinal Strategies | 375 | 0 | 375 | 10775
12 | 2 | Earthwork - SW3P | Cardinal Strategies | 375 | 0 | 375 | 10792
12 | 2 | Water Hose for Water Meter | From Stuart Hose & Pipe | 1243.18 | 0 | 1243.18 | [TBD]
12 | 2 | Inlet Protection | From White Cap | 34.31 | 0 | 34.31 | [TBD]
12 | 2 | Utilities - Misc. Material | From Home Depot - Plastic Utility Pump | 128.82 | 0 | 128.82 | 10786
12 | 3 | Concrete and Density Testing | Geoscience Engineers | 1222 | 0 | 1222 | 10776
12 | 3 | Quikcrete Concrete Mix | From Home Depot - Concrete Mix | 17.47 | 0 | 17.47 | 10790
12 | 6 | Framing Labor - Hardware | For Martin Aguilar | 8550 | 0 | 8550 | 10802
12 | 6 | Framing Labor - Misc. Punch List | For Martin Aguilar | 13436.9 | 0 | 13436.9 | 10803
12 | 6 | Travel for Truss Engineer - Inspection | From Expedia | 417.97 | 0 | 417.97 | [TBD]
12 | 6 | Travel for Truss Engineer - Inspection | From Expedia | 34.11 | 0 | 34.11 | [TBD]
12 | 6 | Travel for Truss Engineer - Inspection | From Expedia | 201.4 | 0 | 201.4 | [TBD]
12 | 6 | Framing Material | From Home Depot - OSB Subfloor & Dimensional Lumber | 738.52 | 0 | 738.52 | 10808
12 | 6 | Framing Material | From Home Depot - Ratchet & Screws | 916.78 | 0 | 916.78 | 10809
12 | 6 | Framing Material | From Home Depot - Zinc & Galvanized Screws | 405.1 | 0 | 405.1 | 10811
12 | 6 | Framing Material | From Home Depot - Galvanized Washer | 85.19 | 0 | 85.19 | 10830
12 | 6 | Framing Material | From Home Depot - Galvanised Hex Nut, Carriage Bolt, Drill Bit, Washer | 271.51 | 0 | 271.51 | 10782
12 | 6 | Framing Material | From Home Depot - Sheathing Panel | 1653.28 | 0 | 1653.28 | 10783
12 | 6 | Framing Material | From Home Depot - Southern Yellow Pine Dimensional Lumber | 321.77 | 0 | 321.77 | 10784
12 | 6 | Framing Material | From Home Depot - Adhesive, Retrofit Bolt, Standoff Post and Post Cap | 749.21 | 0 | 749.21 | 10785
12 | 6 | Framing Material | From Home Depot - Exterior Wall Sheathing | 135.31 | 0 | 135.31 | 10787
12 | 6 | Framing Material | From Home Depot - Pressure Treated Timber Wood Post and Lumber | 622.81 | 0 | 622.81 | 10788
12 | 6 | Framing Material | From Home Depot - Loose Lumber Refund | -1863.84 | 0 | -1863.84 | 10687
12 | 6 | Millwork 50% Deposit | From Graniti Vicentia LLC | 52002.26 | 0 | 52002.26 | 10857
12 | 6 | Framing Labor - Misc. Punch List | For Martin Aguilar | 4450 | 0 | 4450 | 10858
12 | 7 | Stucco/Stone Material | From Silicone Specialities - Pay App 06 | 753.42 | 0 | 753.42 | 10777
12 | 7 | Insulation for Ceiling / Interior Wall / Corridor | RFM Ventures - Third Invoice (First Payment) | 33333.3333 | 3333.3333 | 30000 | 10847 | Pay App needs to be revised upward by $500 before Docusign. Actual Retainage Amount for Past Draw is $34,335 instead of $33,835.
12 | 7 | Labor & Gas for Generators | From J&S7 Consulting | 1083.0733 | 0 | 1083.0733 | 10833
12 | 8 | Windows Installation | From GW Glass Construction | 12000 | 0 | 12000 | 10855
12 | 8 | Windows Installation | From GW Glass Construction | 8200 | 0 | 8200 | 10856
12 | 9 | Drywall Material | From Home Depot - Drywall Screws & Tape | 161.75 | 0 | 161.75 | 10812
12 | 9 | Drywall Material | From Home Depot - Knife, Tape, Pan, etc. | 198.23 | 0 | 198.23 | 10813
12 | 9 | Drywall Material | From Home Depot - Drywall Joint Tape | 85.36 | 0 | 85.36 | 10814
12 | 9 | Drywall Material | From Home Depot - Tarp, Knife, Shear & Tin Snip | 537.8 | 0 | 537.8 | 10815
12 | 9 | Labor for Sheetrocking Elevator | From JG AU Drywall | 4200 | 0 | 4200 | 10841
12 | 15 | Mechanical Equipment | From Trane - Iceberg Heating & Ac | 69612.22 | 6961.22 | 62651 | 10854
12 | 15 | Jobsite Labor | Clean Up & Other Misc. Tasks | 855 | 0 | 855 | 10794
12 | 15 | Jobsite Labor | Clean Up & Other Misc. Tasks | 150 | 0 | 150 | 10795
12 | 15 | Jobsite Labor | Clean Up & Other Misc. Tasks | 1068.75 | 0 | 1068.75 | 10796
12 | 15 | Jobsite Labor | Clean Up & Other Misc. Tasks | 681.25 | 0 | 681.25 | 10797
12 | 15 | Jobsite Labor | Clean Up & Other Misc. Tasks | 465 | 0 | 465 | 10798
12 | 15 | Jobsite Labor | Clean Up & Other Misc. Tasks | 405 | 0 | 405 | 10799
12 | 15 | Jobsite Labor | Clean Up & Other Misc. Tasks | 405 | 0 | 405 | 10800
12 | 15 | Jobsite Labor | Clean Up & Other Misc. Tasks | 1045 | 0 | 1045 | 10834
12 | 15 | Jobsite Labor | Clean Up & Other Misc. Tasks | 712.5 | 0 | 712.5 | 10835
12 | 15 | Jobsite Labor | Clean Up & Other Misc. Tasks | 1500 | 0 | 1500 | 10839
12 | 15 | Jobsite Labor | Clean Up & Other Misc. Tasks | 315 | 0 | 315 | 10852
12 | 15 | Jobsite Labor | Clean Up & Other Misc. Tasks | 641.25 | 0 | 641.25 | 10853
12 | 15 | Labor & Gas for Generators | From J&S7 Consulting | 1083.0733 | 0 | 1083.0733 | 10833
12 | 16 | Electrical Material | Elliott Electric | 2259.56 | 0 | 2259.56 | 10732
12 | 16 | Electrical Material | Elliott Electric | 907.52 | 0 | 907.52 | 10733
12 | 16 | Electrical Material | Elliott Electric | 3006.12 | 0 | 3006.12 | 10734
12 | 16 | Electrical Material | Elliott Electric | 607.3 | 0 | 607.3 | 10735
12 | 16 | Electrical Material | Elliott Electric | 607.26 | 0 | 607.26 | 10736
12 | 16 | Electrical Material | Elliott Electric | 215.96 | 0 | 215.96 | 10737
12 | 16 | Electrical Material | Elliott Electric | 41.2 | 0 | 41.2 | 10738
12 | 16 | Electrical Material | Elliott Electric | 4.81 | 0 | 4.81 | 10739
12 | 16 | Electrical Material | Elliott Electric - Return | -640.05 | 0 | -640.05 | 10740
12 | 16 | Electrical Material | Elliott Electric - Return | -1267.89 | 0 | -1267.89 | 10741
12 | 16 | Electrical Material | Elliott Electric | 10.99 | 0 | 10.99 | 10742
12 | 16 | Electrical Material | Elliott Electric | 28.49 | 0 | 28.49 | 10743
12 | 16 | Electrical Material | Elliott Electric | 1669.52 | 0 | 1669.52 | 10744
12 | 16 | Electrical Material | Elliott Electric | 63.33 | 0 | 63.33 | 10745
12 | 16 | Electrical Material | Elliott Electric | 1461.38 | 0 | 1461.38 | 10746
12 | 16 | Electrical Material | Elliott Electric | 171.16 | 0 | 171.16 | 10747
12 | 16 | Electrical Material | Elliott Electric | 1007.43 | 0 | 1007.43 | 10748
12 | 16 | Electrical Material | Elliott Electric | 1217.25 | 0 | 1217.25 | 10749
12 | 16 | Electrical Material | Elliott Electric | 2027.07 | 0 | 2027.07 | 10750
12 | 16 | Electrical Material | Elliott Electric | 1231.86 | 0 | 1231.86 | 10751
12 | 16 | Electrical Material | Elliott Electric | 1456.31 | 0 | 1456.31 | 10752
12 | 16 | Electrical Material | Elliott Electric | 308.32 | 0 | 308.32 | 10753
12 | 16 | Electrical Material | Elliott Electric | 27.82 | 0 | 27.82 | 10754
12 | 16 | Electrical Material | Elliott Electric | 38688.38 | 0 | 38688.38 | 10755
12 | 16 | Electrical Material | Elliott Electric | 1727.37 | 0 | 1727.37 | 10756
12 | 16 | Electrical Material | Elliott Electric | 1061.9 | 0 | 1061.9 | 10757
12 | 16 | Electrical Material | Elliott Electric | 170.3 | 0 | 170.3 | 10758
12 | 16 | Electrical Material | Elliott Electric | 78.16 | 0 | 78.16 | 10759
12 | 16 | Electrical Material | Elliott Electric | 66.01 | 0 | 66.01 | 10760
12 | 16 | Electrical Material | Elliott Electric | 40.33 | 0 | 40.33 | 10761
12 | 16 | Electrical Material | Elliott Electric | 363.55 | 0 | 363.55 | 10762
12 | 16 | Electrical Material | Elliott Electric | 1016.46 | 0 | 1016.46 | 10763
12 | 16 | Electrical Material | Elliott Electric | 54.67 | 0 | 54.67 | 10766
12 | 16 | Electrical Material | Elliott Electric | 292.28 | 0 | 292.28 | 10816
12 | 16 | Electrical Material | Elliott Electric | 23.99 | 0 | 23.99 | 10817
12 | 16 | Electrical Material | Elliott Electric | 14.2 | 0 | 14.2 | 10818
12 | 16 | Electrical Material | Elliott Electric | 2196.07 | 0 | 2196.07 | 10819
12 | 16 | Electrical Material | From GMC Electric | 5500 | 550 | 4950 | 10836
12 | 16 | Labor & Gas for Generators | From J&S7 Consulting | 1083.0733 | 0 | 1083.0733 | 10833
12 | 1 | Job Supervisor | For August 2025 | 10000 | 0 | 10000 | NA
12 | 1 | Project Manager | Boulder Construction - For August 2025 | 3888.8889 | 0 | 3888.8889 | NA
12 | 1 | Job Accounting / Administration | Boulder Construction - For August 2025 | 3611.1111 | 0 | 3611.1111 | NA
12 | 2 | Equipment Rentals (For General) | EquipmentShare | 8886.04 | 0 | 8886.04 | 10851
12 | 7 | Stucco/Stone Material | From VG Stucco - Pay App 06 | 16171.81 | 1532.251 | 14639.559 | 10848
12 | 7 | Insulation for Ceiling / Interior Wall / Corridor | RFM Ventures - Third Invoice (Final Payment) | 16666.6667 | 1666.6667 | 15000 | 10847 | Pay App needs to be revised upward by $500 before Docusign. Actual Retainage Amount for Past Draw is $34,335 instead of $33,835.
12 | 7 | EFIS/Stone - Equipment | EquipmentShare | 2574.55 | 0 | 2574.55 | 10849
12 | 9 | RC Channel & Sheetrocking for Walls, Celing, Corridor | RFM Ventures - Third Invoice (Final Payment) | 118000 | 11800 | 106200 | 10847 | Pay App needs to be revised upward by $500 before Docusign. Actual Retainage Amount for Past Draw is $34,335 instead of $33,835.
12 | 13 | Elevator Material & Installation Labor | From Kone | 134936.07 | 17830.407 | 117105.663 | 10846 | Pay App needs to be revised upward by $3,000 before Docusign. Actual Gross Amount for Past Draw is $80,848 instead of $70,848.
12 | 16 | Equipment Rentals (For Electrical) | EquipmentShare | 2028.98 | 0 | 2028.98 | 10850
12 | 18 | Contractor's Fee | Boulder Construction - For August 2025 | 16666.6667 | 1666.6667 | 15000 | NA
13 | 1 | Cornerstone Safety | Per Ownership Requirements | 1500 | 0 | 1500 | 10793
13 | 1 | Jobsite Dumpster | From Waste Connections | 1521.58 | 0 | 1521.58 | 10832
13 | 1 | Jobsite Office - Recurring Rental | From Willscot | 817.83 | 0 | 817.83 | 10859
13 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 10860
13 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 190.52 | 0 | 190.52 | 10861
13 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 190.52 | 0 | 190.52 | 10862
13 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 10863
13 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 172.33 | 0 | 172.33 | 10864
13 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 172.33 | 0 | 172.33 | 10865
13 | 1 | Jobsite Dumpster | From Waste Connections | 1521.58 | 0 | 1521.58 | 10870
13 | 1 | Jobsite Dumpster | From Waste Connections | 538 | 0 | 538 | 10871
13 | 1 | Notary Fees | For Draw | 10 | 0 | 10 | 10872
13 | 1 | Temporary Toilets - Recurring Payment | A-1 Little John | 521.77 | 0 | 521.77 | 10873
13 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 10875
13 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 10876
13 | 1 | Misc. Jobsite Materials | From Home Depot - Ripstop, Permanent Marker & Spray Paint | 32.33 | 0 | 32.33 | 10877
13 | 1 | Jobsite Dumpster | From Waste Connections | 1521.58 | 0 | 1521.58 | 10879
13 | 1 | Misc. Jobsite Expenses | Takeoffs, Scheduling / Forecasting, Punch Lists, etc. - True Up | 1385.92 | 0 | 1385.92 | Various
13 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 1068.75 | 0 | 1068.75 | 10881
13 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 1068.75 | 0 | 1068.75 | 10882
13 | 1 | Misc. Jobsite Materials | From Home Depot - Lock, Gloves, Clean-Up Bags, Safety Vest, Tow Chains | 540.3 | 0 | 540.3 | 10885
13 | 1 | Misc. Jobsite Materials | From Home Depot - Master Lock, Staple & Door Hinge | 63.17 | 0 | 63.17 | 10886
13 | 1 | Misc. Jobsite Expenses | From J&S7 Consulting | 460.73 | 0 | 460.73 | 10889
13 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 160 | 0 | 160 | 10894
13 | 1 | Monthly Plan Printing Expense | From Great America Financial Services | 634.94 | 0 | 634.94 | 10896
13 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 10924
13 | 1 | Jobsite Labor | Clean Up & Other Misc. Tasks | 1068.75 | 0 | 1068.75 | 10937
13 | 1 | Fuel | From Interstate | 136.67 | 0 | 136.67 | [TBD]
13 | 1 | Lunch | From Interstate | 18.25 | 0 | 18.25 | [TBD]
13 | 1 | Lunch | From Interstate | 19.49 | 0 | 19.49 | [TBD]
13 | 1 | Hydration | From N Highway | 26.11 | 0 | 26.11 | [TBD]
13 | 1 | Hydration | From N Highway | 35.29 | 0 | 35.29 | [TBD]
13 | 1 | Cellular Data & WiFi for Jobsite Office - True Up | From AT&T | 719.44 | 0 | 719.44 | [TBD]
13 | 1 | Misc. Jobsite Expenses | From Plaud | 215.99 | 0 | 215.99 | [TBD]
13 | 1 | Gas/Fuel/Travel Expenses - True Up | Meals/Gas/Fuel/Travel Expenses - True Up | 1094.01 | 0 | 1094.01 | Various
13 | 2 | Water Meter Usage | From City of Waxahachie | 440.22 | 0 | 440.22 | 10831
13 | 2 | Water Meter Usage | From City of Waxahachie | 248.78 | 0 | 248.78 | 10895
13 | 2 | Earthwork - SW3P | Cardinal Strategies | 375 | 0 | 375 | 10888
13 | 3 | Concrete Mix | From Home Depot | 81.53 | 0 | 81.53 | 10866
13 | 3 | Concrete - Surveyor to Stake Out Paving | For AIM CS Inc | 700 | 0 | 700 | 10880
13 | 6 | Framing Labor - Hardware | For Martin Aguilar | 7145 | 0 | 7145 | 10890
13 | 6 | Framing Labor - Hardware | For Martin Aguilar | 2000 | 0 | 2000 | 10891
13 | 6 | Framing Material | From Harbor Freight - Ladders | 649.46 | 0 | 649.46 | 10925
13 | 6 | Framing Material | From Harbor Freight - Safety Stand, Wrench, Screws | 247.83 | 0 | 247.83 | 10926
13 | 6 | Framing Material | From Home Depot - OSB Subfloor and Pine Dimensional Lumber | 516.89 | 0 | 516.89 | 10867
13 | 6 | Framing Material | From Home Depot - Framing Nails & Dimensional Lumber | 253.06 | 0 | 253.06 | 10868
13 | 6 | Framing Material | From Home Depot - Dimensional Lumber | 2273.94 | 0 | 2273.94 | 10869
13 | 6 | Framing Material | From Home Depot - Galvanized Bolts, Standoff Post Base and Adhesive | 121.8 | 0 | 121.8 | 10874
13 | 6 | Framing Material | From Home Depot - OSB Subfloor | 617.35 | 0 | 617.35 | 10878
13 | 6 | Framing Material | From Home Depot - Washer & Hex Nut | 161.54 | 0 | 161.54 | 10887
13 | 6 | Framing Log + Verification | For Truss and Framing Corrections | 1500 | 0 | 1500 | 10837
13 | 7 | Insulation Inspection | Geoscience Engineers | 342 | 0 | 342 | 10829
13 | 16 | Electrical Material | Elliott Electric | 78246.35 | 0 | 78246.35 | 10930
13 | 16 | Electrical Material | From GMC Electric | 11000 | 1100 | 9900 | 10893
13 | 17 | Equipment Insurance | Liberty Mutual | 170.23 | 0 | 170.23 | [TBD]
13 | 1 | Job Supervisor | For September 2025 | 10000 | 0 | 10000 | NA
13 | 1 | Project Manager | Boulder Construction - For September 2025 | 3888.8889 | 0 | 3888.8889 | NA
13 | 1 | Job Accounting / Administration | Boulder Construction - For September 2025 | 3611.1111 | 0 | 3611.1111 | NA
13 | 2 | Equipment Rentals (For General) | EquipmentShare | 11583.68 | 0 | 11583.68 | 10933
13 | 2 | Elevator Generator - Equipment | EquipmentShare | 6305.66 | 0 | 6305.66 | 10936
13 | 3 | Concrete - Equipment | EquipmentShare | 1200.32 | 0 | 1200.32 | 10934
13 | 7 | Final Invoice | From LED Roofing | 100000 | 10000 | 90000 | 10927
13 | 7 | Insulation for Floor 4 | RFM Ventures - Fourth Invoice | 25000 | 2500 | 22500 | 10932
13 | 7 | EFIS/Stone - Equipment | EquipmentShare | 2574.55 | 0 | 2574.55 | 10935
13 | 9 | RC Channel & Sheetrock for Floor 4 | RFM Ventures - Fourth Invoice | 59000 | 5900 | 53100 | 10932
13 | 9 | Texture & Tape/Bed/Sand for Floors 2/3 | RFM Ventures - Fourth Invoice | 42000 | 4200 | 37800 | 10932
13 | 12 | Elevator Material & Installation Labor | From Kone - Allocated Payment (Pay App 05) | 1294.7 | 129.47 | 1165.23 | 10929
13 | 13 | Elevator Material & Installation Labor | From Kone - Allocated Payment (Pay App 05) | 42415.93 | 4241.593 | 38174.337 | 10929
13 | 15 | HVAC/Mechanical Material and Labor | From Iceberg Heating & AC - Pay App 05 (Final Payment) | 23000 | 2300 | 20700 | 10931
13 | 18 | Contractor's Fee | Boulder Construction - For September 2025 | 16666.6667 | 1666.6667 | 15000 | NA
14 | 1 | Jobsite Office - Recurring Rental | From Willscot | 921.75 | 0 | 921.75 | 10939
14 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 10940
14 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 190.52 | 0 | 190.52 | 10941
14 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 190.52 | 0 | 190.52 | 10942
14 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 10943
14 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 172.33 | 0 | 172.33 | 10944
14 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 172.33 | 0 | 172.33 | 10945
14 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 10946
14 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 10947
14 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 10948
14 | 1 | Jobsite Office - Recurring Rental | From Willscot | 921.75 | 0 | 921.75 | 10949
14 | 1 | Jobsite Dumpster | From Waste Connections | 1521.58 | 0 | 1521.58 | 10950
14 | 1 | Jobsite Dumpster | From Waste Connections | 1521.58 | 0 | 1521.58 | 10951
14 | 1 | Jobsite Dumpster | From Waste Connections | 1696.89 | 0 | 1696.89 | 10952
14 | 1 | Notary Fees | For Draw | 10 | 0 | 10 | 10872
14 | 1 | Temporary Toilets - Recurring Payment | A-1 Little John | 521.77 | 0 | 521.77 | 10954
14 | 1 | Security Cameras | Birdseye Surveillance | 1515.5 | 0 | 1515.5 | 10955
14 | 1 | Security Cameras | Birdseye Surveillance | 1515.5 | 0 | 1515.5 | 10956
14 | 1 | Temporary Toilets - Recurring Payment | A-1 Little John | 521.77 | 0 | 521.77 | 11000
14 | 1 | Misc. Jobsite Expenses | From J&S7 Consulting | 1325.69 | 0 | 1325.69 | 11006
14 | 1 | OpenSpace - Subscription | Testing and Inspection Services - Monitoring | 6156.15 | 0 | 6156.15 | 11013
14 | 1 | Temporary Toilets - Recurring Payment | A-1 Little John | 521.77 | 0 | 521.77 | 11014
14 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 11016
14 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 190.52 | 0 | 190.52 | 11017
14 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 190.52 | 0 | 190.52 | 11018
14 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 11019
14 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 172.33 | 0 | 172.33 | 11020
14 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 172.33 | 0 | 172.33 | 11021
14 | 1 | Jobsite Dumpster | From Waste Connections | 1521.58 | 0 | 1521.58 | 11023
14 | 1 | Cornerstone Safety | Per Ownership Requirements | 1500 | 0 | 1500 | 11025
14 | 1 | Cornerstone Safety | Per Ownership Requirements | 1500 | 0 | 1500 | 11026
14 | 1 | Cornerstone Safety | Per Ownership Requirements | 1500 | 0 | 1500 | 11027
14 | 1 | Cornerstone Safety | Per Ownership Requirements | 1500 | 0 | 1500 | 11028
14 | 1 | Meals | From Ohana | 39.5 | 0 | 39.5 | [TBD]
14 | 1 | Fuel | From Exxon | 115.61 | 0 | 115.61 | [TBD]
14 | 1 | Fuel | From [200S Interstate] | 121.22 | 0 | 121.22 | [TBD]
14 | 1 | Misc. Jobsite Materials | From Plaud | 129.594 | 0 | 129.594 | [TBD]
14 | 1 | Cellular Data & WiFi for Jobsite Office | From AT&T | 37.11 | 0 | 37.11 | [TBD]
14 | 1 | Cellular Data & WiFi for Jobsite Office - True Up | From AT&T | 22.266 | 0 | 22.266 | [TBD]
14 | 1 | Misc. Jobsite Expenses (Softwares, etc.) - True Up | Takeoffs, Scheduling / Forecasting, Punch Lists, etc. | 1155.67 | 0 | 1155.67 | [TBD]
14 | 1 | Cellular Data & WiFi for Jobsite Office | From Google Fi | 537.72 | 0 | 537.72 | [TBD]
14 | 2 | Earthwork - SW3P | Cardinal Strategies | 375 | 0 | 375 | 11003
14 | 2 | Import Dirt Material | From Alliance Trucking | 2340 | 0 | 2340 | 10998
14 | 2 | Misc. Jobsite Materials | From Home Depot - Coat Welded Wire, Metal T-Post & Clips & Post Driver | 491.1 | 0 | 491.1 | 11033
14 | 2 | Jobsite Equipment | From Harbor Freight | 413.46 | 0 | 413.46 | [TBD]
14 | 3 | Quikcrete Concrete Mix | From Home Depot | 174.72 | 0 | 174.72 | 10959
14 | 3 | Quikcrete Concrete Mix | From Home Depot | 99.01 | 0 | 99.01 | 10960
14 | 3 | Misc. Jobsite Materials | From Home Depot - Degreaser Concrete Pressure Wash & Concrete | 15.67 | 0 | 15.67 | 10961
14 | 3 | Bore for PVC | From Alpha Directional Drilling | 4500 | 0 | 4500 | 10996
14 | 3 | Elevator Concrete Work | From POR Construction | 300 | 0 | 300 | 11005
14 | 3 | Concrete & Masonry Waterproofer | From Lowe's | 477.21 | 0 | 477.21 | 11015
14 | 3 | Misc. Jobsite Materials | From Home Depot - Aerosol Liquid Rubber Sealant Coating | 389.18 | 0 | 389.18 | 11034
14 | 3 | Misc. Jobsite Materials | From Home Depot - Waterproof Patch and Seal Tape Black, Insect Repellent | 43.75 | 0 | 43.75 | 11036
14 | 3 | Misc. Jobsite Materials | From Home Depot - Window and Door Sealant Clear | 321.92 | 0 | 321.92 | 11039
14 | 6 | Framing Material | From Home Depot - Shackle, Slide Lock & Zinc Thread | 127.97 | 0 | 127.97 | 10957
14 | 6 | Framing Material | From Home Depot -Simpson Epoxy Adhesive & Retro-Fit Bolt | 3281.06 | 0 | 3281.06 | 10978
14 | 6 | Framing Material | From Home Depot -Simpson Epoxy Adhesive & Retro-Fit Bolt Refund | -2137.94 | 0 | -2137.94 | 10978
14 | 6 | Framing Material | From Home Depot - Dimensional Lumber | 203.85 | 0 | 203.85 | 10981
14 | 6 | Framing Material | From Home Depot - Dimensional Lumber | 596.28 | 0 | 596.28 | 10984
14 | 6 | Framing Labor - Hardware | For Martin Aguilar | 2150 | 0 | 2150 | 11009
14 | 6 | Framing Labor - Misc. Punch List | For Martin Aguilar | 3695 | 0 | 3695 | 11010
14 | 6 | Framing Material | From Home Depot - Exterior Wall Sheathing | 1053.27 | 0 | 1053.27 | 11030
14 | 6 | Framing Material | From Home Depot - Dimensional Lumber | 586.5 | 0 | 586.5 | 11031
14 | 6 | Framing Material | From Home Depot - Galvanized Screw | 124.3 | 0 | 124.3 | 11037
14 | 7 | EFIS Payment - Change Order for Stone Columns | From VG Stucco - Pay App 07 (First Payment) | 5000 | 500 | 4500 | 11061
14 | 7 | EFIS Payment | From VG Stucco - Pay App 07 (Final Payment) | 25000 | 0 | 25000 | 11061
14 | 8 | Windows Fixes | From Bryant Construction | 11474.5 | 0 | 11474.5 | 10997
14 | 8 | Doors Material | From Home Depot - Commercial Grade with Ball Bearing & Butt Door Hinge | 51.57 | 0 | 51.57 | 11041
14 | 9 | Painting Material | From Home Depot - Interior Primer | 6321.8 | 0 | 6321.8 | 10958
14 | 9 | Paint Brush, Extension Cord, Waterproofer & Floor Fan | From Home Depot | 176.08 | 0 | 176.08 | 10962
14 | 9 | Interior Primer | From Home Depot | 6321.8 | 0 | 6321.8 | 10963
14 | 9 | Paint Brush & Waterproofer | From Home Depot | 39.45 | 0 | 39.45 | 10964
14 | 9 | Tile Leveling Clip and Cutters, Diamond Blade & Adhesive | From Home Depot | 616.65 | 0 | 616.65 | 10965
14 | 9 | Tile Leveling Clip, Rim Blade with Mesh & Thinset Mortar | From Home Depot | 549.13 | 0 | 549.13 | 10966
14 | 9 | Tile Leveling Clip & Contractor Bags | From Home Depot | 304.89 | 0 | 304.89 | 10967
14 | 9 | Thinset Mortar | From Home Depot | 256.62 | 0 | 256.62 | 10968
14 | 9 | Tile Leveling Clip, Lubricant Spray & Thinset Mortar | From Home Depot | 531.43 | 0 | 531.43 | 10969
14 | 9 | Thinset Mortar | From Home Depot | 498.98 | 0 | 498.98 | 10970
14 | 9 | Aluminium Reducer Tile Edging Trim | From Home Depot | 98.78 | 0 | 98.78 | 10971
14 | 9 | Aluminium Reducer Tile Edging Trim Refund | From Home Depot | -98.78 | 0 | -98.78 | 10971
14 | 9 | Flooring Material | From Home Depot - All Surface Construction Adhesive | 636.92 | 0 | 636.92 | 10972
14 | 9 | Thinset Mortar & Contractor Bags | From Home Depot | 232.03 | 0 | 232.03 | 10973
14 | 9 | Flooring Material | From Home Depot - Silicone Caulk & Gun, Diamond Blade, Painter's Towels | 612.85 | 0 | 612.85 | 10974
14 | 9 | Drywall Material | From Home Depot - Drywall Screw | 22.98 | 0 | 22.98 | 10975
14 | 9 | Flooring Material | From Home Depot - Premium Tile Diamond Blade | 68.55 | 0 | 68.55 | 10976
14 | 9 | Thinset Mortar | From Home Depot | 498.98 | 0 | 498.98 | 10977
14 | 9 | Flooring Material | From Home Depot - All Surface Construction Adhesive | 454.93 | 0 | 454.93 | 10980
14 | 9 | Liquid Nails, Thinset Mortar, Tile Leveling Stems & Caps | From Home Depot | 1868.5 | 0 | 1868.5 | 10982
14 | 9 | Flooring Labor | TKG Construction | 27180 | 0 | 27180 | 11004
14 | 9 | Flooring Material | From Home Depot - Heavy Duty Temporary Floor Protection | 913.68 | 0 | 913.68 | 11029
14 | 9 | Thinset Mortar | From Home Depot | 498.98 | 0 | 498.98 | 11038
14 | 9 | Painting Material | From Home Depot - Bi-Metal Hole Saw and Multi-Use Painter's Tape | 264.56 | 0 | 264.56 | 11040
14 | 9 | Self-Leveling Underlayment & Thinset Mortar | From Home Depot | 379.47 | 0 | 379.47 | 11042
14 | 9 | Self-Leveling Underlayment & Spray Foam Sealant | From Home Depot | 502.97 | 0 | 502.97 | 11043
14 | 9 | Flooring Material | From Floor & Décor | 1297.7 | 0 | 1297.7 | [TBD]
14 | 9 | Flooring Material | From Floor & Décor | 91.23 | 0 | 91.23 | [TBD]
14 | 9 | Flooring Material | From Floor & Décor | -64.89 | 0 | -64.89 | [TBD]
14 | 9 | Flooring Material | From Floor & Décor | 345.23 | 0 | 345.23 | [TBD]
14 | 9 | Paint Material | From PPG Paints | 9672.95 | 0 | 9672.95 | [TBD]
14 | 9 | Flooring Labor | TKG Construction Final Payment | 30000 | 3000 | 27000 | 11004
14 | 10 | Shower Surrounds | From JMHS - Bathroom Scope Remaining 50% Payment - RIWTX-102 | 2009.89 | 0 | 2009.89 | 10679
14 | 10 | Hook, Bars, Rods, Seats, Glass Shelf, Toilet Holder | From JMHS - Bathroom Scope Remaining 50% Payment - RIWTX-102 | 18423.79 | 0 | 18423.79 | 10679
14 | 10 | Fire Extinguisher Cabinets | From Texas Fire Extinguishers | 553.25 | 0 | 553.25 | 11022
14 | 11 | Undermount Vanity Sink | From JMHS - Bathroom Scope Remaining 50% Payment - RIWTX-102 | 2428.92 | 0 | 2428.92 | 10679
14 | 11 | Fixed Glass Shower Panel and Hinge Shower Door | From JMHS - Bathroom Scope Remaining 50% Payment - RIWTX-102 | 8029.14 | 0 | 8029.14 | 10679
14 | 11 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 405 | 0 | 405 | 10883
14 | 11 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 615 | 0 | 615 | 10884
14 | 11 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 630 | 0 | 630 | 10938
14 | 11 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 585 | 0 | 585 | 10985
14 | 11 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 375 | 0 | 375 | 10986
14 | 11 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 510 | 0 | 510 | 10987
14 | 11 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 615 | 0 | 615 | 10988
14 | 11 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 660 | 0 | 660 | 10989
14 | 11 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 1045 | 0 | 1045 | 10990
14 | 11 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 1068.75 | 0 | 1068.75 | 10991
14 | 11 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 760 | 0 | 760 | 10992
14 | 11 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 1068.75 | 0 | 1068.75 | 10993
14 | 11 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 1068.75 | 0 | 1068.75 | 10994
14 | 11 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 1065 | 0 | 1065 | 11011
14 | 11 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 1686.25 | 0 | 1686.25 | 11012
14 | 15 | Plumbing Material | From Home Depot - Utility Pump & Tethered Switch | 400.47 | 0 | 400.47 | 11032
14 | 15 | Plumbing Material | From Home Depot - HP Plastic Utlity Pump | 107.17 | 0 | 107.17 | 11035
14 | 16 | Electrical Labor | From GMC Electric | 11800 | 1180 | 10620 | 10995
14 | 16 | Electrical Material | From Elliott Electrical | 93000.01 | 0 | 93000.01 | 11053
14 | 17 | Equipment Insurance | Liberty Mutual | 170.23 | 0 | 170.23 | [TBD]
14 | 17 | Builder's Risk Insurance | Newman & Trucker | 9698.76 | 0 | 9698.76 | [TBD]
14 | 17 | Builder's Risk Insurance | Liberty Mutual | 3454.07 | 0 | 3454.07 | [TBD]
14 | 1 | Job Supervisor | For October 2025 | 10000 | 0 | 10000 | NA
14 | 1 | Project Manager | Boulder Construction - For October 2025 | 3888.8889 | 0 | 3888.8889 | NA
14 | 1 | Job Accounting / Administration | Boulder Construction - For October 2025 | 3611.1111 | 0 | 3611.1111 | NA
14 | 2 | Equipment Rentals (For General) | From EquipmentShare | 10182.47 | 0 | 10182.47 | 11057
14 | 3 | Gypcrete | From Kent Companies | 69000 | 6900 | 62100 | 11059
14 | 7 | Insulation for Floor 1 | From RFM Ventures - Pay App 06 | 12500 | 1250 | 11250 | 11050
14 | 7 | EFIS/Stone - Equipment | From EquipmentShare | 2574.55 | 0 | 2574.55 | 11055
14 | 9 | RC Channel & Sheetrock for Floor 1 | From RFM Ventures - Pay App 06 | 59000 | 5900 | 53100 | 11050
14 | 9 | Texture & Tape/Bed/Sand for Floors 1 to 4 | From RFM Ventures - Pay App 06 | 66000 | 6600 | 59400 | 11050
14 | 9 | Coat Heavy Primer 2 Coat Paint Floors 1 to 4 | From RFM Ventures - Pay App 06 | 90000 | 9000 | 81000 | 11050
14 | 9 | ACT 2 Draws Floors 1 to 4 | From RFM Ventures - Pay App 06 | 44000 | 4400 | 39600 | 11050
14 | 10 | Kitchen Equipment |  | 150000 | 0 | 150000 | NA
14 | 10 | Laundry Equipment |  | 100000 | 0 | 100000 | NA
14 | 12 | Elevator - Equipment | From EquipmentShare | 6496.1 | 0 | 6496.1 | 11056
14 | 13 | Elevator - Equipment | From EquipmentShare | 6496.1 | 0 | 6496.1 | 11056
14 | 13 | Elevator - Equipment | From EquipmentShare | -6496.1 | 0 | -6496.1 | 11056
14 | 15 | HVAC/Mechanical Material and Labor | From Iceberg Heating & AC - Pay App 06 | 551.36 | 0 | 551.36 | 11058
14 | 15 | HVAC/Mechanical Material and Labor | From Iceberg Heating & AC - Pay App 06 | 344.3 | 0 | 344.3 | 11058
14 | 15 | HVAC/Mechanical Material and Labor | From Iceberg Heating & AC - Pay App 06 | 2252.18 | 0 | 2252.18 | 11058
14 | 15 | HVAC/Mechanical Material and Labor | From Iceberg Heating & AC - Pay App 06 | 58.4 | 0 | 58.4 | 11058
14 | 15 | HVAC/Mechanical Material and Labor | From Iceberg Heating & AC - Pay App 06 | 151.72 | 0 | 151.72 | 11058
14 | 15 | HVAC/Mechanical Material and Labor | From Iceberg Heating & AC - Pay App 06 | 2001.8 | 0 | 2001.8 | 11058
14 | 15 | HVAC/Mechanical Material and Labor | From Iceberg Heating & AC - Pay App 06 | 1251.46 | 0 | 1251.46 | 11058
14 | 15 | HVAC/Mechanical Material and Labor | From Iceberg Heating & AC - Pay App 06 | 1388.78 | 800 | 588.78 | 11058
14 | 16 | Electrical Labor | From GMC Electric | 30750 | 3075 | 27675 | 11060
14 | 16 | Electrical - Equipment | From EquipmentShare | 4742.58 | 0 | 4742.58 | 11054
14 | 18 | Contractor's Fee | Boulder Construction - For October 2025 | 16666.6667 | 1666.6667 | 15000 | NA
15 | 1 | Notary Fees | For Draw | 10 | 0 | 10 | 11063
15 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 11066
15 | 1 | Jobsite Material Expenses | From Home Depot - Rust-Oleum Stops Rust 5 in 1 Custom Spray | 32.39 | 0 | 32.39 | 11070
15 | 1 | Jobsite Dumpster | From Waste Connections | 1521.58 | 0 | 1521.58 | 11073
15 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 11077
15 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 11078
15 | 1 | Jobsite Office - Recurring Rental | From Willscot | 921.75 | 0 | 921.75 | 11079
15 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 11080
15 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 190.52 | 0 | 190.52 | 11081
15 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 190.52 | 0 | 190.52 | 11082
15 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 11083
15 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 172.33 | 0 | 172.33 | 11084
15 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 172.33 | 0 | 172.33 | 11085
15 | 1 | Jobsite Storage Container - Recurring Rental | From Willscott | 1038.12 | 0 | 1038.12 | 11086
15 | 1 | Jobsite Storage Container - Recurring Rental | From Willscott | 187.27 | 0 | 187.27 | 11087
15 | 1 | Jobsite Dumpster | From Waste Connections | 1521.58 | 0 | 1521.58 | 11088
15 | 1 | Jobsite Dumpster | From Waste Connections | 1613.43 | 0 | 1613.43 | 11089
15 | 1 | Jobsite Material Expenses | From Home Depot - Washer Head Drill-Point Screw & Padlock with Key | 60.65 | 0 | 60.65 | 11096
15 | 1 | Temporary Toilets - Recurring Payment | A-1 Little John | 521.77 | 0 | 521.77 | 11097
15 | 1 | Jobsite Material Expenses | From Home Depot - Contractor Bags | 64.89 | 0 | 64.89 | 11106
15 | 1 | Jobsite Material Expenses | From Home Depot - Black Large Chisel Tip Jobsite Permanent Marker | 21.01 | 0 | 21.01 | 11119
15 | 1 | Blueprint Printing | Stewart Engineering | 277.66 | 0 | 277.66 | 11142
15 | 1 | Monthly Plan Printing Expense | From Great America Financial Services | 1108.25 | 0 | 1108.25 | 11151
15 | 1 | Temporary Toilets - Recurring Payment | A-1 Little John | 521.77 | 0 | 521.77 | 11154
15 | 1 | Misc. Jobsite Expenses | From J&S7 Consulting | 1586.97 | 0 | 1586.97 | 11159
15 | 1 | Jobsite Dumpster | From Waste Connections | 2105.22 | 0 | 2105.22 | 11165
15 | 1 | Jobsite Storage Container - Recurring Rental | From Willscott | 187.27 | 0 | 187.27 | 11175
15 | 1 | Jobsite Storage Container - Recurring Rental | From Willscott | 187.27 | 0 | 187.27 | 11176
15 | 1 | Jobsite Material Expenses | From Home Depot - Vacuum with Filter, Hose and Accessories | 108.23 | 0 | 108.23 | 11178
15 | 1 | Jobsite Dumpster | From Waste Connections | 1052.61 | 0 | 1052.61 | 11185
15 | 1 | Jobsite Dumpster | From Waste Connections | 491.79 | 0 | 491.79 | 11186
15 | 1 | Jobsite Material Expenses | From Home Depot - Contractor Bags | 64.89 | 0 | 64.89 | 11189
15 | 1 | Jobsite Office - Recurring Rental | From Willscott | 921.75 | 0 | 921.75 | 11190
15 | 1 | Jobsite Storage Container - Recurring Rental | From Willscott | 214.06 | 0 | 214.06 | 11197
15 | 1 | Jobsite Storage Container - Recurring Rental | From Willscott | 214.06 | 0 | 214.06 | 11199
15 | 1 | Jobsite Storage Container - Recurring Rental | From Willscott | 190.52 | 0 | 190.52 | 11200
15 | 1 | Jobsite Storage Container - Recurring Rental | From Willscott | 190.52 | 0 | 190.52 | 11201
15 | 1 | Jobsite Storage Container - Recurring Rental | From Willscott | 172.33 | 0 | 172.33 | 11202
15 | 1 | Jobsite Storage Container - Recurring Rental | From Willscott | 172.33 | 0 | 172.33 | 11203
15 | 1 | Temporary Toilets - Recurring Payment | From A-1 Little John | 521.77 | 0 | 521.77 | 11204
15 | 1 | Jobsite Storage Container - Recurring Rental | From Willscott | 190.52 | 0 | 190.52 | 11210
15 | 1 | Jobsite Dumpster | From Waste Connections | 2105.22 | 0 | 2105.22 | 11215
15 | 1 | Fuel | From Lovers | 126.64 | 0 | 126.64 | [TBD]
15 | 1 | Fuel | From Texaco | 13.45 | 0 | 13.45 | [TBD]
15 | 1 | Fuel | From Interstate | 10.47 | 0 | 10.47 | [TBD]
15 | 1 | Fuel | From Racetrac | 35.51 | 0 | 35.51 | [TBD]
15 | 1 | Fuel | From Racetrac | 24.9 | 0 | 24.9 | [TBD]
15 | 1 | Fuel | From QT | 19.68 | 0 | 19.68 | [TBD]
15 | 1 | Fuel | From Circle K | 18.34 | 0 | 18.34 | [TBD]
15 | 1 | Diesel for Equipment | Job Supervisor | 1000 | 0 | 1000 | [TBD]
15 | 1 | Meal | From Dairy Queen | 19.06 | 0 | 19.06 | [TBD]
15 | 1 | Fuel | From N Highway | 92.95 | 0 | 92.95 | [TBD]
15 | 1 | Fuel | From Exxon | 25.48 | 0 | 25.48 | [TBD]
15 | 1 | Notary Fees | For Draw | 10 | 0 | 10 | [TBD]
15 | 1 | Fuel/Vehicle | From Take 5 | 325.12 | 0 | 325.12 | [TBD]
15 | 1 | Misc. Jobsite Expenses (Softwares, etc.) - True Up | Takeoffs, Scheduling / Forecasting, Punch Lists, etc. | 2123.79 | 0 | 2123.79 | [TBD]
15 | 1 | Cellular Data & WiFi for Jobsite Office | From Google Fi | 269.16 | 0 | 269.16 | [TBD]
15 | 1 | Cellular Data & WiFi for Jobsite Office | From AT&T | 1470.87 | 0 | 1470.87 | [TBD]
15 | 1 | Misc. Jobsite Expenses | From Google One | 10.65 | 0 | 10.65 | [TBD]
15 | 1 | Misc. Jobsite Expenses | From Google One | 10.65 | 0 | 10.65 | [TBD]
15 | 1 | Misc. Jobsite Expenses | From S P Plaud | 179 | 0 | 179 | [TBD]
15 | 1 | Misc. Jobsite Expenses | From S P Plaud | 169 | 0 | 169 | [TBD]
15 | 1 | Monthly Plan Printing Expense | From Great America Financial Services | 302.35 | 0 | 302.35 | [TBD]
15 | 1 | Monthly Plan Printing Expense | From Great America Financial Services | 1108.25 | 0 | 1108.25 | [TBD]
15 | 1 | Misc. Wire and ACH Fees for RIW | From Austin Bank for Wires and ACH | 766.3 | 0 | 766.3 | NA
15 | 2 | Earthwork - SW3P | Cardinal Strategies | 375 | 0 | 375 | 11062
15 | 2 | Utility Material | From Britton Meter Supply | 902.81 | 0 | 902.81 | 11207
15 | 2 | Utility Labor | From MA Williams Plumbing - Partial Adjusted in Prior Forecast | 3477.4556 | 347.7456 | 3129.71 | 11222
15 | 3 | Concrete Material | From Home Depot - Black Large Chisel Tip Jobsite Permanent Marker | 21.01 | 0 | 21.01 | 11045
15 | 3 | Concrete Material | From Home Depot - Rotary Hammer & Carbide Drill Bit | 505.35 | 0 | 505.35 | 11071
15 | 3 | Concrete Material | From Home Depot - Turbo Diamond Blade & Diamond Grit | 61.31 | 0 | 61.31 | 11072
15 | 6 | Framing Material | From Home Depot - Dimensional Lumber | 274.74 | 0 | 274.74 | 11100
15 | 6 | Framing Material | From Home Depot - Prime KD Whitewood Stud & Sheathing Material | 325.56 | 0 | 325.56 | 11104
15 | 6 | Framing Material | From Home Depot - Thread Coated Exterior Wood Screws & Cutting Tool-Kit | 128.37 | 0 | 128.37 | 11105
15 | 6 | Framing Material | From Home Depot - Standard Grade Dimensional Lumber | 2084.98 | 0 | 2084.98 | 11109
15 | 6 | Framing Material | From Home Depot - Southern Yellow Pine Lumber | 869.12 | 0 | 869.12 | 11110
15 | 6 | Framing Material | From Home Depot - Glue Collated Straight Finish Nails | 100.46 | 0 | 100.46 | 11111
15 | 6 | Framing Material | From Home Depot - Sheathing Material & Heavy Duty Glove | 211.09 | 0 | 211.09 | 11118
15 | 6 | Framing Labor - Misc. Punch List | For Martin Aguilar | 7200 | 0 | 7200 | 11137
15 | 6 | Framing Labor - Misc. Punch List | For Martin Aguilar | 7000 | 0 | 7000 | 11138
15 | 6 | Framing Labor - Misc. Punch List | For Martin Aguilar | 800 | 0 | 800 | 11157
15 | 6 | Framing Labor - Misc. Punch List | For Martin Aguilar | 600 | 0 | 600 | 11221
15 | 7 | EFIS | From VG Stucco | 5000 | 500 | 4500 | 11139
15 | 7 | EFIS | From VG Stucco | 5000 | 500 | 4500 | 11145
15 | 7 | EIFS Mesh, Dryvit Sandblast & Adhesive, Portland Cement | From Silicone Specialities Inc | 2302.48 | 0 | 2302.48 | 11150
15 | 7 | EFIS | From VG Stucco | 5000 | 500 | 4500 | 11158
15 | 7 | EFIS | From VG Stucco | 5000 | 500 | 4500 | 11211
15 | 8 | Windows Installation Labor | From GW Glass Construction | 7000 | 0 | 7000 | 11098
15 | 8 | Doors and Hardware | From WB Doors | 3415.29 | 0 | 3415.29 | 11161
15 | 8 | Doors and Hardware | From Home Depot - Flush Right Hand Inswing Steel Prehung Front Door | 231.81 | 0 | 231.81 | 11187
15 | 9 | Flooring Material | From Home Depot - Polymer-Modified Thinset Mortar | 427.7 | 0 | 427.7 | 11048
15 | 9 | Flooring Material | From Home Depot - Original Multi-Use Painter's Tape | 37.61 | 0 | 37.61 | 11064
15 | 9 | Flooring Material | From Home Depot - High Density Painters Plastic Sheeting & Multi-Use Painter Tape | 384.42 | 0 | 384.42 | 11065
15 | 9 | Flooring Material | From Home Depot - Cement Backerboard & Polymer-Modified Thinset Mortar | 292.09 | 0 | 292.09 | 11067
15 | 9 | Drywall Material | From Home Depot - Drywall Screws & Exterior Wood Screws | 75.18 | 0 | 75.18 | 11069
15 | 9 | Flooring Material | From Home Depot - Board Surface Protector Paper & Heavy Duty Tape | 236.89 | 0 | 236.89 | 11075
15 | 9 | Flooring Material | From Home Depot - Polymer-Modified Thinset Mortar | 213.85 | 0 | 213.85 | 11092
15 | 9 | Flooring Material | From Home Depot - Diamond Grit Grout Removal Multi-Tool Blade | 57.74 | 0 | 57.74 | 11094
15 | 9 | Carpet Installation | From Home Depot - Self-Adhesive Film & Carpet Protection Self Adhesive Film | 926.64 | 0 | 926.64 | 11099
15 | 9 | Carpet Installation | From Home Depot - Self-Adhesive Film | 1338.19 | 0 | 1338.19 | 11102
15 | 9 | Carpet Installation | From Home Depot - Self-Adhesive Film | 1147.02 | 0 | 1147.02 | 11103
15 | 9 | Drywall Material | From Home Depot - Black Forced Air Kerosene/Diesel Outdoor Space Heater with Thermostat | 1181.83 | 0 | 1181.83 | 11114
15 | 9 | Carpet Installation | From Home Depot - Self-Adhesive Film | 955.85 | 0 | 955.85 | 11120
15 | 9 | Flooring Labor | From TKG Construction | 35000 | 0 | 35000 | 11140
15 | 9 | Drywall Material | From Home Depot - Drywall Anchors, Drywall Screws, Steel Screwdriving Bit | 173.71 | 0 | 173.71 | 11168
15 | 9 | Carpet Installation | From Home Depot - Construction Adhesive, Bi-Metal Hole Saw & Tape | 260.79 | 0 | 260.79 | 11174
15 | 9 | Drywall Material | From Home Depot - Drywall Anchors & Microfiber Spin Mop | 220.55 | 0 | 220.55 | 11188
15 | 9 | RC Channel & Sheetrock for Floor 1 | From RFM Ventures - Pay App 06 (First Payment) | 19000 | 1900 | 17100 | 11155
15 | 9 | Texture & Tape/Bed/Sand for Floor 1 | From RFM Ventures - Pay App 06 (First Payment) | 12000 | 1200 | 10800 | 11155
15 | 9 | Paint for Floor 1 | From RFM Ventures - Pay App 06 (First Payment) | 13000 | 1300 | 11700 | 11155
15 | 9 | Vinyl for Floors 1 to 4 | From RFM Ventures - Pay App 06 (First Payment) | 35194.44 | 3519.44 | 31675 | 11155
15 | 10 | Misc. Shower/Surround Install Material | From Home Depot - Kitchen & Bath Sealant Clear & Furring Strip Board | 400.31 | 0 | 400.31 | 11068
15 | 10 | Misc. Shower/Surround Install Material | From Home Depot - Window, Door, Kitchen & Bath Sealant White, Acetone | 1154.25 | 0 | 1154.25 | 11090
15 | 10 | Misc. Shower/Surround Install Material | From Home Depot - Window, Door, Kitchen & Bath Sealant White & Liquid Nails | 877.11 | 0 | 877.11 | 11091
15 | 10 | Misc. Shower/Surround Install Material | From Home Depot - Acetone, Furring Strip Board & Heavy Duty Nitrile | 68.75 | 0 | 68.75 | 11093
15 | 10 | Misc. Shower/Surround Install Material | From Home Depot - Kitchen and Bath Sealant White & Finish Nails | 232.28 | 0 | 232.28 | 11095
15 | 10 | Misc. Shower/Surround Install Material | From Home Depot - Window & Door Sealant White and Hardwood Blade | 145.32 | 0 | 145.32 | 11101
15 | 10 | Misc. Shower/Surround Install Material | From Home Depot - Window, Door, Kitchen & Bath Sealant White, Acetone | 378.49 | 0 | 378.49 | 11107
15 | 10 | Misc. Shower/Surround Install Material | From Home Depot - Kitchen and Bath Sealant White | 772.91 | 0 | 772.91 | 11108
15 | 10 | Misc. Shower/Surround Install Material | From Home Depot - Furring Strip Board & Multi-Purpose Terry Towel | 36.58 | 0 | 36.58 | 11112
15 | 10 | Misc. Shower/Surround Install Material | From Home Depot - Urine Remover Spray, Sealer and Stain-Blocker Aerosol, etc. | 162.04 | 0 | 162.04 | 11134
15 | 10 | Misc. Shower/Surround Install Material | From Home Depot - All Surface Construction Adhesive, Furring Strip Board, etc. | 190.53 | 0 | 190.53 | 11135
15 | 10 | Misc. Shower/Surround Install Material | From Home Depot - Kitchen and Bath Sealant White | 449.24 | 0 | 449.24 | 11149
15 | 10 | Misc. Shower/Surround Install Material | From Home Depot - Kitchen and Bath Sealant White | 449.24 | 0 | 449.24 | 11167
15 | 10 | Misc. Shower/Surround Install Material | From Home Depot - Window and Door Sealant White | 132.19 | 0 | 132.19 | 11169
15 | 10 | Misc. Shower/Surround Install Material | From Home Depot - Painter's Tape, Epoxy and Adhesives & Fiberglass Resins | 71.63 | 0 | 71.63 | 11192
15 | 11 | FF&E Installation | From Home Depot - Blue Medium Duty Tarp | 104.35 | 0 | 104.35 | 11044
15 | 11 | FF&E Installation | From Home Depot - Wood Moving Dolly | 66.64 | 0 | 66.64 | 11046
15 | 11 | FF&E Installation | From Home Depot - Blue Medium Duty Tarp | 269.52 | 0 | 269.52 | 11047
15 | 11 | FF&E Installation | From Home Depot - Bidirectional Break Shim & Painters Multi-Tool | 31.2 | 0 | 31.2 | 11116
15 | 11 | FF&E Installation | From Home Depot - Reversible Drill & Multi-Tool Oscillating Blade, etc. | 328.12 | 0 | 328.12 | 11117
15 | 11 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 1187.5 | 0 | 1187.5 | 11121
15 | 11 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 1068.75 | 0 | 1068.75 | 11122
15 | 11 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 1235 | 0 | 1235 | 11123
15 | 11 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 1068.75 | 0 | 1068.75 | 11124
15 | 11 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 1187.5 | 0 | 1187.5 | 11125
15 | 11 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 690 | 0 | 690 | 11126
15 | 11 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 780 | 0 | 780 | 11127
15 | 11 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 690 | 0 | 690 | 11128
15 | 11 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 1280 | 0 | 1280 | 11129
15 | 11 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 735 | 0 | 735 | 11130
15 | 11 | FF&E Installation | From Home Depot - Stretch Wrap | 324.62 | 0 | 324.62 | 11131
15 | 11 | FF&E Installation | From Home Depot - Oscillating Blade, Thread Coated Exterior Wood Screws, etc. | 132.81 | 0 | 132.81 | 11133
15 | 11 | FF&E Installation | From TKG Construction | 25000 | 0 | 25000 | 11146
15 | 11 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 495 | 0 | 495 | 11147
15 | 11 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 1725 | 0 | 1725 | 11148
15 | 11 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 1725 | 0 | 1725 | 11152
15 | 11 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 1520 | 0 | 1520 | 11153
15 | 11 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 2500 | 0 | 2500 | 11156
15 | 11 | FF&E Installation | From Home Depot - Markers & Wax Crayons | 13.43 | 0 | 13.43 | 11166
15 | 11 | Granite Installation | From Home Depot - All-Purpose Acrylic Latex Caulk | 264.02 | 0 | 264.02 | 11191
15 | 11 | Granite Installation | From Home Depot - Construction Adhesive, Japanese Hardwood Blade | 99.56 | 0 | 99.56 | 11196
15 | 11 | FF&E Installation | From Home Depot - Hex Drive Stainless Steel Lag Screw | 102.86 | 0 | 102.86 | 11206
15 | 11 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 1117.5 | 0 | 1117.5 | 11212
15 | 11 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 1237.5 | 0 | 1237.5 | 11213
15 | 11 | Granite Material & Labor | From TKG Construction | 30000 | 0 | 30000 | 11214
15 | 11 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 630 | 0 | 630 | 11219
15 | 11 | FF&E Labor | Unloading, Clean Up, & Other Misc. Tasks | 1202.5 | 0 | 1202.5 | 11220
15 | 15 | Mechanical | From Home Depot - Indoor/Outdoor Wireless Thermometer & Acurite Monitor | 136.91 | 0 | 136.91 | 11113
15 | 15 | Guest Room Thermostats | From Supply House | 6724.97 | 0 | 6724.97 | 11224
15 | 15 | Thermostats | From Jackson B2C | 5169.67 | 0 | 5169.67 | [TBD]
15 | 15 | Thermostats - Refund | From Jackson B2C | -5169.67 | 0 | -5169.67 | [TBD]
15 | 16 | Electrical Material | From Home Depot - Electrical Nonmetallic Tubing & Black Oxide Step Drill Bit | 323.18 | 0 | 323.18 | 11074
15 | 16 | Electrical Material | From Home Depot - Electrical Nonmetallic Tubing | 51.96 | 0 | 51.96 | 11076
15 | 16 | Electrical Material | From Home Depot - Indoor Multi-Outlet Extension Cord with Banana Tap | 59.38 | 0 | 59.38 | 11115
15 | 16 | Electrical Material | From Home Depot - Extension Cords and Appliance Replacement Cord | 1251.87 | 0 | 1251.87 | 11173
15 | 16 | Electrical Material | From Home Depot - Extension Cords and Appliance Replacement Cord | 300.5 | 0 | 300.5 | 11179
15 | 16 | Electrical Material | Elliott Electric | 24792.5 | 0 | 24792.5 | 11223
15 | 17 | General Liability Insurance | General Liability Insurance | 2479.45 | 0 | 2479.45 | [TBD]
15 | 17 | General Liability Insurance | General Liability Insurance | 2479.45 | 0 | 2479.45 | [TBD]
15 | 17 | Equipment Insurance | From Liberty Mutual | 170.23 | 0 | 170.23 | [TBD]
15 | 17 | Equipment Insurance | From Liberty Mutual | 170.23 | 0 | 170.23 | [TBD]
15 | 1 | Job Supervisor | For November 2025 | 10000 | 0 | 10000 | NA
15 | 1 | Project Manager | Boulder Construction - For November 2025 | 3888.8889 | 0 | 3888.8889 | NA
15 | 1 | Job Accounting / Administration | Boulder Construction - For November 2025 | 3611.1111 | 0 | 3611.1111 | NA
15 | 1 | Job Supervisor | For December 2025 | 10000 | 0 | 10000 | NA
15 | 1 | Project Manager | Boulder Construction - For December 2025 | 3888.8889 | 0 | 3888.8889 | NA
15 | 1 | Job Accounting / Administration | Boulder Construction - For December 2025 | 3611.1111 | 0 | 3611.1111 | NA
15 | 8 | Door Install Labor | From TKG Construction | 35000 | 0 | 35000 | [TBD]
15 | 9 | Vinyl for Floors 1 to 4 | From RFM Ventures - Pay App 06 (Final Payment) | 39805.56 | 3980.56 | 35825 | 11155
15 | 9 | ACT Floor 1 | From RFM Ventures - Pay App 06 (Final Payment) | 26000 | 2600 | 23400 | 11155
15 | 11 | Change Order - FF&E Installation | From TKG Construction | 18000 | 0 | 18000 | [TBD]
15 | 11 | Tub/Shower Surround Installation | From TKG Construction | 17000 | 0 | 17000 | [TBD]
15 | 14 | Fire Sprinkler Trim | From Safe Life FP (Invoice 04) | 10000 | 1000 | 9000 | 11225
15 | 15 | HVAC/Mechanical Material and Labor | From Iceberg Heating & AC - Pay App 07 | 14341.29 | 2136.998 | 12204.292 | 11217
15 | 15 | HVAC/Mechanical Material and Labor | From Iceberg Heating & AC - Pay App 07 | 7028.69 | 0 | 7028.69 | 11217
15 | 15 | HVAC/Mechanical Material and Labor | From Iceberg Heating & AC - Pay App 08 | 5650.88 | 0 | 5650.88 | 11218
15 | 15 | HVAC/Mechanical Material and Labor | From Iceberg Heating & AC - Pay App 08 | 2446.45 | 0 | 2446.45 | 11218
15 | 15 | HVAC/Mechanical Material and Labor | From Iceberg Heating & AC - Pay App 08 | 1407.87 | 0 | 1407.87 | 11218
15 | 15 | HVAC/Mechanical Material and Labor | From Iceberg Heating & AC - Pay App 08 | 12831.99 | 0 | 12831.99 | 11218
15 | 15 | HVAC/Mechanical Material and Labor | From Iceberg Heating & AC - Pay App 08 | 93662.81 | 11600.002 | 82062.808 | 11218
15 | 18 | Contractor's Fee | Boulder Construction - For November 2025 | 16666.6667 | 1666.6667 | 15000 | NA
15 | 18 | Contractor's Fee | Boulder Construction - For December 2025 | 16666.6667 | 1666.6667 | 15000 | NA
16 | 1 | Misc. Jobsite Material Expenses | From Home Depot - Diesel Exhaust Fluid | 20.52 | 0 | 20.52 | 11136
16 | 1 | Jobsite Storage Container - Recurring Rental | From Willscott | 190.52 | 0 | 190.52 | 11210
16 | 1 | Jobsite Office - Recurring Rental | From Willscott | 921.75 | 0 | 921.75 | 11226
16 | 1 | Jobsite Storage Container - Recurring Rental | From Willscott | 214.06 | 0 | 214.06 | 11229
16 | 1 | Temporary Toilets | From A-1 Little John | 954.77 | 0 | 954.77 | 11230
16 | 1 | Jobsite Storage Container - Recurring Rental | From Willscot | 187.27 | 0 | 187.27 | 11236
16 | 1 | Jobsite Storage Container - Recurring Rental | From Willscott | 187.27 | 0 | 187.27 | 11248
16 | 1 | Jobsite Storage Container - Recurring Rental | From Willscott | 187.27 | 0 | 187.27 | 11249
16 | 1 | Jobsite Dumpster | From City of Waxahachie | 3439.37 | 0 | 3439.37 | 11272
16 | 1 | Construction Site Camera | From Birdseye Surveillance LLC | 1299 | 0 | 1299 | 11274
16 | 1 | Construction Site Camera | From Birdseye Surveillance LLC | 1299 | 0 | 1299 | 11275
16 | 1 | Construction Site Camera | From Birdseye Surveillance LLC | 1515.5 | 0 | 1515.5 | 11277
16 | 1 | Jobsite Labor | From Rodolfo Rios | 1187.5 | 0 | 1187.5 | 11293
16 | 1 | Jobsite Labor | From Rodolfo Rios | 1306.25 | 0 | 1306.25 | 12170
16 | 1 | Jobsite Labor | From David Salinas | 795 | 0 | 795 | 12171
16 | 1 | Jobsite Labor | From Rodolfo Rios | 1068.75 | 0 | 1068.75 | 12172
16 | 1 | Jobsite Labor | From David Salinas | 525.5 | 0 | 525.5 | 12173
16 | 1 | Procore | For Jobsite Reporting | 8859.8 | 0 | 8859.8 | 12180
16 | 1 | Jobsite Storage Container - Recurring Rental | From Willscott | 214.06 | 0 | 214.06 | [TBD]
16 | 1 | Jobsite Storage Container - Recurring Rental | From Willscott | 190.52 | 0 | 190.52 | [TBD]
16 | 1 | Jobsite Storage Container - Recurring Rental | From Willscott | 190.52 | 0 | 190.52 | [TBD]
16 | 1 | Jobsite Storage Container - Recurring Rental | From Willscott | 172.33 | 0 | 172.33 | [TBD]
16 | 1 | Jobsite Storage Container - Recurring Rental | From Willscott | 172.33 | 0 | 172.33 | [TBD]
16 | 1 | Misc. Jobsite Material Expenses | From Lowe's | 41.09 | 0 | 41.09 | [TBD]
16 | 1 | Jobsite Storage Container - Recurring Rental | From Willscott | 190.52 | 0 | 190.52 | [TBD]
16 | 1 | Jobsite Dumpster | From City of Waxahachie | 2105.22 | 0 | 2105.22 | [TBD]
16 | 1 | OpenSpace Camera - Battery | From Amazon | 86.58 | 0 | 86.58 | [TBD]
16 | 1 | OpenSpace Camera - SD Card | From Amazon | 123.08 | 0 | 123.08 | [TBD]
16 | 1 | OpenSpace Camera - Cover | From Amazon | 6.48 | 0 | 6.48 | [TBD]
16 | 1 | Jobs Supervisor Equipment Accessories | From Amazon | 37.88 | 0 | 37.88 | [TBD]
16 | 1 | OpenSpace Camera - Stick | From Amazon | 20.56 | 0 | 20.56 | [TBD]
16 | 1 | Meals & Fuel | For Jobsite Travel | 818.96 | 0 | 818.96 | [TBD]
16 | 1 | Misc. Jobsite Expenses (Softwares, etc.) - True Up | Takeoffs, Scheduling / Forecasting, Punch Lists, etc. | 948.46 | 0 | 948.46 | [TBD]
16 | 1 | Cellular Data & WiFi for Jobsite Office | From Google Fi | 269.16 | 0 | 269.16 | [TBD]
16 | 1 | Cellular Data & WiFi for Jobsite Office | From Google Fi | 269.16 | 0 | 269.16 | [TBD]
16 | 1 | Cellular Data & WiFi for Jobsite Office | From AT&T | 412.84 | 0 | 412.84 | [TBD]
16 | 1 | Misc. Jobsite Expenses | From Google One | 10.65 | 0 | 10.65 | [TBD]
16 | 1 | Fuel | From Racetrac | 99.63 | 0 | 99.63 | [TBD]
16 | 1 | Fuel | From Racetrac | 94.54 | 0 | 94.54 | [TBD]
16 | 1 | Fuel | From QT | 184.66 | 0 | 184.66 | [TBD]
16 | 1 | Meals & Fuel | For Jobsite Travel | 162.59 | 0 | 162.59 | [TBD]
16 | 1 | Fuel | From Circle K | 91.62 | 0 | 91.62 | [TBD]
16 | 1 | Misc. Wire and ACH Fees for RIW | From Austin Bank for Wires and ACH | 153.6 | 0 | 153.6 | NA
16 | 2 | Earthwork - SW3P | From Cardinal Strategies | 375 | 0 | 375 | 11252
16 | 2 | Earthwork - SW3P | From Cardinal Strategies | 375 | 0 | 375 | 11253
16 | 2 | Sitework - Grade Stakes | From AIM Construction Services | 940 | 0 | 940 | 11263
16 | 2 | Landscaping Pay App 01 | From 4 Nature Landscape | 16000 | 0 | 16000 | 11270
16 | 2 | Jobsite Equipment | From EquipmentShare - Split | 65747.89 | 0 | 65747.89 | 12190
16 | 2 | Landscaping Pay App 03 | From 4 Nature Landscape | 65000 | 0 | 65000 | 12190
16 | 2 | Viking Fence Invoices | From Viking Fence | 576.43 | 0 | 576.43 | 12191
16 | 2 | Viking Fence Invoices | From Viking Fence | 457.36 | 0 | 457.36 | 12192
16 | 2 | Landscaping Pay App 02 | From 4 Nature Landscape | 4234 | 0 | 4234 | 12193
16 | 3 | Concrete - Retaining Walls & Perimeter Staking | From AIM Construction Services | 900 | 0 | 900 | 11262
16 | 5 | Metal Handrails For Stairs | For Go Construction - Pay App 08 | 320 | 320 | 0 | 12189
16 | 6 | Millwork 50% Final Payment | From Graniti Vicentia - Split | 43357.31 | 0 | 43357.31 | 10857
16 | 6 | Framing Material | From Home Depot - Galvanized Lag Screw | 98.11 | 0 | 98.11 | 11264
16 | 6 | Framing Labor - Misc. Punch List | For Martin Aguilar | 3425 | 0 | 3425 | 12177
16 | 7 | EFIS | From VG Stucco - Pay App 09 | 9857.1222 | 985.7122 | 8871.41 | 12178
16 | 8 | Doors Labor | From JR Construction | 2725 | 0 | 2725 | 12196
16 | 8 | Door Material | From Home Depot - Ballbearing Door Hinge | 79.21 | 0 | 79.21 | 12200
16 | 8 | Access Panels For Dog Houses | From WB Doors | 3415.29 | 0 | 3415.29 | [TBD]
16 | 9 | Flooring Material | From Home Depot - T-Hinge | 40.67 | 0 | 40.67 | 11049
16 | 9 | Flooring Material | From Home Depot - Tan Star Drive Flat-Head Wood Deck Screws | 34.19 | 0 | 34.19 | 11132
16 | 9 | Flooring Material | From Home Depot - Liquid nails, Circular Saw Blade & Head Screw | 142.21 | 0 | 142.21 | 11231
16 | 9 | Flooring Material | From Home Depot - Microfiber Refills & Multi-Purpose Microfiber Cloth | 31.34 | 0 | 31.34 | 11232
16 | 9 | Flooring Material | From Home Depot - 90-Degree Pull Elbow, Compression Coupling & One-Hole Strap | 38.4 | 0 | 38.4 | 11233
16 | 9 | Flooring Material | From Home Depot - Universal Patch and Skimcoat, Floor Adhesive & Self-Leveling Underlayment | 375.27 | 0 | 375.27 | 11235
16 | 9 | Flooring Material | From Home Depot - Adhesive & Head Toggle Bolt Anchors | 99.18 | 0 | 99.18 | 11237
16 | 9 | Flooring Material | From Home Depot - Trash Bags, Contractor Bags & Towels | 144.85 | 0 | 144.85 | 11238
16 | 9 | Flooring Material | From Home Depot - Cement Board, Grade, Outdoor Lock & Multi-Purpose Cleaner Concentrate | 862.58 | 0 | 862.58 | 11239
16 | 9 | Flooring Material | From Home Depot - Aggregate Grout & Cabinet Screw | 92.63 | 0 | 92.63 | 11240
16 | 9 | Drywall Material | From Home Depot - Drywall Anchors, Drilling Screws | 53.37 | 0 | 53.37 | 11242
16 | 9 | Flooring Material | From Home Depot - Toggle Bolt Anchors & Steel Screwdriving | 71.46 | 0 | 71.46 | 11243
16 | 9 | Flooring Material | From Home Depot - Super Hold Glue, Socket Wrench & Twist Drill | 243.94 | 0 | 243.94 | 11245
16 | 9 | Flooring Material | From Home Depot - Contractor Grade Tan Masking Tape | 19.01 | 0 | 19.01 | 11250
16 | 9 | Flooring Material | From Home Depot - Thermoplastic Rubber Wall Coil & Floor Adhesive | 465.22 | 0 | 465.22 | 11251
16 | 9 | Paint Material | From PPG Paints | 15784.59 | 0 | 15784.59 | 11254
16 | 9 | Flooring Material | From Home Depot - String Mop, Dust Flat Mop, Contractor Bags & Scrub Brush | 160.51 | 0 | 160.51 | 11255
16 | 9 | Flooring Material | From Home Depot - Thinset Mortar | 498.98 | 0 | 498.98 | 11256
16 | 9 | Flooring Material | From Home Depot - Thinset Mortar | 498.98 | 0 | 498.98 | 11257
16 | 9 | Flooring Material | From Home Depot - Wood Subfloors | 137.08 | 0 | 137.08 | 11259
16 | 9 | Flooring Material | From Home Depot - Wood Subfloors | 228.46 | 0 | 228.46 | 11260
16 | 9 | Flooring Material | From Home Depot - Canister Vacuum, Floor Protection & Painter's Tape | 899.95 | 0 | 899.95 | 11261
16 | 9 | Flooring Material | From Home Depot - Glazed Ceramic Floor and Wall Tile | 2112.56 | 0 | 2112.56 | 11265
16 | 9 | Paint Material | From Lowe's - Ultracolor Plus | 562.47 | 0 | 562.47 | 11266
16 | 9 | Paint Material | From Lowe's - Ultracolor Plus & Horseshoe Spacer | 381.6 | 0 | 381.6 | 11267
16 | 9 | COs | From TKG Construction | 28500 | 0 | 28500 | 11285
16 | 9 | Flooring Labor | From TKG Construction | 1500 | 0 | 1500 | 11285
16 | 9 | Flooring Labor | From TKG Construction | 15000 | 0 | 15000 | 11285
16 | 9 | Drywall Material | From Home Depot - Drywall Material | 70.72 | 0 | 70.72 | 11287
16 | 9 | Paint Material | From Lowe's - Ultracolor Plus & Flex | 269.37 | 0 | 269.37 | 12169
16 | 9 | Corner Guards | From Inpro Corporation | 2960.47 | 0 | 2960.47 | 12194
16 | 9 | Paint Material | From Sherwin Williams | 707.53 | 0 | 707.53 | 12195
16 | 9 | Painting Material | From Home Depot - Multi Surface Painter's Tape | 92.64 | 0 | 92.64 | 12197
16 | 9 | Flooring Material | From Home Depot - Waterproof & Crack Prevention Membrance | 383.19 | 0 | 383.19 | 12199
16 | 9 | Carpet Installation | From Home Depot - Self Adhesive Film & Stretch Wrap | 198.39 | 0 | 198.39 | 12201
16 | 9 | Flooring Material | From Home Depot - Thinset Mortar & Thermoplastic Rubber Base Coil | 622.5 | 0 | 622.5 | 12202
16 | 9 | Paint Material | From Lowe's - Masking Tape | 115.89 | 0 | 115.89 | [TBD]
16 | 9 | Flooring Material | From C&C Wholesale | 356.36 | 0 | 356.36 | [TBD]
16 | 9 | Flooring Material | From Surface Material | 775.69 | 0 | 775.69 | [TBD]
16 | 9 | Flooring Material | From C&C Wholesale | 1241.94 | 0 | 1241.94 | [TBD]
16 | 9 | Flooring Material | From C&C Wholesale | 1628.06 | 0 | 1628.06 | [TBD]
16 | 9 | Flooring Material | From C&C Wholesale | -1241.94 | 0 | -1241.94 | [TBD]
16 | 9 | Flooring Material | From Surface Material | 530.96 | 0 | 530.96 | [TBD]
16 | 9 | Flooring Material | From C&C Wholesale | 332.54 | 0 | 332.54 | [TBD]
16 | 9 | Flooring Material | From C&C Wholesale | 332.54 | 0 | 332.54 | [TBD]
16 | 9 | Flooring Material | From C&C Wholesale | 2704.41 | 0 | 2704.41 | [TBD]
16 | 9 | Flooring Material | From Floor & Décor | 339.65 | 0 | 339.65 | [TBD]
16 | 10 | Misc. Shower/Surround Install Material | From Home Depot - Tub and Tile Silicone Caulk & Window, Door and Trim Sealant | 82.67 | 0 | 82.67 | 11228
16 | 10 | BBQ Grill | From BBQ | 4847.47 | 0 | 4847.47 | 11246
16 | 10 | Misc. Shower/Surround Install Material | From Home Depot - Steel Enhancing Polish, Window and Door Sealant | 194.96 | 0 | 194.96 | 11247
16 | 10 | Fire Extinguisher Cabinets | From Texas Fire Extinguisher | 5306.72 | 0 | 5306.72 | 11271
16 | 10 | Misc. Shower/Surround Install Material | From Home Depot - Kitchen & Bath Sealant White | 278.51 | 0 | 278.51 | 12198
16 | 10 | Caulking Material | From Jordan Toplano | 533 | 0 | 533 | [TBD]
16 | 11 | Granite Installation | From Home Depot - Sanded Ceramic Tile Caulk | 11.4 | 0 | 11.4 | 11227
16 | 11 | Granite Installation | From Home Depot - Acrylic Latex Plus Silicone Caulk | 684.43 | 0 | 684.43 | 11241
16 | 11 | Granite Installation | From Home Depot - Steel Round Tube, Head Screw, Spray Paint & Primer | 122.8 | 0 | 122.8 | 11244
16 | 11 | Granite Installation | From Home Depot - Adhesive & Circular Saw Blade | 106.49 | 0 | 106.49 | 11268
16 | 11 | Granite Glue and Caulking | From Gran Quartz | 1485.03 | 0 | 1485.03 | [TBD]
16 | 12 | Millwork 50% Final Payment | From Graniti Vicentia - Split | 11769.86 | 0 | 11769.86 | 10857
16 | 12 | Elevator Material & Installation Labor | From Kone - Allocated Payment Pay App 04 | 25651.2889 | 2565.1289 | 23086.16 | 12176
16 | 12 | Jobsite Equipment | From EquipmentShare - Split | 3495.72 | 0 | 3495.72 | 12190
16 | 12 | Safety Net for Elevator | From Amazon | 204.95 | 0 | 204.95 | [TBD]
16 | 15 | Wall Mounted Fire Place Heater w/Thermostat | From Amazon | 649.48 | 0 | 649.48 | 12175
16 | 16 | Electrical Material | From Home Depot - Electrical Tape & Electrical Switch and Outlet Box | 213.58 | 0 | 213.58 | 11234
16 | 16 | Electrical - Light Pole Staking | From AIM Construction Services | 720 | 0 | 720 | 11273
16 | 16 | Electrical Material | From Home Depot - PVC Conduit, Cable Zip & Electrical Tape | 148.42 | 0 | 148.42 | 11282
16 | 16 | Light Pole Removal and Relocation | From Oncor Electric Delivery Company LLC | 5003.22 | 0 | 5003.22 | 11284
16 | 17 | Builder's Risk Insurance | Liberty Mutual | 3454.07 | 0 | 3454.07 | [TBD]
16 | 17 | Builder's Risk Insurance | Liberty Mutual | 3454.07 | 0 | 3454.07 | [TBD]
16 | 17 | Builder's Risk Insurance | Liberty Mutual | 3454.23 | 0 | 3454.23 | [TBD]
16 | 17 | Equipment Insurance | From Liberty Mutual | 170.23 | 0 | 170.23 | [TBD]
16 | 17 | General Liability Insurance | Newman & Trucker | 3893.43 | 0 | 3893.43 | [TBD]
16 | 17 | General Liability Insurance | Newman & Trucker | 3893.43 | 0 | 3893.43 | [TBD]
16 | 1 | Job Supervisor | For January 2026 | 10000 | 0 | 10000 | NA
16 | 3 | Concrete - Testing & Inspections | From Geoscience Engineers LLC | 855 | 0 | 855 | 12179
16 | 3 | Backfill and Grading | From T18 Construction LLC | 7500 | 750 | 6750 | 12181
16 | 3 | Concrete | From M D Bowles Construction - Pay App 10 | 20500 | 0 | 20500 | 12185
16 | 7 | EFIS | From VG Stucco - Pay App 10 | 27483 | 600 | 26883 | 12188
16 | 8 | Doors and Hardware Install | From TKG Construction | 500 | 0 | 500 | 11285
16 | 9 | Flooring Labor | From TKG Construction | 18320 | 0 | 18320 | 11285
16 | 9 | Deliveries & Repairs | From TKG Construction | 23500 | 0 | 23500 | 11285
16 | 10 | Caulking Material | From ESSA Group of America | 519.6 | 0 | 519.6 | 11216
16 | 10 | Shower Door Install | From TKG Construction | 13750 | 0 | 13750 | 11285
16 | 10 | Bathroom Hardware Install | From TKG Construction | 7500 | 0 | 7500 | 11285
16 | 11 | Guestroom Granite Install | From TKG Construction | 24000 | 0 | 24000 | 11285
16 | 11 | Tub/Shower Surrounds and Pan Install | From TKG Construction | 9500 | 0 | 9500 | 11285
16 | 12 | FF&E Installation | From TKG Construction | 5000 | 0 | 5000 | 11285
16 | 15 | Plumbing | From MA Williams Plumbing - Pay App 05 | 200000 | 20000 | 180000 | 12182
16 | 15 | HVAC/Mechanical Material and Labor | From Iceberg Heating and AC - Pay App 10 | 147166.03 | 14716.603 | 132449.427 | 12184
16 | 16 | Structured Cabling | From PSM Tech LLC - Pay App 02 | 37500 | 3750 | 33750 | 12183
16 | 16 | Electrical Labor | From GMC Electric - Pay App 09 | 20000 | 2000 | 18000 | 12186
Note on J1109: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pay App needs to be revised upward by $500 before Docusign. Actual Retainage Amount for Past Draw is $34,335 instead of $33,835.
Note on J1169: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to get Pay App from the Sub-Contractor
Note on J1176: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pay App needs to be revised upward by $500 before Docusign. Actual Retainage Amount for Past Draw is $34,335 instead of $33,835.
Note on J1178: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pay App needs to be revised upward by $500 before Docusign. Actual Retainage Amount for Past Draw is $34,335 instead of $33,835.
Note on J1179: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pay App needs to be revised upward by $3,000 before Docusign. Actual Gross Amount for Past Draw is $80,848 instead of $70,848.